## Customer Support
Week | Team | Apps Engineer | Effort (man- days) | Total Effort | Segment | Customer | Family | Part | Customer Phase | MP Date | Product | LTR ($M) | GIBC | Module | Tools | Request brief | Progress record | Root cause | Solution | Support Type | Input Source | Community Link (Mandatory)

## Apps Lead
Week | Team | Apps Engineer | Open Date | Close Date | Effort (man- days) | Total Effort | Family | Project | NPI Phase | Next Apps Milestone | TO Date | Enablement Task | Highlight/Lowlight/Issues/Risks | Progress record
WW01 | William | Guo Jia | 2015/11/10 |  |  | 2 | Kinetis L | KL28 | Execution |  |  | Board |  | 1. Updated the MOSFEF chip according to the suggestion from core team.
WW01 | Eric | Wang Ben | 2015/11/23 |  | 0.5 |  | Kinetis E | MT512P | Execution |  | Q1'16 | Board | Execution: TWR layout - 1/7 | 1.TWR-KE18F layout is on-going,target to finish and send out for review on about 1/7. 2.Design schedule is on track, TO still on 1/12. 3.Core team reviewed the CR of extend temperature range to 125C.
WW01 | Eric | Wang Ben | 2015/11/30 |  | 1.5 |  | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases |  | 1.Pre-coding MT256P usecases, do some testing on MA512 TWR.
WW01 | Eric | Cao Nan | 2015/12/7 | 2015/12/31 | 2 |  | Kinetis K | KS22_256R | Execution |  | Q3'15 | System Engineering |  | Finished recording the getting started video. Will publish to Web soon.
WW01 | Eric | Chen Xinyu | 2015/10/10 |  | 0.5 |  | Kinetis K | KS22_256R | Execution |  | Q3'15 | Documentation | Execution: Publish ANs - 1/8 | 1. Double checked the final production MAPS-KS22 board, the OOBE and CMSIS-DAP firmware is correct. Updated the QSG for this updated firmware. 2. Still driving how to get the MAX IDD data for datasheet.
WW01 | Eric | Chen Xinyu | 2015/12/24 |  | 2 |  | Kinetis E | KE15Z | Plan |  | Q4'15 | System Cases |  | Finished pre-coding and porting for adc_lpit_trgmux, adc_pdb_trigger, flexio_pwm, lpi2c_vlps, trgmux_clone_pwm use cases
WW01 | Eric | Chen Yonggang | 2015/12/28 | 2015/12/29 | 2 |  | Kinetis E | KE18F512VLL15 | Execution |  | Q2'15 | System Cases | Execution: Alpha customer support - 12/30 | 1. Bring up Spansion FM4-U120-9B560 demo board successfully, edit GPIO toggle code in IAR7.4, and download via an on board debugger CMSIS-DAP. Porting motor control FOC code to Spansion demo board, in order to compare the performance with KE18F. 2. Searched the CoreMark result of Spansion FM4 9B serires MCU is 3.37 CoreMark/MHz at 160MHz.
WW01 | Eric | Chen Yonggang | 2015/12/25 | 2015/12/27 | 2 |  | Kinetis E | KE15Z | Plan |  | Q4'15 | Board | Exection: EMC Board Design - 12/30 | 1. Finished FRDM-TOUCH layout reviewed, and updated schematic/layout according to marketing's comments. The final layout is released for board building. 2. Reviewed KE value point document. 3. Tested the original Fotile IH Cooder C21FW, but failed to ESD Contact Discharge 6KV test. Checked with FAE, customer Fotile standard is GB-4076.1-2015: Contact Discharge 4KV, Air Discharge 8KV, EFT 4KV.
WW01 | Richy | Howard Liu | 2015/7/16 |  | 3 | 50.5 | Kinetis E | KE18F512VLL15 | Execution |  | Q1'16 | System Cases |  | 3in1 system timing evaluation: 1) Implemented the 3in1 system timing as expectation including PWM synchronization with specific phase shift among motor 1, motor 2 and PFC. The test result proves the system design feasible for 3in1 outdoor unit. 2) The test points aren't wired on the PCB even they are connected to chip in the schematic. Some other interfaces were used for GPIO toggle show the system timing. Found PTE0/PTE1 default settings are inconsistent with RM doc on pull enable control. 3) Found a limitation about the PDB triggering ADC sequence. ADC result registers MUST be read before next h/w trigger from PDB, otherwise the PDB will report channel sequence error. We cannot say it a bug but the document should note this limitation. Alpha customer support: For KE1xF performance issue reported from customer, there's still no further update from Japan FAE. In order to measure the generic FOC performance on KE1xF, modified the motor control state machine to remove all h/w related code and create the pure software FOC test code to measure the time consumed by FOC algorithm. The result is about 11.28us @150MHz with cache enabled and putting data on SRAM_U. Jonson sent the detailed test report. The performance is improved greatly comparing with the KV3 @100MHz with 64bit FMC executed from FLASH (KV30) = ~35usec and KV4 @150MHz with 128bit FMC executed from FLASH (KV40) = ~25usec
WW02 | William | Guo Jia | 2015/11/10 |  |  | 2 | Kinetis L | KL28 | Execution |  |  | Board |  | Updated the schematic according to the feedback from core team. The review is still going on.
WW02 | William | WP | 2015/11/13 | 2016/1/18 | 2 |  | Kinetis L | KL80 | Launching | Launch: OOBE materials - 1/18 |  | Documentation |  | 1. Review user guide of twr-kl82z72m and FRDM_KL82Z, add some comments, and expect to finalize it next Monday. 2. Create the Quick start package of twr-kl82z72m and FRDM_KL82Z, and deliver to launch marketing.
WW02 | william | YangXi | 2015/1/5 |  | 1 |  | Kinetis L | KL28 | Execution |  |  | Board |  | 1. Update schematic, add pull-up register on openSDA UART-TX pin, update PKL28 to MKL28 for production.
WW02 | Eric | Wang Ben | 2015/11/23 |  | 1.5 |  | Kinetis E | MT512P | Execution | TWR-KE18F layout release - 1/15 | Q1'16 | Board | MA512 found sosc duty and output issue when low gain/high gain switch. The same issue should exists on MT512P, because of same sosc IP used. Design team is doing timing simulation and work out one software workaround. MT256P PESD result is not good, which will impact MT512P TO on 1/12 per original schedule. | 1. TWR-KE18F layout is finished and reviewed this week. Some comments are provided to update, target to release to Agile for fabrication on 1/15. 2. HVP-KE18F schematic is done and start to layout from next week. 3. MA512 found sosc duty and output issue when low gain/high gain switch. The same issue should exists on MT512P, because of same sosc IP used.Design team is doing timing simulation and work out one software workaround. 4. MT256P PESD result is not good,which will impact MT512P TO on 1/12 per original schedule.
WW02 | Eric | Wang Ben | 2015/12/30 |  | 3 |  | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases |  | Pre-coding MT256P usecases, 80% is finished. Will do the silicon test after get the chips and FRDM board.
WW02 | Eric | Chen Xinyu | 2015/10/10 |  | 4 |  | Kinetis K | KS22_256R | Launching | Publish ANs - 1/15 | Q3'15 | Documentation |  | 1. Discussed with PE/TE/Marketing/System about the how to get MAX IDD data for datasheet. Come out a rough schedule Mar. 25th for PE/TE to finished the data. 2. Drafted out the "Using LPI2C in STOP low power mode" Application Note, and send for internal review. 3. Two AN "Wakeup system from LLSx mode by USB device" and "Emulating Dual SPI By Using FlexIO" are under doc team's review. Hope to publish this week. 4. Published the MAPS-KS22 Gettings Start video on Web.
WW02 | Eric | Chen Yonggang | 2016/1/4 | 2016/1/6 | 2 |  | Kinetis E | KE18F512VLL15 | Execution | Alpha customer support - 1/30 | Q2'15 | System Cases |  | 1. Summarized the performance report of KE18F and competitor Spansion MB9 uner different core clock and Cache enabled/disabled. KE18F is slightly faster than Spansion MB9 with both Cache enable but slower with both Cache disabled. Marketing is asking Jap FAE to get customer Daikin's code for further benchmark. 2. Bought Renesas RX62T for analysis if needed. Renesas RX62T is the platform that customer Daikin using currently.
WW02 | Eric | Chen Yonggang | 2016/1/6 | 2016/1/8 | 3 |  | Kinetis E | KE15Z | Plan | Use Cases Validation - 1/30 | Q4'15 | Board | The preliminary PESD test shows bad performance: -3KV demaged which would cause MT512P TO hold. | 1. The preliminary PESD test shows bad performance: -3KV demaged which would cause MT512P TO hold. 2. The overlay design of FRDM-TOUCH is done, and passed review by Marketing. 3. Reviewed the KSDK TSI driver and example code, added 10 comments 4. Got the FRDM-KE15Z and EMC test board PCBA, will finish sample manual solder this week.
WW02 | Richy | Howard Liu | 2015/7/16 |  | 4 | 51.5 | Kinetis E | KE18F512VLL15 | Execution |  | Q1'16 | System Cases |  | 13in1 system timing evaluation: 1) The phase relationship of 3 PWM frequencies were accurately implemented, captured the phase relationship diagram through oscilloscope. Tuned the control timing and interrupt schedule time point so that the ADC result can be read correctly. 2) Checked the GPIO toggle issue that the compiler optimization causes different GPIOs having different results. 3) Measured the accurate timing of ISR start time for different control loops that are exactly consistent with the design expectation. 4) Completed the slides of the first version of 3in1 system timing on KE1xF including the designed timing and the implemented timing and gave the evaluation result that the system is feasible for 3in1 A/C outdoor unit. Alpha customer support: Asked Japan FAE to have double check with customer to understand their test method well so that we can find the root cause of big gap between KE1xF and the competitor's chip. Now we didn't get any obvious performance gab here.
WW03 | william | WP | 2015/11/13 | 2016/1/18 | 1 |  | Kinetis L | KL80 | Launching | Launch: OOBE materials - 1/18 |  | Documentation |  | 1. Review AN "how to use QSPI on KL8x series", add the comments and finalize it.
WW03 | william | Guo Jia | 2015/11/10 |  |  | 2 | Kinetis L | KL28 | Execution |  |  | Board |  | Updated the schematic according to the feedback from core team. The review is still going on.
WW03 | Eric | Wang Ben | 2015/11/23 |  | 1.5 |  | Kinetis E | MT512P | Execution | HVP-KE18F layout -1/27 | Q1'16 | Board | TO on hold due to PESD issue reported on MT256P. FA is in progress. | 1.TO on hold due to PESD issue reported on MT256P. FA is in progress. 2.TWR-KE18F schematic and layout are finalized and uploaded to Agile. Reviewed the BOM quotation with Sammy. Some NXP samples are applied freely for board cost down. 3.HVP-KE18F schematic is done and layout is ongoing. 4.Reviewed and signoff the rev0 DS for TO stage use. Provided ~17 comments. 5.Updated the use cases list for team review.
WW03 | Eric | Wang Ben, Chen Xinyu | 2015/10/10 |  | 2 |  | Kinetis K | KS22_256R | Launching | Get MAX IDD from PE - 3/25 | Q3'15 | Documentation |  | 1. Revised and published the AN of "Emulating Dual SPI by using FlexIO" and "Wakeup system from LLS by USB device" after Doc team's review. 2. Reviewed the chapter 6(Clock distribution) of KS22 RM CHN version translation.Provided ~40 comments. 3. Submit the "Using LPI2C in STOP mode" to the doc team for review.
WW03 | Eric | Chen Yonggang | 2016/1/11 | 2016/1/13 | 2 |  | Kinetis E | KE18F512VLL15 | Execution | Alpha customer support - 1/30 | Q2'15 | System Cases |  | 1. Jap FAE reported that the customer Daikin decided to continue using Renesas RX62T and stop change MCU platform for 1st project, Oct’16 production model (oversea market - 200ku/y). KE1xF target is changed to the 2nd project which starts production from Dec’16 or Jan’17. 2. Brought up gpio/timer functions on Renesas RX62T board. But the Renesas board can't run motor control library due to the different IDE platform checked with motor control team. Plan to port CoreMark to benchmark performance this week. 3. Support Jap FAE prepare a technical seminar to Mitsubishi(on Jan/20), anwsered several technical questions about LPI2C.
WW03 | Eric | Chen Yonggang | 2016/1/13 | 2016/1/15 | 3 |  | Kinetis E | KE15Z | Plan | Use Cases Validation - 1/30 | Q4'15 | Board | Sample delivery delayed one week, caused X-FRDM-KE15Z delay. | 1. Support FRDM-KE15Z board building. The sample is delayed 1 week because of the wrong trim value for FIRC/SIRC/FLL and ADC calibration. Now the FRDM board is uner soldering, will be ready this week, 1 week delayed. 2. Drive board cost down by DNP several connectors and find alternative for Diodes on the 2nd version of FRDM-KE15Z 3. Reviewed clock chapter for RM improvement 4. Verified scg module use case on EVB board, and report FIRC wrong trim issue to PE to make sure the sample for FRDM-KE15Z would be trimmed correctly
WW03 | Richy | Howard Liu | 2015/7/16 |  | 1.5 | 53 | Kinetis E | KE18F512VLL15 | Execution |  | Q1'16 | System Cases |  | 3in1 system timing evaluation: The APIs of latest MC libraries were greatly different from version 3.0. In order to expedite the software porting from DSC to Kinetis with latest MC lib, the porting task was divided into two steps. Porting the MC lib from Ver3.0 to Ver4.2 on the DSC platform first to verify the latest MC lib working correctly, then porting the 3in1 s/w from DSC to Kinetis. Now the structures and function calls had been changed to consistent with the new MC lib, just passed the compiling. Will calculate the PI controller parameters and rotate the real motor on DSC this weekly.
WW04 | William | Guo Jia | 2015/11/10 |  |  | 2 | Kinetis L | KL28 | Execution |  |  | Board |  | Updated the schematic according to the feedback from core team. The power circuit need to be updated. The review will be closed early this week.
WW04 | william | WP | 2015/11/13 | 2016/1/18 | 0.5 |  | Kinetis L | KL80 | Launching | Launch: OOBE materials - 1/18 |  | Documentation |  | KL82 launch on time(1/18/2016).
WW04 | william | william jiang | 2015/1/21 | 2015/1/21 | 0.5 |  | Kinetis L | KL28 | Execution | FRDM-KL28Z w/ TO 1.1-3/18/2016 |  | Bug analysis support | ROM team found FRDM-KL28Z has issue with UART data receiving and asked us to check. | Supported ROM team on the UART data receiving issue through OpenSDA virtual serial port, found it is ROM code issue that does not enable pull-up for the UART Rx pins and provided a workaround to them. This issue applies to all Kinetis ROM code and ROM team will fix it in new revision
WW04 | Eric | Wang Ben | 2015/11/23 |  | 1 |  | Kinetis E | MT512P | Execution | HVP-KE18F layout -1/27 | Q1'16 | Board | TO on hold due to PESD issue reported on MT256P. FA is in progress. | 1. TO on hold due to PESD issue reported on MT256P. FA is in progress. 2. TWR-KE18F gerber released for fabrication. 3. HVP-KE18F layout is on going. Schematic did minor update to align with layout. First draft of layout would be ready on 1/30. 4. Prepare and sent the 3in1 daughter board BOM list to Sammy for procurement quotation.
WW04 | Eric | Wang Ben, Chen Xinyu, Chen Yonggang | 2016/1/4 |  | 5 |  | Kinetis E | KE15Z | Execution | Use Cases Validation - 1/30 | Q4'15 | System Cases |  | 1. Finished and passed test of the use case: hello_world, scg_demo, dual_osc_demo, ftm_demo, lpi2c_vlps, adc_pdb_trigger, adc_lpit_trgmux, flexio_pwm, trgmux_pwm_clone and tsi_selfmode_demo on FRDM-KE15Z. 2. Found doc issues on SCG/PCC module,which will impact SDK headfile. 1)Both bus clock and flash clock come from DIVSLOW divider, DIVBUS divider should be reserved. 2)Peripheral clock source selection in PCC for LPFLL should be “101”,not “110”. 3. Found issue of ISR vector table can not be redirected after boot from BOOTROM. Confirmed with ROM team, the RCM FORCEBOOT must be reset to flash when bootup. Otherwise SCB->VTOR set is ignored. Warn the SDK team for this issue. 4. Found hard to use TRGMUX for DMA trigger, which is caused by the RM doc. Suggest to write a clear guide in TRGMUX chapter for how to trigger DMA channel with DMAMUX configurations. 5. Found FRDM-KE15Z hardware issue of lack of pull up on the level shift chip 3.3V side for I2C. 6. Found the ADC calibration is still failed, checking with system and design. 7. Reviewed the new clocking category chapters in RM,provided ~10 comments.
WW04 | Eric | Wang Ben, Chen Xinyu | 2015/10/10 |  | 1.5 |  | Kinetis K | KS22_256R | Launching | Get MAX IDD from PE - 3/25 | Q3'15 | Documentation |  | 1. Reviewed the RESET chapters of KS22 RM CHN version translation.Provided ~50 comments. 2. Reviewed the comments from Doc team on the AN of "Using LPI2C in the STOP low power mode".
WW04 | Eric | Chen Yonggang | 2016/1/22 | 2016/1/22 | 1 |  | Kinetis E | KE18F512VLL15 | Execution | Alpha customer support - 1/30 | Q2'15 | System Cases |  | 1. Support Jap FAE answer customer MITSUBISHI questions about BootROM. MITSUBISHI has developed KE1xF based board for evaluation.
WW04 | Eric | Chen Yonggang | 2016/1/18 | 2016/1/21 | 4 |  | Kinetis E | KE15Z | Plan | Use Cases Validation - 1/30 | Q4'15 | Board | Sample delivery delayed one week, caused X-FRDM-KE15Z delay. | 1. The 1st 18pcs X-FRDM-KE15Z boards are available and sent out for SDK software development and Apps use cases verification. 2. Supported FRDM-KE15Z production board cost down. Proposed competitor Renesas's one page board introduction for QSG to save box cost, and DNP several headers/diodes to save board cost. The sample is delayed 1 week because of the wrong trim value for FIRC/SIRC/FLL and ADC calibration. Now the FRDM board is under soldering, will be ready this week, 1 week delayed. 3. Updated schematic of FRDM-KE15Z to fix 2 issues found in 32K OSC and I2C sensor level-shift circuit. The schematic and PCB layout update is done and released to factory for the 2nd 114pcs board building, and the latest silicons will be sent out for board building this week. 4. Finished IH cooker board PCBA assembly and developing software, 60% done, finished TSI/LED drivers, and will finish the serial communication with the main board and bring up IH cooker whole functions this week. 5. MT256 PESD test made progress and found out the PESD damage level depends on the VDD voltage. The PESD damage level is increased when the VDD voltage is reduced. FA is going on to find the root cause on chip level.
WW04 | Richy | Howard Liu | 2015/7/16 |  | 1.5 | 54.5 | Kinetis E | KE18F512VLL15 | Execution |  | Q1'16 | System Cases |  | Alpha customer support: In order to port the pure s/w FOC code to Renesas platform, created the new pure s/w FOC package with the C source code for the MC lib functions called in the package. 3in1 system timing evaluation: The linking process was passed with the new MC lib on DSC platform. Will change the parameters to adapt to the new API this week.
WW05 | William | Guo Jia | 2015/11/10 |  | 4.5 |  | Kinetis L | KL28 | Execution |  |  | Board |  | Updated the schematic according to the feedback from core team. The power circuit need to be updated.
WW05 | Eric | Wang Ben | 2015/11/23 |  | 0.5 |  | Kinetis E | MT512P | Execution |  | Q1'16 | Board | TO on hold due to PESD issue reported on MT256P. FA is in progress. | TO still on hold due to PESD issue reported on MT256P. FA is in progress.
WW05 | Eric | Wang Ben | 2016/1/4 |  | 1.5 |  | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases |  | Finished porting the Coremark use case on FRDM-KE15Z. Get the result of 2.1 coremark/Mhz under LPFLL 72Mhz max speed w/ cache enable when code running in Flash; 2.488 coremark/Mhz when code running in SRAM. It meets system/application's expectation. KE1xZ CPU performance looks fine.
WW05 | Eric | Chen Xinyu, Fang Yizhou | 2015/10/10 |  | 2.5 |  | Kinetis K | KS22_256R | Launching | Get MAX IDD from PE - 3/25 | Q3'15 | Documentation |  | 1. Reviewed the "Kinetis Flashloader" chapters of KS22 RM CHN version translation. Raised concerns to Doc team about the bad quality of the translation, even the same word translation result is not consistent in one section. Not to mention the incorrect translations. 2. Reviewed Chapter1/2 of KS22 RM CHN version translation. 3. Published the AN of "Using LPI2C in the STOP low power mode".
WW05 | Eric | Chen Yonggang | 2016/1/25 | 2016/1/26 | 1 |  | Kinetis E | KE18F512VLL15 | Execution | Alpha customer support - 1/30 | Q2'15 | System Cases |  | 1. Support Jap FAE answer questions that customer found in clock configuration in KE1xF sample code. 2. New Opportunity: Customer: Mitsubishi Nagoya. Device: Kinetis KE14F256VLH15. Application: (1). Sub MCU for servo amp. (2). Low end inverter. Customer requirements include: FTM, ADC, PDB, 150MHz core clock, 10MHz SPI Slave mode, ECC flash/RAM. 3. KE1xF performance benchmark: (1). Jap FAE visited customer Daikin and reported the disappointed customer Compressor/Fan Motor benchmark result: Cypress(CM4F 160MHz) is 10% better than Renesas(RX62T 100MHz), but KE1xF is 10% worse than RX62T. Daikin thought the performance difference is caused by Flash access speed(Cypress 75MHz, RX62T 100MHz, KE1xF 25MHz). Action: Had conference call and Jap FAE would ask customer to change link file as we suggested.. (2). Sent Renesas RX62T boards and FOC code to FAE Steve, and he will help porting the KE1xF based FOC code to Renesas IDE.
WW05 | Eric | Chen Yonggang | 2016/1/26 | 2016/1/29 | 4 |  | Kinetis E | KE15Z | Plan | Use Cases Validation - 1/30 | Q4'15 | Board | Sample delivery delayed one week, caused X-FRDM-KE15Z delay. | 1. Finished IH cooker software development, Debugging the serial communication error with the main board. 2. MT256 PESD FA is on going. Meanwhile, IO design team made a new change as an experiment to improve PESD performance and the change was included in MT512 FEOL(front end of line) TO on Jan 29th. 3. Finished TSI self mode demo porting to sdk 2.0 4. Got the 2nd 18pcs FRDM-KE15Z with the latest samples which fixed 32K flash size issue.
WW05 | Richy | Howard Liu | 2015/7/16 |  | 3 | 57.5 | Kinetis E | KE18F512VLL15 | Execution |  | Q1'16 | System Cases |  | 3in1 system timing evaluation: 1) Changed the parameters for new API and run 3in1 with latest MC lib on DSC 3in1 h/w platform successfully. 2) Finished the the 3in1 source code porting from DSC to KE1xF. Replaced all the DSC math intrinsic functions with ARM MC math libraries, customized the low level h/w related operations with KE1xF h/w settings. Next step is to debug and test the code on the KE1xF platform. Alpha customer support: 1) Had meeting with Japan FAE team to align the customer's benchmark performance issue. two suggestions were given to Japan FAE: a) to modify the link file to have KE1xF working in the real Harvard architecture since there might be have a lot of static data in the customer performance test; b) to execute the code from the RAM to check the performance degradation due to execute from flash. 2) Sent the FOC pure s/w of ARM CM4 to FAE team. They will help with porting it to Renesas platform.
WW06 | William | William, Guo Jia | 2016/2/1 | 2016/2/5 | 2 |  | Kinetis L | L5K | Execution | FRDM-KL28Z w/ TO 1.1-3/18/2016 | Q4'15 | Board | Finalize FRDM-KL28T schematic and board schedule proposal | o Marketing decided to NOT take a dual core version of L5K to market, work that helps with K3S will be done. No NTF demo for dual core and no dual core production board needed. o Updated schematic energy monitor part and new OpenSDA part as well as power supply by the latest comment. o Had an online meeting to review the schematic for FRDM-KL28T with Alistair, Greg o Raised online sample request for FRDM-KL28Z pilot build (23 pcs full trimmed) o Worked with HW PM Sammy to propose new FRDM-KL28T schedule: schematic signoff – 2/5, layout start – 2/17, board available- 4/18
WW06 | Eric | Wang Ben | 2015/11/23 |  | 0.5 |  | Kinetis E | MT512P | Execution |  | Q1'16 | Board | TO on hold due to PESD issue reported on MT256P. FA is in progress. | 1.Frontend TO on 1/29.Backend TO will hold till 2/19. IO change will be handled by Auto IO design team. 2.HVP-KE18F layout is delayed for team review after CNY. 3.3in1 reference design board quotation is ongoing.
WW06 | Eric | Wang Ben | 2016/2/1 |  | 2 |  | S08 | MC9S08SU16 | Execution |  | Q1'16 | Documentation |  | 1.SU16 design TO on 1/26.It will do metal ECO on SD8 to fix the VREFH issue and some other design fix/improvement. Core team weekly meeting will setup after CNY. 2.Reviewed the draft RM and datasheet of SU16.There are some doc issues which need to correct in next version.
WW06 | Eric | Chen Yonggang | 2016/2/3 | 2016/2/5 | 2 |  | Kinetis E | KE18F512VLL15 | Execution | Alpha customer support - 2/30 | Q2'15 | System Cases |  | 1. Attended KE1xF performance improvement discussion and finished Renesas RX62T performance benchmark by running motor control source code. The test result shows KE1xF take 16us while Renesas RX62T take 14us under the same 100MHz core clock. 2. Delivered the motor control FOC software based on Spansion MB9 platform to Jap FAE to help them on performance benchmark.
WW06 | Eric | Chen Yonggang | 2016/2/1 | 2016/2/2 | 2 |  | Kinetis E | KE15Z | Plan | FRDM(Pilot) - 3/1 | Q4'15 | Board | Sample delivery delayed one week, caused X-FRDM-KE15Z delay. | 1. Supported the pilot version FRDM board building, drafted the FCC test plan. 2. Debugging the IH cooker functions. The touch board can't receive UART data from the main board, even tried different baud rate. 3. Delivered FRDM boards to the 3rd party companies and US FAE to support US Whirpool evaluation. 4. Discussed the board and demo code plan with Marketing for the coming US FTF. We're going to show FRDM-TOUCH board and support US AE conduct a hands-on training about the new TSI. 5. Supported the debugging of IO/Vrefh pin damage issue found by BACES team, the root cause is the power supply, not a silicon issue.
WW08 | William | Guo Jia | 2015/11/10 |  | 1 |  | Kinetis L | KL28 | Execution |  |  | Board |  | 1.Found an issue in the schematic design, and fixed it. 2.Added one feature to detect the external debugger for KL28T. 3.PCB placement is finished, and routing will get started this week.
WW08 | Eric | Wang Ben | 2015/11/23 |  | 2 |  | Kinetis E | MT512P | Execution | HVP-KE18F layout review 3/4 | Q1'16 | Board - Design |  | 1.IO change for PESD fix final released on 2/12, BEOL TO on 2/16. 2.Revisit and change the HW&SW plan based on the project schedule update. 3.HVP-KE18F layout is released and under review by team,target to be finalized by 3/4. 4.3in1 reference design board will start to do minor schematic change next week. 5.Follow up the newly found SCG issue(TKT289037),design team has reproduced the same case on MT512P and proved that another reset can make clock switcher recover.
WW08 | Eric | Chen Xinyu | 2016/2/15 |  | 0.5 |  | Kinetis K | KS22_256R | Launching |  | Q3'15 | Documentation - RM |  | 1. Collecting the general issues we found in the KS22 RM Chinese version translation. 2. Support USB IP block guide issue found by FAE, the HOST-only, Dual-mode diagram for USB power is not correct which still use internal USB regulator which removed from KS22. Asked IP owner if we can update a version of USBVDD power supply.
WW08 | Eric | Wang Ben | 2016/2/16 |  | 2.5 |  | Kinetis E | KE15Z | Execution |  | Q4'15 | System EMC |  | 1.Debug the comm issue of KE15Z IHCooker platform.It is due to KE15Z failed to initialize the relay interface, which make the MCU on IHcooker mainboard has no power.The workaround method to short relay signal to GND could make the comm succcessfully. Need further debug on the software/protocol to find the root cause.
WW08 | Eric | Wang Ben | 2016/2/1 |  | 0.5 |  | S08 | MC9S08SU16 | Execution | CW SP testing 4/11 | Q1'16 | Tools Support |  | 1.Attend the first core team meeting. No HW needed for SU16, EVB will reuse from SD8. 2.PM and AE will check with Ruth on CW SP deliverable and testing. 3.Aligned with marketing that Richy's team will take the ownership of Drone ESC reference design,it is target to be released in Q3. 4.TJN BACES team will support POR test for SU16. They will run 3 pcs SU16 samples @ 250KV/s, cover -40C, 25C and 125C.
WW08 | Eric | Chen Xinyu | 2016/2/15 |  | 0.5 |  | Kinetis K | KS22_256R | Launching |  | Q3'15 | Certification - USB |  | 1. Delivered the USB demo of HID to Ye Xian. 2. Delivered MAPS-KS22 and related documenation to Ye Xian. 3. Discussed with him, and come out a draft schedule of KS22 USB certification data: 3/21
WW08 | Eric | Chen Yonggang | 2016/2/1 | 2016/2/2 | 2 |  | Kinetis E | KE15Z | Execution | FRDM(Pilot) - 3/1 | Q4'15 | Board - FAT Coding & test |  | 1.Finished TSI mutual-cap demo porting to SDK2.0 ER, which will be released on 2/29 for alpha program. 2. Got the first 5pcs prototype FRDM-TOUCH boards, tested the board by TSI use case and the result showed the FRDM-TOUCH work well with the 1mm thick overlay. Sent the board to marketing for review, and got the positive feedbacks. The next 30pcs FRDM-TOUCH boards will be ready on 2/29/2016 without any schematic modification. 3. Finished discussion with Roznov team about the TSI FT schedule, Roznov team Petr will provide demo FT demo code based on SDK2.0 to support FRDM-TOUCH by the end of March. Sent FRDM-TOUCh and FRDM-KE15Z to Petr for software development.
WW08 | Eric | Chen Yonggang | 2016/2/3 | 2016/2/5 | 2 |  | Kinetis E | KE18F512VLL15 | Execution | Alpha customer support - 2/30 | Q2'15 | System Cases |  | 1. Samsung is evaluating MA512 to replace Toshiba for inverter project, will finish schematic in March, then start software development. Supported Samsung evaluation by providing the demo code. Per customer request, will provide the KEIL version demo project by porting the hello world use case this week. 2. Answered Jap FAE questions about IAR tools and FTM demo code to support Mitsubishi evaluation
WW08 | Eric | FANG YIZHOU | 2016/2/17 | 2016/2/19 | 2 | 2 | Kinetis E | KE15Z | Execution | FRDM(Pilot) - 3/1 | Q4'15 | Board - FAT Coding & test |  | 1. Develop FRDM KE15Z factory acceptance test demo. 2. Write FRDM KE15Z FSW doc.
WW09 | william | Guo Jia | 2015/11/10 |  | 1 |  | Kinetis L | KL28 | Execution |  |  | Board |  | 1. Renamed KL28T to KL28ZEM in the schematic. 2. As we need to follow the AGILE flow, we must use lib in AGILE system. So need to request the new part lib and apply them in the schematic. This would introduce delay about 1 week.
WW09 | Eric | Wang Ben | 2015/11/23 |  | 1 |  | Kinetis E | MT512P | Execution | 3in1-DC-KE18F schematic 3/4 | Q1'16 | Board - Design |  | 1.HVP-KE18F layout is finalized after team review.Will release to fabrication. 2.3in1 reference design board will do minor schematic and layout change. There are no other HW issue found during MA512 except the pin assignment for the interleaved PFC PWM.
WW09 | Eric | Wang Ben | 2016/2/16 |  | 3 |  | Kinetis E | KE15Z | Execution |  | Q4'15 | System EMC |  | Debug and found the root cause of the comm issue of KE15Z IHStove. The first is incorrect TSI key value during POR calibration, we need to calibrate twice to get the baseline value.The second is the cap in RESET circuit could NOT DNP,otherwise it will genereate PIN reset randomly when touch the power key. Now the system could run correctly. EMC can be tested next week.
WW09 | Eric | Wang Ben | 2016/2/1 |  | 1 |  | S08 | MC9S08SU16 | Execution | Execution: ES1.0 – 4/11 | Q1'16 | Documentation - RM |  | 1. Checking with Ruth on CW SP deliverable schedule.Marketing hope it to be private until end of 2016 and make it public on 2017. 2. Reviewed the RM and RDP file which will deliver to enablement team for CW SP. Found one doc issue in SIM, it will impact the headfile.Feedback to design/doc team.
WW09 | Eric | Chen Xinyu | 2016/2/15 |  | 0.5 |  | Kinetis K | KS22_256R | Launching |  | Q3'15 | Documentation - RM |  | 1. All the KS22 CHN RM version review have been done, summarized the general issues and comments to Doc Team. 2. KS22/20 RM/DS has been combined together, and passed review. 3. The USB use case block guide of KS22/20 RM has been updated by IP owner for non-regulator USB SoC.
WW09 | Eric | Chen Xinyu | 2016/2/15 |  | 1.5 |  | Kinetis K | KS22_256R | Launching |  | Q3'15 | Certification - USB |  | 1. Updating the USB certification test code, due to the requirement is not very clear from YeXian at the beginning. Added USB host test code, updated the HID code to control moving mouse by pressing key for interaction, updated the HID code to detect VBUS. 2. Will write a tiny USB certification SW requirement for future who will provide the test code.
WW09 | Eric | Chen Yonggang | 2016/2/24 | 2016/2/26 | 2 |  | Kinetis E | KE15Z | Plan | Alpha program support - 3/31 | Q4'15 | Board |  | 1. MT256 1.0 production launch was cancelled due to the unclear PESD issue rootcause. Planned the 1.1 Engineer sample available on 6/29 if the PESD is ok on MT512 sample. Rescheduled the board plan according to the changed sample plan: (1) Cancelled the 1Kpcs FRDM-KE15Z production boards, hold for 1.1 samples. (2). reschedule the TSI EVB board plan, postponed the board ready to June/2016. 2.Drafted the specs of RD-KE15Z-TSI. According to Greg's comments, the TSI-EVB is renamed as RD-KE15Z-TSI to be aligned with other NPI boards. 3. Customer Whirlpool asked for a live meeting on March 3 to introduce their touch project status and learn more about our TSI features. Preparing the training slides together with TSI Design and Marketing.
WW09 | Eric | Chen Yonggang | 2016/2/22 | 2016/2/23 | 2 |  | Kinetis E | KE18F512VLL15 | Execution | Alpha customer support - 3/31 | Q2'15 | System Cases |  | 1. Finished KEIL version template project and released to Korea FAE to support Sumsang eveluating on KE1xF. 2. Answered Jap FAE questions about FTM reload timing to support Mitsubishi evaluation
WW09 | Richy | Howard Liu | 2015/7/16 |  | 4 | 61.5 | Kinetis E | KE18F512VLL15 | Execution |  | Q1'16 | System Cases |  | 3in1 system timing evaluation: 1) Went through the low level code carefully again to avoid the potential issue caused by the running real 3in1 state machine on the h/w. Updated the interrupt handlers for the fan, compressor and FPC state machine respectively ot get a workaround for PDB/ADC sequence error issue. Alpha customer support: 1) Reviewed the performance data run by the Japan team and had meeting with system architecture to align the performance result from Japan team and that done by China team. KE1xF performance will have gap compared with competitor in the case of low cache hit.
WW10 | William | Jia Ding | 2016/3/2 | 2016/3/3 | 1 | 1 | Kinetis L | L5K | Execution |  |  |  |  | Ran CoreMark code on the single core devices of 1.1 silicon under various conditions, and measured the current consumption. Summarized the results and compared with 1.0 silicon. Found that the low power performance of 1.1 silicon is much better than 1.0.
WW10 | William | Guo Jia | 2015/11/10 |  | 0 |  | Kinetis L | KL28 | Execution |  |  | Board |  | As we need to follow the AGILE flow, we must use lib in AGILE system. So I have requested lib for up to 10 new parts. But after 1 week, only 1 of them is finished so far.
WW10 | Eric | Wang Ben | 2015/11/23 |  | 1.5 |  | Kinetis E | MT512P | Execution | 3in1-DC-KE18F schematic 3/25 | Q1'16 | Board - Design |  | 1. Revised 3in1 reference design board schematic, provided the change list. Original ADC input passive filters are not close to MCU pins, relocated them will bring big changes during layout. So the schedule will extend to three weeks(2 week revise+1 week review). 2. Applied new part of KE18F silicon and socket lib in FCL library. Will update board schematic with correct Agile P/N in next release.
WW10 | Eric | Wang Ben | 2016/2/1 |  | 0.5 |  | S08 | MC9S08SU16 | Execution | Execution: ES1.0 – 4/11 | Q1'16 | Documentation - RM |  | 1. Attended the core meeting, SoC design team and TE/PE discussed 40MHz max freq case. Datasheet specs will update IDD test parameters only, the other data will reuse SD8. 2. Reviewed the validation plan of SU16. It will only test the VREFH issue, 40Mhz max freq and memory size increase.
WW10 | Eric | Chen Yonggang | 2016/2/29 | 2016/3/3 | 4 |  | Kinetis E | KE15Z | Plan | Alpha program support - 3/31 | Q4'15 | Board |  | 1. Joined the Marketing/FAE meeting with customer Whirlpool to promote KE15Z, conducted TSI presentation to introduce TSI technical details and impressed customer with high noise immunity of the new TSI. Answered customer questions about TSI measurement, hardware and software support, touch tuning tools. and EMC test report. Whirlpool also introduced currently they're using Renesas RX130 and evaluating KE15Z for dish washer. 2. IH cooker works well now and can display reset information during the EMC test. Performed the preliminary ESD test, and test result shows the MT256 based touch board can pass 8KV-15KV, but failed to 20KV ESD test. The MT256 ESD test steps are recorded as Video and will be sent to TC for further check whether the test steps are correct. 3. Finished writing quick start guide of FRDM-TOUCH, and sent to creative service team for document editing. 4. Communicated with Roznov team and tracked the Freescale Touch software development for the new TSI. Petr is developing FT software based on FRDM-TOUCH board, and FT general code is ready to work with the new TSI and the specific driver code for the new TSI is under development. The first alpha version will be ready by the end of March.
WW10 | Eric | Chen Yonggang | 2016/3/4 | 2016/3/4 | 1 |  | Kinetis E | KE18F512VLL15 | Execution | Alpha customer support - 3/31 | Q2'15 | System Cases |  | Daikin support: Jap FAE is planning an onsite support on 3/15 to test Daikin's code with different Cache/Linker configurations to summarize the factors that affects KE1xF performance. Reviewed the test plan together with NPI team, and feedback FAE the suggestions including don't test the cache disabled cases, send NPI team the customer's map files and linker files for further check.
WW10 | William | wang peng | 2016/2/28 |  | 1 |  | Kinetis E | Industry | Microwave | Design - PCBA | 2015/3/10 | Receive the PCB boards, cooperate with vendor to align the components, expect to finish PCBA in the early of next week.
WW10 | William | wang peng | 2016/3/3 |  | 1 |  | Kinetis E | Industry | MA256 EMC test | Design - PCBA | 2015/3/11 | Prepare the EMC test code with MA256, but it has the different clock module, discuss with T.C. on how to prepare test code for comparison of MA256 and MT512
WW10 | Eric | Chen Xinyu | 2016/2/15 |  | 2.5 |  | Kinetis K | KS22_256R | Launching |  | Q3'15 | Certification - USB |  | 1. KS22 USB certification pre-test passed. But several issues found, e.g: 1) PET test - error message mismatch, HOST compliance test function not fully supported. 2) USBCV test - No HID Get description function implemented in demo. 3) USBDP/DM pin does not pulldown when no VBUS. Co-work with SW team's USB owner to fix them. The SDK2.0 REL1 USB demo/stack has not been passed any USB certification tests, that's big gap. Raised JIRA ticket KPSDK-9622 for this to SW team. 2. Written a draft USB certification Tips for SE team.
WW10 | Eric | Chen Xinyu | 2016/1/29 |  | 1 |  | Kinetis E | MT512P | Execution |  | Q1'16 | Documentation - Data Sheet |  | Meeting with PM/BACES/SYSTEM/MARKETING on the importance of making sure all the data on DS is correct, especically for Japanese customers, and we all agree on this point. Then discussed on how to verify the data SE team filtered out on MT512P DS. SE would delivery a spreadsheet with all the items collected from DS for BACES/PE/TE to fill in the ownership, data source, test method and etc information.
WW10 | Richy | Howard Liu | 2015/7/16 |  | 4 | 61.5 | Kinetis E | KE18F512VLL15 | Execution |  | Q1'16 | System Cases |  | MT512P NPI: 1) Reviewed the FTM document for the RM doc improvement. Clarified some content with IP owner that are easy cause to misunderstanding. The sub-section "Application info" will be added into the document as supplementary for easy understanding. 2) The DC source wasn't available last week. Checked the 3in1 low level initialization for fault protection code according to the schematic statically. 3) Checked the PCB layout of MA512P 3in1 daughter card that'll be reused by MT512P. Suggested to put the resistors and capacitors of the passive filters of analog input as around and close to MCU as possible and route the wire from capacitor end to MCU. Alpha customer support: 1) Continued to work with team to collect and review the performance data in different conditions.
WW10 | Richy | Richy Ye, Zhou Xuwei | 2016/1/25 |  | 0.5 | 4.5 | UHV | MU64 | Concept | Feasibility | Q3'16 | Features definition |  | MU64 entered into concept phase. Had conf. call with NPI market, system & architecture to discuss some key technical concerns for feasibility. GDU and on-chip power regulator are the key challenges in current IP library. Provided high side N-MOSFET pre-drive design with bootstrap for next discussion.
WW11 | William | Jia Ding | 2015/3/9 | 2015/3/10 | 1.5 |  | Kinetis L | KL28 | Execution |  |  | System Cases |  | Ported the FlexIO-8080-LCD demo to FRDM-KL28Z and TWR-KL28Z for customer Motorola and the use case pool development.
WW11 | William | Guo Jia | 2015/3/7 | 2015/3/8 | 1 |  | Kinetis L | KL28 | Execution |  |  | Board |  | 1.The agile lib is ready, and schematic has been updated. Layout is going on, and expect to finish this week. 2.Update QSG according to new template.
WW11 | william | YangXi | 2016/3/11 |  | 1 |  | Kinetis L | KL28 | Execution |  |  | Documentation - Others | Quick Start Guide | Marketing use new NXP QSG template, change the old QSG to new template and release to marketing. Issues: OOBE demo need to be finish and aligned with other boards.
WW11 | Eric | Wang Ben | 2015/11/23 |  | 0.5 |  | Kinetis E | MT512P | Execution | 3in1-DC-KE18F layout 3/25 | Q1'16 | Board - Design |  | 1.The vendor cannot arrange board building during May.1~May.7 since they need to move product line to extend the product capability. This will delay HVP-KE18F and 3in1-DC-KE18F for one week. 2.3in1-DC-KE18F layout is on-going.
WW11 | Richy | Howard Liu | 2015/7/16 |  | 3 | 64.5 | Kinetis E | KE18F512VLL15 | Execution |  | Q1'16 | System Cases |  | MT512P NPI: 1) FreeMASTER based on the Packed-Driven BDM communication Plug-in works for recorder support. 2) The PDB/ADC sequence error still has big impact on the system timing. Minor code modification may cause control timing not working correctly that I had spent much time to investigate. The reason is the happen of PDB/ADC sequence error and no ADC interrupts for PFC calculations. The P&E multilink used for FreeMASTER also cause the same PDB/ADC sequence error. For this issue, I still didn't find the good solution to the issue in all cases. 3) Called with team for RM improvement. I'll add the "application info" subsection for FTM based on the information exchanged with IP owner and the experience on 3in1 system timing design. Alpha customer support: 1) Japan FAE team will visit Daikin to test the KE1xF performances on different conditions again. Helped Japan FAE team review the code of 150MHz/160MHz system clock setting and cache enable configuration, the link configuration files for different test cases. Told them how to put the read-only data from Flash to RAM by modifying the link files.
WW11 | Richy | Richy Ye | 2016/1/25 |  | 0.5 | 5 | UHV | MU64 | Concept | Feasibility | Q3'16 | Features definition |  | MU64 entered into concept phase. Had conf. call with NPI market, system & architecture and Analog designer to discuss the feasibility about high side N-MOSFET pre-drive design. Then will plan power tool customer visit to get more requirements from end customer for MU64 definition.
WW12 | William | Jia Ding | 2015/3/14 | 2015/3/15 | 1 |  | Kinetis L | KL28 | Execution |  |  | System Engineering |  | 1. Measured the assigned peripheral adders of 1.1 silicon. Provide the source code and results to BACES team for their reference. 2. Measured the SOC current consumption of 1.1 silicon under those stop modes in which BACES team got larger current value than 1.0 silicon. Found the results in the modes are similar to the BACES team's results.
WW12 | William | Guo jia | 2015/3/14 | 2015/3/15 | 1 |  | Kinetis L | KL28 | Execution |  |  | System Engineering |  | 1. The KL28Z-FRDM based on TO1.1 is ready. Factory report the new board is not working. After APP is downloaded, they cannot see any response from the APP. After the investigation, the root cause is: the PFSIZE in TO1.0 is 0xf, and in TO1.1 is 0xb. And this affect the CMSIS-DAP FW. When PFSIZE is 0xb, the FW would not program the chip and report an error. This issue is finally solved by using a new version CMSIS DAP. Now up to 20 new KL28Z-FRDM boards have passed the test and have been shipped to Shanghai office. 2. The KL28ZEM layout draft finished. After review, found some issues like silk screen text not correct, GND type not right, USB signals are not route as differential pair. Edadoc is improving the layout now.
WW12 | william | YangXi | 2016/3/14 | 2016/3/16 | 1.5 |  | Kinetis L | KL28 | Execution |  |  | Board - FAT Coding & test |  | 1. Change new QSD document according to marketing request. Add Jumpers setting section and features section. 2. OOBE demo: aligned with FRDM board, use SDK bubble demo as OOBE demo, but SDK does not have TWR-KL28Z bubble demo, porting FRDM-board’s demo to TWR’s and push sources back into SDK2.0(Jira ticket: KPSDK-9848).
WW12 | Eric | Wang Ben | 2015/11/23 |  | 0.5 |  | Kinetis E | MT512P | Execution | 3in1-DC-KE18F layout 3/25 | Q1'16 | Board - Design |  | 1. 3in1-KE18F layout is released for team review. 2. Rasied CCB for 1.0 schedule re-baseline.Marketing launch date push out to 9/3 (China FTF). 3. Updated sample plan,remove sample for Daikin in June. 4. Update the IDD table format in DS.
WW12 | Eric | Chen Xinyu | 2016/3/18 |  | 0.5 |  | Kinetis E | KE06Z | Launching |  |  | System Engineering |  | Verified the latest FRDM-KE06Z OpenSDA firmware on Win8. No problem found.
WW12 | Eric | Chen Xinyu | 2016/2/15 | 2016/3/18 |  |  | Kinetis K | KS22_256R | Launching |  | Q3'15 | Certification - USB | KS22 passed the USB certification for both HOST and DEVICE. | KS22 passed the USB certification for both HOST and DEVICE.
WW12 | Eric | Chen Yonggang | 2016/3/14 | 2016/3/18 | 5 |  | Kinetis E | KE15Z | Plan | Alpha program support - 3/31 | Q4'15 | Board |  | 1. Supported KE15Z alpha program, finished documents writing including QSG and User Manual of FRDM-KE15Z. 2. Finished TSI golden chapter writing, added application informations into MT256 reference manual. 3. Finished TSI introduction slides for Kinetis E training, and uploaded to compass for review. 4. Supported FRDM-KE15Z board building, double-checked the BOM for the production board. 5. Communicated with Rozrov team to track the FT software development, Petr has finished the first function alpha version of FT to KE15Z, and will provide some demo code soon. 6. Supported Whirlpool KE15Z evaluation, answered Sale's questions on IEC61000-4-6 certification and TSI EVB boards. Checked with Design about the part-to-part variation under different temperature, as Whirlpool's interested in the variation questions, the test result shows the new TSI has good variations.
WW12 | Richy | Howard Liu | 2015/7/16 |  | 3 | 64.5 | Kinetis E | KE18F512VLL15 | Execution |  | Q1'16 | System Cases |  | MT512P NPI: 1) Discussed with the SoC team about the PDB/ADC sequence error implementation and its influence on the 3in1 time design. Recalculated the ADC conversion time based on the configured ADC clock and applied the calculated time into the PDB delays to schedule interrupts for motor 1 and motor 2 PI calculations. The issue that the unstable system control timing caused by the PDB/ADC sequence error was fixed after considering the SoC implementation. Now the system control timing works without influence from minor code change any more. 2) JLink-lite replacing P&E multilink for FreeMASTER connection is stable. 3) Verified the two motor current offset measurement and DC bus voltage. The rectified input voltage measurement is right also. Alpha customer support: 1) Had call meeting with Japan FAE to review the configuration code and link configuration files for all suggested test cases. Given a comment on the potential case that the customer's data table is too big to be saved in the upper SRAM, suggest them to use all SRAM to test for this case.
WW12 | Richy | Richy Ye | 2016/1/25 |  | 0.5 | 5.5 | UHV | MU64 | Concept | Feasibility | Q3'16 | Features definition |  | MU64 entered into concept phase. Had conf. call with NPI market, system & architecture and Analog designer to review the high side N-MOSFET pre-drive design. Then will plan customer visit to get technical requirements details for GDU feasibility analysis.
WW13 | William | Wang Hao | 2016/3/21 |  | 1 |  | Kinetis K | K4 TV | Concept | Feasibility | July 21st |  |  | Reviewed K4 TV ADD, this part is based on M4F core, including CAUv3 and totally 384KB SRAM. Initial chip selection includes three options for running core frequency, 120MHz, 180MHz and 300MHz. The TV chip will boot from SRAM with no internal flash. Main purpose of the TV is for checking low power implementation, performance analysis and C40 technology flow. Added 20 comments in ADD and will review with core team on hardware and use case requirement.
WW13 | william | Guo Jia | 2016/3/21 |  | 4 |  | Kinetis L | KL28 | Execution |  |  | Documentation - Errata |  | 1.Reproduced ERR009364 and ERR009365 on KL28TWR, both TO1.1 and TO 1.0. For ERR009365 , the fix seems to force a STOP after the first NACK in address stage. If this is true, it would bring a limitation to application. I am double confirming this with design. For ERR009364, the description did not tell how to reproduce this issue clearly, updated it. 2. Got up to 20 new KL28Z-FRDM boards, and distributed to each owner. 3. Updated the schematic lib to following agile flow. 4. Review the layout from Edadoc, and found some silkscreen layer content is not correct.
WW13 | william | YangXi | 2016/3/23 |  | 2 |  | Kinetis L | KL28 | Execution |  |  | Certification - USB |  | Prepare for KL28 USB certification: 1. Rework 3 FRDM-KL28 board, replace MCU to 1.1 silicon. 2. Prepare USB Host and USB device certification firmware base on KSDK2.0 USB Stack. 3. Install certification software(CV3.0) and make a local test before shipment, for device, do a CV chapter9 test and HID test, passed. And host, do a MSD and hub test, passed.
WW13 | william | YangXi | 2016/3/24 |  | 1 |  | Kinetis L | KL28 | Execution |  |  | Documentation - Errata |  | Errata review/update: TKT269512, Cannot access VREF2V1 Enable Bit in user mode: fixed in 1.1 silicon, but the RM description of enable bit is just the opposite. Need update doc. TKT251570, Reading FlexIO register when FlexIO functional clock is disabled results in a bus hang. Not fixed.
WW13 | Eric | Wang Ben | 2015/11/23 |  | 3 |  | Kinetis E | MT512P | Execution | Eng sample available 4/1 | Q1'16 | Board - Design |  | 1. Reviewd 3in1-KE18F layout. Uploaded final schematic and layout to Agile by JOB A085. 2. Basic trimmed engineering samples will be ready on 4/1.Full trimmed part delivery will rely on the debug progress, current target is to have them available by 4/15. 3. Prototype TWR-KE18F w/ socket will be ready on 3/29. 4. Had meeting with marketing to sync the board and software schedule.Also did the KE FTF lecture slides review. 5. Had meeting with PE/TE/BACES to check the items in DS.
WW13 | Eric | Chen Xinyu | 2016/3/25 |  | 0.5 |  | Kinetis E | KE15Z | Execution |  | Q4'15 | System Engineering |  | Checking the KPET related IDD and Adder test code, see how we can support the data in KPET, and how to work with BACES for data in DS.
WW13 | Eric | Chen Xinyu | 2016/3/25 |  | 0.5 |  | Kinetis E | MT512P | Execution |  | Q1'16 | Documentation - Data Sheet |  | Hold a meeting to discuss each data's source in the data sheet with TE/PE/BACES/S&A. After all the ownerships and what data need to be test are clarified, will send to PM for next efforts estimation and schedule.
WW13 | Eric | Chen Yonggang | 2016/3/21 | 2016/3/25 | 4.5 |  | Kinetis E | KE15Z | Plan | Alpha program support - 3/31 | Q4'15 |  |  | 1. Supported Samsung KE1xF evaluation, helped FAE solve LPTMR configurations problem. 2. Supported Mitsubishi servo amp project, helped FAE set up Keil template project for KE1xF. 3. Joined Whirlpool commnication meeting, and got the detailed customer project schedule. Whirlpool's project is named as "Touch Buttons Technology Refresh", which plans to change touch platform from Atmel to new one vendor from NXP, Cpress, or Renesas, in order to solve system and performance level issue they meet now. 4. Passed KE15Z IH Stove 15KV ESD test by changing power cable placement and improved touch sensitivity. 5. Reviewed the FTF KE+ training slides.
WW13 | Richy | Liu Zhen | 2016/3/21 |  | 0.5 |  | Kinetis E | MT512P | Execution |  | Q1'16 | Tools Support |  | Ten motors have been received.
WW13 | Richy | Howard Liu | 2015/7/16 |  | 2 | 66.5 | Kinetis E | KE18F512VLL15 | Execution |  | Q1'16 | System Cases |  | MT512P NPI: 1) System state machine always entered the fault state and failed to return back normal state. The root cause was that there was the bug in the GDFLIB_FilterMAInit_F16 function for ARM CM4. Reported the issue to Roznov team. 2) Reviewed the PCB layout of MT512P 3in1 daughter card. Alpha customer support: 1) Had call meeting with Japan FAE to review the performance test report done in Daikin's on-site test. The conclusion from all the tests is that the flash access speed causes the performance gap between KE1xF and Renesas X62T. 2) Supported Japan FAE team on FTM initialization sequence and FTM PWM generation configuration.
WW14 | William | YangXi | 31/3/2016 |  | 3.5 | 3.5 | Kinetis L | KL28 | Execution |  |  | Documentation - Others | Review new QSD contents | 1. Review new KL28 QSD from Austin marketing, many of board pin description are wrong. give 7 comments and one comments feedback. 2. CES demo: FRDM-KL28Z QR decode: finish porting decode library to CM0+ platform. Update code to use 96M SystemClock in HSRUN mode. The SPI clock frequency can reach max to ~25M.(>25M cause signal distortion) the refresh rate can reach to ~10 f/s.
WW14 | william | Guo Jia | 2016/3/21 |  | 4 |  | Kinetis L | KL28 | Execution |  |  | Board - Design |  | 1. PM is reporting two resistor with special value is not available on market. Sync with Alistair to update the resistor value to be standard. 2. Pushed KL28Z-FRDM and KL28ZEM-FRDM schematic to. Figure 4-7 in JOB-A085 is wrong, we need to pay attention to it when upload schematic to agile. Back annotation failed after replace 74LVC125. 3. KL28ZEM-FRDM layout finished, Alistair will help have a check on it.
WW14 | william | Wang Hao | 2016/3/21 |  | 1 |  | Kinetis K | K4 TV | Concept | Feasibility | July 21st |  |  | Review 28nm TV BACES board schematic, K4 TV most likely will reuse this board for validation purpose.
WW14 | Eric | Wang Ben | 2015/11/23 |  | 2 |  | Kinetis E | MT512P | Execution | Use case development 4/30 | Q1'16 | System Engineering | 3. The negative PESD damage level has generally improved from ~-2kV/-3kV to ~-6kV on IO pads, due to our BEOL experiment. Although this is a significant improvement it is still shy of our general “high immunity” target of passing -8kV. 4.On one IO pad type (p_io_20ma), which is used only eight times on the entire chip, the negative PESD damage happened again at -2kV. The damage mode is likely due to transient LU and consecutive burn-out of the part, not a direct damage from the PESD pulse. Investigation in progress. | 1. Got 50pcs prototype TWR-KE18F w/ socket and 5pcs MT512P silicons. Debug and set up the HW&SW environment for use case development. "Hello_world" project has passed test on TWR based on SDK2.0. 2. Found two issues:1) Current samples do not enable FPU by PE/TE,so we should mask the FPU setting in IAR configuration,otherwise hardfault will occur after programming.2) OpenSDA circuit on TWR-KE18F has RESET pin issue when Jlink firmware is downloaded. When user touch the reset pin and release it, MCU will continually stay in RESET status until POR. Such issue does not happen on P&E mirco OpenSDA firmware.It should related to the reset timing check mechanism inside the firmware. The workaround is to change the decoupling capacitor C12 beside reset pin from 0.1uF to 1000pF, or just remove it. 3. The negative PESD damage level has generally improved from ~-2kV/-3kV to ~-6kV on IO pads, due to our BEOL experiment. Although this is a significant improvement it is still shy of our general “high immunity” target of passing -8kV. 4.On one IO pad type (p_io_20ma), which is used only eight times on the entire chip, the negative PESD damage happened again at -2kV. The damage mode is likely due to transient LU and consecutive burn-out of the part, not a direct damage from the PESD pulse. Investigation in progress.
WW14 | Eric | Chen Xinyu | 2016/3/25 |  | 1 |  | Kinetis E | MT512P | Execution |  | Q1'16 | Documentation - Data Sheet |  | 1. Finialize the MT512P DS items check list, and sent to Karen for making schedule to test those data. And most of the data testing ownership is BACES. 2. Asking design for the power mode transition timing simulation for the non-stop cases. The tPOR and STOP related cases need BACES help. 3. Confirmed with validation team, the max SPI speed is varient from single board to two boards. Decide not put max SPI speed on DS, which high depends on the hardware.
WW14 | Eric | Chen Xinyu | 2016/3/25 |  | 1.5 |  | Kinetis E | KE15Z | Execution |  | Q4'15 | System Engineering |  | 1. Reading the ATE and Bench code for IDD and Adder test. Defining the cases on MT512P. 2. Plan to discuss with S&A team for the case.
WW14 | Eric | Chen Yonggang | 2016/3/28 | 2016/4/1 | 5 |  | Kinetis E | KE15Z | Plan | Alpha program support - 4/31 | Q4'15 |  |  | 1. Communicated with Whirlpool Sales and got the part number of the primary competitors: Atmel SAMD21, Renesas RX130 and Renesas Synergy S1/S3. The next step is to compare the TSI features and summary a table to list out the advantage and disvantage. 2. Supported Mitsubishi servo amp project, helped FAE answer questions on WDOG, the major question about WDOG that FAE met is that MCU reset after 16bit refresh, checking with Design with this issue. 3. Started RD-KE15Z-TSI Specs design, held the first review meeting and collected comments from Design/Marketing. 4. Collected and discussed board change requirements for the production version FRDM-KE15Z, no board change is needed as confirmed by SDK team. Developed FCC test code, and sent the board to Shanghai Audix Lab for FCC test. 5. For FRDM-TOUCH, got the draft FT Library and Demo from Rozrov team on time. 6. Finished the KE clocking training slides for Kinetis E web training.
WW14 | Richy | Howard Liu | 2015/7/16 |  | 3 | 69.5 | Kinetis E | KE18F512VLL15 | Execution |  | Q1'16 | System Cases |  | MT512P NPI: 1) Rotated the fan and compressor at the same time successfully. 2) The zero detection algorithm failed quickly after PFC enabled. After long time debugging, found the root cause. It's caused by the overflow of signed short type that's ok on 16bit DSC but failed on 32bit ARM core. The length of int type on DSC is 16bit, however, it's 32bit on ARM core. 3) One 3in1 power stage board was damaged while testing PFC. now only 2 boards are available for 3in1 demo and evaluation. Sent MT512 PM for manufacturing more 3in1 power stage board. Alpha customer support: 1) Helped Japan FAE/customer with the FTM initialization procedure and answer their questions about initialization. 2) Answered Japan FAE's question about FTM channel output value in forced initialization and FTM counter stops. Discussed the FTM pin output in PWM disabled, PWM counter stops, PWM clock disabled and PWM fault.
WW14 | Richy | Richy Ye | 2016/1/25 |  | 0.5 | 6 | UHV | MU64 | Concept | Feasibility | Q3'16 | Features definition |  | MU64 entered into concept phase. Had conf. call with NPI market to discuss the customer technical requirement information gotten during key customers visit. Now NPI market is clear about different high voltage requirement betweewn chip power and pin operating voltage.
WW15 | william | Guo Jia | 2016/4/4 |  | 4 |  | Kinetis L | KL28 | Execution |  |  | Board - Design |  | 1. Updated the schematic according to the feedback from Alistair. Some resistors are not standard ones, and are not available in market. 2. Uploaded FRDM-KL28Z & FRDM-KL28ZEM to agile system. 3. Found one footprint issue by Edadoc. This is fixed by Edadoc. And I have reported this issue to the team who make the library. FRDM-KL28ZEM layout finished and manufacture is going on. 4. Finished two use case for L5K. As another two SAI use cases are covered by SDK demo and validation code. There are 3 use cases left. 5. Finished validation on the ERR010220.
WW26 | william | YangXi | 2016/3/21 |  | 3 |  | Kinetis L | KL28 | Execution |  |  | System Cases | marketing support:CES demo | marketing support: CES demo 1. CES QR decoder demo: decoder library porting to KL28 complete, decoder function verified on FRDM-KL28. It works fine. Now, the main task is to improve decoder/display speed: a. Enhance SPI performance, Move SPI pinmux to fast pin, but performance cannot reach to >25MHz either. b. Change LCD display method from polling to DMA, display speed can reach to ~15 f/s. but that require OV7670 output format set to be RGB565(2 byte per pixel, same as LCD, so that we can use DMA to move data directly). But decoder library need a gray format data(1byte per pixel, indicate luminance). CPU is too slow to change every pixel from RGGB565 to gary format. Still working on that issue. 2. Solder one demo adapter board for CES demo.
WW15 | Eric | Wang Ben, Chen Xinyu | 2015/11/23 |  | 2 |  | Kinetis E | MT512P | Execution | Use case development 4/30 | Q1'16 | System Engineering |  | 1. PESD failure units arrived KLM on 4/4. Core team working with KLM FA lab to proceed as top priority. 2. Got another 30pcs samples from PE and delivered them with TWR boards to Validation/SW/ROM team. 3. Updated HVP-KE18F schematic with MCU formal Agile P/N and uploaded to Agile. 4. Aligend with motor control team on the HVP-KE18F and 3in1-KE18F board reference design schedule and FCC test requirement on HVP-KE18F. 5. PE will ship out 150pcs full trimmed samples with FPU enabled, we will use them to build all the boards(TWR,HVP,3in1) on 4/21. 6. Run the use case of ADC trigger by LPIT/TRGMUX, Bubble demo and FlexIO simulate PWM, also check the external ETXAL32 crystal. No problem found yet.
WW15 | Eric | Wang Ben | 2016/2/1 |  | 0.5 |  | S08 | MC9S08SU16 | Execution | Execution: ES1.0 – 4/30 | Q1'16 | Documentation - RM |  | 1.Eng samples push out to 4/30. 2.Requested 60pcs samples for Drone reference design and testing.
WW15 | Eric | Chen Yonggang | 2016/4/5 | 2016/4/8 | 4 |  | Kinetis E | KE15Z | Plan | Alpha program support - 4/31 | Q4'15 |  |  | 1. Conducted and passed FCC test for FRDM-KE15Z, got the formal test report from Audix test lab. 2. Conducted TSI IP behavior under very low power(1.7V) per TSI Design request, in order to evaluate the feasibililty that TSI IP integrated to 3V Kinetis silicon like KK series. The test configuration includes setting up tsi software on EVB board, configure silicon into test mode, then turn down the power supply. The test result showed that both self-cap and mutual-cap mode can work until 1.75V and detect finger touch well. The detailed waveforms were recorded by FreeMASTER(FreeMASTER itself can work until 1.95V). 3. Answered EMEA FAE questions on KE14Z128 FTM/ADC for Bosch-Rexroth project, who's evaluating KE14Z128 FTM quadrature decorder for the optical encoder and sync up with ADC for the sin/cos encoder at the same time. 4. Searched and compared the competitor's solution for TSI, summarizing the detailed differences.
WW15 | Richy | Howard Liu | 2015/7/16 |  | 1 | 70.5 | Kinetis E | KE18F512VLL15 | Execution |  | Q1'16 | System Cases |  | MT512P NPI: 1) Checked the damaged board and found it cannot be repaired because two IMPs and MOSFETs for PFC were burned . We have IPMs available to replace. Now only 3 boards are available for use. Suggested MT512P NPI to manufacture more power stage board for future use. 2) Wrote the slides to introduce the 3in1 A/C outdoor unit demo on KE1xF platform and sent to market team for Gree promotion.
WW16 | William | Jia Ding | 2015/4/13 | 2015/4/13 | 1 | 1 | Kinetis L | KL28 | Execution |  |  | System Engineering |  | 1. Validated latest Keil KL28 device package. No problem was found. 2. Measured various wake up time of 1.1 silicon on three chips.
WW16 | william | YangXi | 2016/4/10 | 2016/4/13 | 3 | 1 | Kinetis L | KL28 | Execution |  |  | System Engineering | CES demo: FRDM-KL28Z QR decoder Peripheral IDD adder test support | 1. Finish demo software, test performance, resolution: 320x240, decode rate can reach to: 8~10 f/s. prepared two sets of hardware. 2. need prepare a box for CES exhibition and also an introduction PPT due marketing request. 3. Got finial result of BACES IDD result, all match except CMP:, AE test result is about ~20uA while BACES got ~13uA, will aligned with BACES for software. And ask BACES to double check the hardware connection.
WW16 | Eric | Wang Ben | 2015/11/23 |  | 2 |  | Kinetis E | MT512P | Execution | Use case development 4/30 | Q1'16 | System Engineering |  | 1. PESD failure units arrived KLM on 4/4. FA test is on-going. 2. Verified and delivered 8 TWR boards and samples to third parties for tools development. 3. Delivered 130pcs full trimmed samples to HW vendor for boards building(TWR,HVP,3in1). 4. Summarized the corner cases raised by customer Mitsubishi on MT256P/MA512, will sync with validation team to push them add cases during MT512P validation. 5. Planned to start porting bldc demo from SDK1.3 to SDK2.0, but mistakenly broke down the TWR-MC-LV3PH board during inital testing.Will go on after get the new board.
WW16 | Eric | Chen Xinyu | 2016/3/25 |  | 3 |  | Kinetis E | KE15Z | Execution |  | Q4'15 | System Engineering |  | 1. Gone through the KPET Adder data of KL27 and K22, summarized each IP module's power consumption factors, like functional clock, power mode. 2. Created a git repo for KPET, with KE15Z SDK2.0 RC1 pushed. The project structure has been defined, ADC adder project template is also created.
WW16 | Eric | Chen Xinyu | 2016/4/14 | 2016/4/14 |  |  | Kinetis K | MKS22FN256VLL12 | Launching |  |  | Documentation - Data Sheet |  | IDD MAX data has been collected and reviewed. The update version of Datasheet is ready to publish.
WW16 | Eric | Chen Yonggang | 2016/4/11 | 2016/4/15 | 4.5 |  | Kinetis E | KE15Z | Plan | Alpha program support - 4/31 | Q4'15 |  |  | 1. MT256 IH Stove EMC update: Per our request, customer Fotile conduted EFT test in their test lab. The test result shows that the mass production main board can't pass EFT 4KV test. 2. Summarized KE+ corner cases derived from alpha customer and FAE questions. The corner cases are mainly about single IP usage which are not clearly described in Reference Manual. Checking with Validation team about whether the corner cases are covered by the validation test plan. 3. Updated the Specs of RD-KE15-TSI board and sent out for review. 4. Made FRDM board plan for 1.1 MT256 sample(engineer sample ready in July). The 1.1 FRDM-KE15Z board plan includes 2 type boards: the prototype version 50pcs, use the old 1.0 FRDM board by replacing 1.0 sample with 1.1 sample; the production version 1000pcs, build new boards. 5. Answered Jap FAE's questions on FTM LDFQ timing.
WW16 | Richy | Howard Liu | 2015/7/16 |  | 3 | 73.5 | Kinetis E | KE18F512VLL15 | Execution |  | Q1'16 | System Cases |  | MT512P NPI: 1) The PFC worked also. But PFC still could not work with fan and/or compressor at the same time. Another board was damaged during debugging the issue of PFC not working with fan and/or compressor. After deep debugging and found the PDB and ADC interrupts were "frozen", as a result, the PWM couldn't be updated any more that caused the very high voltage in a very short time and damaged the board. The auxiliary power circuit was damaged also due to sudden very high DCBus voltage, so the protection circuit failed to protect the board. I didn't find the root cause of interrupts "freeze". Just doubt that it's caused by the noise of PFC PWM switching.
WW17 | William | Wang Hao | 2016/3/21 |  | 1 | 5 | Kinetis K | K4TV | Feasibility | Plan | July 21st | Board - Document |  | Drafted HSD and collected BACES board requirement for each functional team, no plan to design new boards for K4TV based on ADD requirement. Reviewed K4TV pinout and BACES board schematic.
WW26 | william | Guo Jia | 2016/4/21 | 2016/4/22 | 1.5 | 1.5 | Kinetis L | KL28 | Launching |  |  | System Engineering |  | Prepare the use case code and AN for LPI2C on L5K.
WW17 | william | YangXi | 2016/4/21 | 2016/4/22 | 1.5 | 1.5 | Kinetis L | KL28 | Launching |  |  | System Engineering | CES QR decoder demo | 1. Marketing need two demo hardware, one for NTF and one for CES. Prepared another hardware for them. Including a PPT introduction for this demo. 2. Checked the new DAP-Link firmware behavior on TWR-KL28Z, it works OK for Keil and IAR(Debug and download). And create new FSW-28400(FAT package) and uploaded to Agile. 3. Due to marketing and feedback from team member, change behavior for exhibition) (on going, 50% done) 1. change result display font from 12x24 to 18x36. 2. When decode success and result in displayed on LCD screen, the real image display mode will stopped until current QR pattern is move out or a new QR pattern is captured. (old behavior is display decode result for 1 second and return to real time image display mode, it could to hard for customer to check whether the decode result is correct or not)
WW17 | Eric | Wang Ben | 2015/11/23 |  | 2.5 | 57 | Kinetis E | MT512P | Execution | Use case development 5/11 | Q1'16 | System Engineering | Marketing team confirm MT512P move as it is for 1.0 launch. | 1.PESD FA test is on-going.Discussion in progress with IO expert on the fix plan.Marketing team confirm MT512P move as it is for 1.0 launch. 2.The 2nd round prototype TWR-KE18F is in assembly, prepared the FSW document and example code/tool package for the vendor. 3. Sync with Greg and Ruth about the OpenSDA firmware release on TWR-KE18F, from now on DAP-link should be the default one on TWR/FRDM if no special request from marketing. 4.Aligned with validation team about the core cases requested from customer Mitsubishi on MT256P.They commit will add and finish the new cases during validation. 5.MT512P 1.0 wafer and MK sample plan updated to meet 1.0 launch needs. All launch boards will be ready in warehouse by 8/15. 6.Validation team reported two DAC corner issues.Helped them for the issues analysis. a) write_pointer does not reset automatically in FIFO mode: talked with IP owners and found the RTL code has the priority issue during 32-bit operation.Users can not automatically reset FIFO write pointer when write DAC0_STATCTRL register directly. They has to do with 8-bit operation for automatically reset or has to clear it manually. b) Hardware trigger pulse width could not more than 2 sysclk width, But in chip user can select any source from trigger mux. Some of them have much wider width which will results in multi triggers occurred. IP owner has confirmed this two issues and would add NOTE in RM.
WW17 | Eric | Wang Ben | 2016/4/19 |  | 1 | 1 | Kinetis E | MT512P | Execution |  | Q1'16 | System Cases-BLDC demo |  | 1.Tried to repair the TWR-MC-LV3PH board by replacing the pre-driver MC33937 and MOSFETs, but it is failed. There may be some other components damaged on the board.Will hold the HW issue tracking because of limited time. 2.Went through the SDK2.0 code repository, the effort of porting bldc demo from SDK1.3 to SDK2.0 is big since all the drivers API and software structure changed a lot. So the code has to re-write. Will start coding from this week.Aim to catch up with the alpha customer date in Mid May.
WW17 | Eric | Wang Ben | 2016/4/19 |  | 1 |  | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | 1.Drafted and updated the KPET test cases document for FTM,FlexIo for MT256P.
WW17 | Eric | Chen Xinyu | 2016/3/25 |  | 3 | 9 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | 1. Finished and reviewed KE15Z KPET Adder cases for each IP modules. 2. Written the typical clock configurations functions and it's related unit test code. Passed test. 3. Writing the LPUART Adder cases.
WW17 | Eric | Chen Xinyu | 2016/4/22 |  | 0.5 | 0.5 | i.MX | i.MX6RT | Concept |  |  | Documentation - Others |  | Join the i.MX6RT PRD review meeting, raised some questions on the requirement for Display, Filesystem and IP reuse source (Kinetis or i.MX).
WW17 | Eric | Chen Xinyu | 2016/3/25 |  | 0.5 | 6 | Kinetis E | MT512P | Execution |  | Q1'16 | Documentation - Data Sheet |  | Still need ADC IP owner to confirm we can reuse MT256P BACES data on MT512P. If we can reuse, BACES would only need to cover the un-test items on MT512P.
WW17 | Eric | Chen Yonggang |  |  | 1.5 | 30 | Kinetis E | KE15Z | Execution | Alpha program support - 4/31 | Q4'15 | Alpha Customer Support |  | 1. Supported US FAE answer customer Whirlpool's questions on how to use OpenSDA debug KE15Z. 2. Supported EMEA FAE answer customer Bosch's questions on MPU, ADC INL, ADC clock, LPUART baudrate. 3. Supported Jap FAE answer customer Mitsubishi's questions on FTM module, submitted comments in KE1xZ RM to fix some document issues on FTM reload point in up-down counting mode. 4. Discussed KE+ corner cases with Validation team, and validation team agree to add most cases into validation test plan 5. QMS 4.0 signoff for MT256 1.1 TO on May 6.
WW17 | Eric | Chen Yonggang |  |  | 1 | 10 | Kinetis E | KE15Z | Execution | Alpha program support - 4/31 | Q4'15 | Board - Design |  | Finalized the Specs of RD-KE15-TSI board and start schematic design.
WW17 | Eric | Chen Yonggang |  |  | 0.5 | 0.5 | Kinetis E | KE06 | Launching | Launching |  | Board - Design |  | FAE reported that the thermistor RT1 on production FRDM-KE06 didn't work, the root cause is the board soldered the wrong part, but the schematic and BOM is the right part number. Checking with the vendor Devtech whether factory soldered the wrong part and rework plan.
WW17 | Eric | Chen Yonggang |  |  | 0.5 | 0.5 | Kinetis E | KE15Z | Execution | Execution |  | System Cases-KPET |  | Finished MT256 KPET adder cases for LPIT, LPTMR and TSI module
WW17 | Eric | Chen Yonggang |  |  | 1 | 1 | Kinetis E | KE15Z | Execution | Execution |  | Training |  | Writing ACMP training slides for Kinetis web training, 80% done.
WW17 | Richy | Howard Liu | 2015/7/16 |  | 2 | 75.5 | Kinetis E | MT512P | Execution |  | Q1'16 | System Cases |  | MT512P NPI: 1) Updated the schematic for new 3in1 power stage board manufacturing to generate the new BOM with changed shunt resistance for fan and inductance for PFC. Alpha customer support: 1) Supported Japan FAE on the FTM reload timing with different reload frequency value set at different time. Current design is that the FTM LDFQ counter will keep counting to overflow and then set the RF bit at the next matching point while setting a smaller value than the current LDFQ counter value. This prolongs the controlling time suddenly if controller is updated in the RF ISR. Suggested Japan FAE to ask customer to update the LDFQ value in the RF ISR only to avoid the issue. 2) Japanese customer wants to use software trigger method to measure several different ADC channels. Suggested Japan FAE to use the DMA channel link method to implement customer's request.
WW17 | Richy | Richy Ye | 2016/1/25 |  | 2 | 8.5 | UHV | MU64 | Concept | Feasibility | Q3'16 | Features definition |  | MU64 entered into concept phase. Had meeting with NPI marketer, system/architecture and analog designer to align the chip power solution, GDU spec and device feature. Now these items are well aligned, helpful for next milestone of feasibility.
WW18 | William | Wang Hao | 2016/3/21 |  | 1 | 6 | Kinetis K | K4TV | Feasibility | Plan | July 21st | Documentation - Others |  | Finished review v0.7 ADD document, estimated validation task for K4TV include run mode max frequency K4TV can achieve, power consumption under run and low power modes, CAUv3 and performance monitor function check.
WW18 | Eric | Chen Xinyu | 2016/3/25 |  | 0.5 | 6.5 | Kinetis E | MT512P | Execution |  | Q1'16 | Documentation - Data Sheet |  | Made a final datasheet item check list for the data must be re-tested on MT512P. Other values not marked for re-test can be reused either from MA512 or MT256P.
WW18 | Eric | Wang Ben | 2015/11/23 |  | 3.5 | 60.5 | Kinetis E | MT512P | Execution | Alpha customer Support 5/11 | Q1'16 | System Engineering |  | 1.PESD FA test is on-going.PE submitted PATS request and shipped damaged samples to KLM FA lab, Sample num15 and num8 FA were finished and reports were sent to ATX team for further review. Meanwhile PE submitted PATS request for SN12 FA. 2.Got 30pcs 64LQFP samples from PE, reserve for future system level EMC test. 3.Enablement third party Segger reported one issue on TWR-KE18F. They found a very strange oscillating reset signal on board, and it does not work correctly. Support Segger engineer analyze and investigate the issue.We guess that the output drivers of the OpenSDA MCU are partially broken,because in software they experimentally changed the port configuration of the reset pin to "high drive strength". Sent a new board to them in order not to gate their enablement tools delivery. 4.Received 15pcs 3in1-KE18F boards, verifed they are ok to program flash and download code. 5.Received 30pcs HVP-KE18F boards, found soldering issue that OpenSDA K20 chip does not solder as its correct pin order. After vendor reworked them, they are ok to program firmware. Found another issue that HVP-KE18F could not be programmed standalone, but has to work with mother board. Because the VDDA voltage comes from mother board.The root cause is the PMC module is new design for Kinetis E+ ,which is different from former Kinetis E/L/V/K family. The VDDA not only used by Analog modules, but also the PMC module itself.So VDDA pin could not be floating.
WW18 | Eric | Wang Ben | 2016/4/19 |  | 1 | 2 | Kinetis E | MT512P | Execution |  | Q1'16 | System Cases-BLDC demo |  | 1.Revised the software directory and structure from SDK1.3 to SDK2.0. Coding started, 10% is done. The demo clock configuration and function is ok.
WW18 | Eric | Wang Ben | 2016/2/1 |  | 0.5 | 5 | S08 | MC9S08SU16 | Execution | Marketing launch 6/10 | Q1'16 | System Engineering |  | 1.Received 60pcs SU16 samples from PE. Did basic flash download test with SD8 CW service pack on SD8 EVB.It is ok. 2.Validation team verified the VREFH damage issue has been fixed on SU16.
WW18 | Eric | Chen Yonggang |  |  | 2 | 32 | Kinetis E | KE15Z | Execution | Alpha program support - 5/31 | Q4'15 | Alpha Customer Support |  | 1. Supported Jap FAE on KE15Z SDK test. Jap FAE started to test SDK ER(Early Release), and found some software issues for the bubble, ecompass demo. Helped FAE solve the issues. 2. Jap FAE visited Mitsubishi RAC(Room Air Conditioner) indoor unit team to promote KE15Z, and reported 2 customer requirements: (1) KE15Z STOP IDD is 20uA, while competitor Renesas is 4uA. (2) Mitsubishi needs 2KB EEPROM data with 1M of endurance, and they are using an external EEPROM device now. KE15Z supports 2K flexRAM for EEPROM emulation, so it's our advantage.
WW18 | Eric | Chen Yonggang |  |  | 2 | 12 | Kinetis E | KE15Z | Execution | Alpha program support - 5/31 | Q4'15 | Board - Design |  | Drafted the schematic of RD-KE15-TSI board and sent out for review.
WW18 | Eric | Chen Yonggang |  |  | 1 | 1 | Kinetis E | KE15Z | Execution | Alpha program support - 5/31 | Q4'15 | Documentation - Application Notes |  | Writing an AN for ADC calibration, 50% done.
WW18 | Richy | Howard Liu | 2015/7/16 |  | 2 | 77.5 | Kinetis E | MT512P | Execution |  | Q1'16 | System Cases |  | MT512P NPI: 1) Got the 5 daughter cards of MT012P used for 3in1 reference demo system. Run the smoking test for the board using the 3in1 code. 2) Continued to check the issue that PFC unworkable with motors simultaneously. But there's still no further progress for this issue. I cannot do more test since there's only one 3in1 power stage board available.
WW19 | William | GuoJia | 2015/5/3 | 2015/5/5 | 3 | 5 | Kinetis L | KL28 | Execution |  |  |  |  | 1. KL28ZEM-FRDM delayed due to two chips sent to factor is wrong. Need to re-order the two chips. 2. Make the use cases for LPI2C and LPSPI. Found the following issues: 1). When LPI2C working in push-pull mode, the fist and 9th rising edge is quite slow, behavior like in open drain mode. The 9th rising edge can be explained by I2C protocol, but the first cannot be. Similar result is seen on SDA line too. 2). With NACK expected, still cannot send data out next. 3). There is no flag indicating current transfer ended. So in application we cannot start sending data after we ensure we have got a ACK. For LPSPI, in continuous mode, found two issues: 1). The last edge in previous frame is delay to next frame. 2). The RX data is delayed to go into the RX FIFO. I am still discussing these issue with design.
WW19 | William | Wang Hao | 2016/3/21 |  | 1 | 7 | Kinetis K | K4TV | Feasibility | Plan | July 21st | Documentation - Others |  | Reviewed K4TV register definition file together with its ADD, as no RM is generated for K4TV, the register definition file will be used for generating header file for validation code. Reviewed CAUv3 block guide to know its main functionality. No performance monitor block guide yet as confirmed from design team.
WW19 | william | Jia Ding | 2016/5/3 |  | 2 | 2 | Kinetis L | KL28 | Execution |  |  | System Cases |  | Made a demo that use FlexIO to emulate Motorola 6800 parallel bus and to drive a LCD. The demo is under debugging stage now.
WW19 | Eric | Wang Ben | 2015/11/23 |  | 1.5 | 62 | Kinetis E | MT512P | Execution | Alpha customer Support 5/15 | Q1'16 | System Engineering |  | 1.PESD FA test is still on-going.MT256P 1.x TO plan is under discussion. 2.Got the TWR-KE18F DAPlink firmware from Chris, did some test and found two issues: a)When download code with IAR, the firmware seems not work very stably, sometimes it would pop up errors/warning window. b)When KE18F powered from 5V,the drag MSD function does not work.The RESET signal will always be pulled down, the bin file could not drag and update correctly. But If KE18F powered from 3.3V on TWR, the function is ok. Feedback to Chris and the issues are under invesitation. 3.Go on investigating the OpenSDA circuit damage issue on TWR with SEGGER engineer. He did not wish to share his source code for Jlink firmware. Just follow his suggestion to do some test, but did not reproduce the issue.
WW19 | Eric | Wang Ben | 2016/4/19 |  | 2 | 4 | Kinetis E | MT512P | Execution |  | Q1'16 | System Cases-BLDC demo |  | 1.Coding for BLDC demo is on-going.40% is done. FTM generating combined PWM signal, PDB synchronization with ADC sampling are done.But from the oscilloscope, the signal have spike pulse periodically,which is abnormal. Still debugging and finding out the root cause.
WW19 | Eric | Wang Ben | 2016/2/1 |  | 0.5 | 5.5 | S08 | MC9S08SU16 | Execution | Marketing launch 6/10 | Q1'16 | System Engineering |  | 1.Installed and tried the SU16 CW service pack from P&E,but it failed to download code to flash.From the output error info,think the programming algorithm file has some issue, which is similar as we met during first SD8 service pack release.Feedback to P&E.
WW19 | Eric | Chen Xinyu | 2016/3/25 |  | 0.5 | 7 | Kinetis E | MT512P | Execution |  | Q1'16 | Documentation - Data Sheet |  | 1. BACES plan to collect the data for MT512P in July after 6ULL tasks. 2. Checked the MT256P latest datasheet, the data source is almost reuse from MA512 and S32K datasheet. Get the MT256P BACES test results from BACES, request doc team to change the data source for all the data tested on MT256P, but not reuse. 3. After the MT256P datasheet get ready, we can go for MT512P datasheet by updating the data which should be reused from MT256P.
WW19 | Eric | Chen Yonggang |  |  | 4 | 16 | Kinetis E | KE15Z | Execution | TSI demo board design - PCB Layout - 5/27 | Q4'15 | Board - Design |  | Finished the schematic of RD-KE15-TSI board according to review comments, and discussed layout guidelines with layout engineer about the part placemnet, and TSI requirements including TSI trace width, shield electrode plane , proximity key pattern.
WW19 | Eric | Chen Yonggang |  |  | 0.5 | 1.5 | Kinetis E | KE15Z | Execution | TSI demo board design - PCB Layout - 5/27 | Q4'15 | Training |  | Prepared FRDM-TOUCH demo based on the preliminary Freescale Touch library, and delivered the demo, sent 3pcs FRDM-TOUCH boards, and uploaded board user guide, FreeMASTER tools to compass to support US FTF in May.
WW19 | Eric | Chen Yonggang |  |  | 0.5 | 1.5 | Kinetis E | KE06 | Execution |  |  |  |  | Sensor team is looking after a Kinetis MCU board 5V capable to bundle with their new MPX5004 Pressure sensor shield(FRDM-MPX5004). FRDM-KE16Z is perfect for this but KE15Z launch is far too late, so FRDM-KE06Z is selected as an interim solution. As FRDM-KE06Z boards is 3V powered by default, Sensor team decided to buy 150pcs FRDM-KE06Z boards and modify the boards to meet MPX5004 shield requirements. Meanwhile, Vendor PM Ethan Li confirmed that Embest will rework all the 3Kpcs FRDM-KE06Z in US inventory for free to fix the thermistor part issue.
WW19 | Eric | Chen Xinyu | 2016/3/25 |  | 3 | 12 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | Finished the LPUART Tx/Rx adder use case. Got the LPUART adder data on FRDM-KE15Z.
WW19 | Richy | Howard Liu | 2015/7/16 |  | 1 | 78.5 | Kinetis E | MT512P | Execution |  | Q3'16 | System Cases |  | MT512P NPI: Compared the difference between MA512PTV and MT512P features and extracted the contents that have impacts on the 3in1 peripheral use. Some low level initialization needs to be modified for MT512P Rev1.0 chip.
WW20 | William | GuoJia | 2015/5/3 | 2015/5/5 | 3 | 5 | Kinetis L | KL28 | Execution |  |  |  |  | 1. For KL28ZEM-FRDM, as factory engineer mixed up the single core and dual core chips and they cannot distinguish them, made to code to detect if one board is single core or dual core. But factory engineer cannot program the code to board. Gave a remote debugging, the issue still not resolved. After going on site, found the root cause is, the JLINK driver of version 5.12 is not working. After retrieve to version 5.00, everything is OK. 2. Finished the test on the peripherals, found the three-color LED is not working correctly. Only two colors can be lighted on each board. But this issue is not seen when testing the 70 boards in factory. 3. Found 1 board on which the VADJ is 4.11V, all other board did not show this issue. But when K26 is not powered on, the VADJ is 3.58V, instead of 3.30V expected. When K26 is powered on, VADJ is 3.30V as expected. 4. Finished testing the KL28/K26 SWD interface on the 70 boards, all passed. 5. Found one issue that the pull-down resistor make the K26 go to EZPORT mode, so the SWD interface cannot be connected. This issue is fixed by removing the pull down resistor, as the test shows this does not affect the KL28 SWD connection, this workaround is applied to all the 70 boards.
WW20 | Eric | Chen Xinyu | 2016/3/25 |  | 1.5 | 12 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | Complete the coding of ADC adder use case, debug and verification is on-going.
WW20 | william | Wang Hao | 2016/3/21 |  | 1 | 8 | Kinetis K | K4TV | Feasibility | Plan | July 21st |  |  | Continue ADD and system register file review and prepare for planning summit.
WW26 | william | YangXi | 20/5/2016 |  |  | 0.5 | Kinetis L | KL28 | Launching |  |  | Documentation - Others |  | 1. Prepared FRDM-KL28Z QR decoder demo’s PPT to marketing 2. Verify USB_SRAM feature and aligned with design: a. USB_SRAM can be accessible only when USB clock gate is opened. b. USB_SRAM cannot be used as code space. USB_SRAM does not connected to Instruction bus.
WW20 | Eric | Wang Ben | 2015/11/23 |  | 1.5 | 63.5 | Kinetis E | MT512P | Execution | Alpha customer Support 5/20 | Q1'16 | System Engineering | 1.PESD light emission FA result was done, aligns with IO expert’s failure theory.Further IO design optimization will be applied on MT512P IO structure. New IO library will be released with BE fix on 5/16, MT256P 1.1 TO on 5/20 based on that. | 1.PESD light emission FA result was done, aligns with IO expert’s failure theory.Further IO design optimization will be applied on MT512P IO structure. New IO library will be released with BE fix on 5/16, MT256P 1.1 TO on 5/20 based on that. 2.Continue test and debug the DAP-link issue, gave some clues and analysis results to SW team.Got one updated version with high drive strength enabled on all SWD pins, after test the drag MSD function still fail under 5V. 3.Prepared the FCC ACR document for TWR-KE18F.
WW20 | Eric | Wang Ben | 2016/4/19 |  | 2 | 6 | Kinetis E | MT512P | Execution |  | Q1'16 | System Cases-BLDC demo |  | 1.BLDC demo porting is on-going.Coding is 80% done.Will do system intergration debug and test later. 2.Found three SDK2.0 headfile and driver issues duing coding.Raised JIRA tickets in system and feedback to SDK team.The ticket numbers are KPSDK-10772,KPSDK-10797 and KPSDK-10798.
WW20 | Eric | Wang Ben | 2016/2/1 |  | 0.5 | 6 | S08 | MC9S08SU16 | Execution | Marketing launch 6/10 | Q1'16 | System Engineering |  | 1.P&E updated the CW service pack for SU16, verfied it is ok to download code to flash.
WW20 | Eric | Chen Yonggang | 2016/3/28 |  | 2 | 18 | Kinetis E | KE15Z | Execution | TSI demo board design - PCB Layout - 5/27 | Q4'15 | Board - Design |  | Finished LCD(Layout Consideration Document) writing to specify layout requirements. Finished all part library building in Agile system. Layout was started on May/09 and on-going by Jimmy, finished placement now.
WW20 | Eric | Chen Yonggang | 2016/5/2 |  | 1 | 2.5 | Kinetis E | KE15Z | Execution | TSI demo board design - PCB Layout - 5/27 | Q4'15 | Training |  | Supported FTF Austin Touch demo show. Helped Marketing Michael set up FRDM-TOUCH demo, and FreeMASTER GUI in the shortest time, as KE15Z Marketing Neil cancelled the trip to Austin.
WW20 | Eric | Chen Yonggang | 2016/5/9 | 2016/5/9 | 1 | 1 | Kinetis E | KE15Z | Execution | TSI demo board design - PCB Layout - 5/27 | Q4'15 | Documentation - Data Sheet |  | Conducted a meeting to update KE15Z datasheet with the existing data that BACES team tested. The ADC, DAC, IDD, IO, LPFLL and PMC chapters are updated after the meeting.
WW20 | Eric | Chen Yonggang | 2016/5/11 | 2016/5/11 | 0.5 | 0.5 | Kinetis E | KE15Z | Execution | TSI demo board design - PCB Layout - 5/27 | Q4'15 | Alpha Customer Support |  | Answered Jap FAE questions on TSI demo, FlexIO demo in KE15Z SDK ER. FAE want to know how to run the mutual TSI demo, and how to measure PWM output in FlexIO demo. Answered Jap FAE question about the feasibity to use KE14F header files and settings to debug KE18F device, as customer Mitsubishi target is KE14F, but they only have KE18F samples.
WW20 | Eric | Chen Yonggang | 2016/5/10 | 2016/5/10 | 0.5 | 0.5 | Kinetis E | KE15Z | Execution | TSI demo board design - PCB Layout - 5/27 | Q4'15 | Board - Design |  | Updated FRDM-KE15Z Schematic and Layout from A2 to B version for the 1Kpcs production board building. The schematic changes only include replace U13 MCU KE15Z and E1,E2 touch pads with the normal parts in Agile system. Sent out the latest schematic to SDK team for review.
WW20 | Eric | Chen Xinyu | 2016/3/25 |  | 0.5 | 7.5 | Kinetis E | MT512P | Execution |  | Q1'16 | Documentation - Data Sheet |  | 1. MT256P datasheet is under updating by BACES and Doc team. 2. MT512P datasheet has been generated a new version, which marked all the data which need BACES/TE/PE test to TBD. And later need to fill in the data which must be reused by MT256P when MT256P DS is ready.
WW20 | Eric | Chen Xinyu | 2016/3/25 |  | 2.5 | 14.5 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | 1. Finished the LPI2C adder use case for Standard, Fast, Fast+ modes. Got the LPI2C adder data on FRDM-KE15Z. Later will do the Ultra Fast mode use case. 2. Discussed with PE for the KPET data collection, Li Wen is learning about the use cases and how to collect data. We still need to co-work with PE to make KPET data collection task easier.
WW20 | Eric | Chen Xinyu | 2016/4/22 |  | 0.5 | 1 | i.MX | i.MX6RT | Feasibility | Plan | Q4'16 | Documentation - Others |  | 1. Reviewed PRD, raised some questions on the doc, SW, HW requirement. 2. Discussed on the SW delivery which may not ready for FreeRTOS support on some drivers. 3. Discussed on the HW plan.
WW20 | Richy | Howard Liu, Liu Zhen | 2015/7/16 |  | 5 | 86.5 | Kinetis E | MT512P | Execution |  | Q3'16 | System Cases |  | The FTM initialization trigger and external triggers are Ored together to generate one FTM trigger as an input of TRGMUX module in MT512P that's different from the MA512 PTV silicon. Changed the interrupt used for compressor control calculation since initialization trigger cannot be used as standalone trigger any more. (Howard Liu) Porting code from 3 in 1. it's finished now. debug is ongoing. (Alex Liu)
WW20 | Richy | Richy Ye | 2016/4/27 |  | 0.5 | 1.5 | i.MX | i.MX6RT | Feasibility |  | Q4'16 | System Cases |  | Had core team meeting to track the activities from different functional group. A question was raised about if the motor control can be implemented on FreeRTOS, and provided the BLDC motor control example code with MQX (High priority kernel interrupt used for motor control timer routine) on K60 to software team for feasibility evaluation.
WW20 | Richy | Richy Ye | 2016/1/25 |  | 0.5 | 9 | UHV | MU64 | Concept | Feasibility | Q3'16 | Features definition |  | MU64 entered into concept phase. Had meeting with product owner, analog design and systems/architecture to discuss the GDU design risk with HGx >20V, VBSx/VCP higher voltage (38V to 45V), and boot strap voltage with 8V/11V option.
WW21 | william | Wang Hao | 2016/3/21 |  | 2 | 10 | Kinetis K | K4TV | Feasibility | Plan | July 21st | Documentation - Data Sheet |  | Got high level schedule for K4TV as follows. 7/21/2016 Tapeout 10/17/2016 Fabout 11/7/2016 Engineering sample Based on latest ADD, K4TV will add chip2(at 200MHz) in the plan and FlexSPI is also added. Evaluation of FlexSPI need connect external NOR flash with flying wire so does not need new board plan. Prepare items need to be included in draft datasheet, as there is no plan for customer facing datasheet, it will be mostly based on validation result to cover power consumption part.
WW21 | william | Wang Peng | 2016/3/25 |  | 1 | 2.5 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | Finish to debug and measure ADC adder user case, then upload to git.
WW26 | william | GuoJia | 16/3/2015 | 2015/5/20 | 4 | 9 | Kinetis L | KL28 | Execution |  |  |  |  | 1. After the 14 KL28-ZEM boards send to Shanghai, I found all the KL28 MCU cannot be connected by SWD interface when K26 is not powered. Later located the root cause is, after U31 and U32 is added on the board, even USB_5V_SDA is not connected, the P3V3_SDA rise from 0.57V to 2.29V, then make U13 working, then SWD interface of KL28 is affected. Then provided a workaround, by which if somebody need to debug KL28, the code provided must be downloaded to K26. This code would drive PTA4/SDA_SWD_EN low, to make KL28 SWD interface work. 2. Continue locating the LED issue, rework 3 bad board, one of them is working correctly. This can prove this issue is caused by soldering. 3. LPI2C & LPSPI use case, about 70% finished, some slave use case is till going on. 4. L5K MK USB certification test passed. But according to the feedback, there are two issues: 1)The signal quality of HOST is not so good although it has passed the test, it may be related to the rework. 2) For the HOST test, the voltage is only 4.80v, although it pass the test, but it is a bit low. (The spec is 4.75~5.25) . I have reworked the HOST board to improve these issues, waiting to see if the result would be any better.
WW21 | Eric | Chen Xinyu | 2016/3/25 |  | 0.5 | 8 | Kinetis E | MT512P | Execution |  | Q1'16 | Documentation - Data Sheet |  | 1. A draft MT512P datasheet is generated with all data planning to test by BACES/TE marked as TBD. The data which should be reused from MT256P is also updated. The power mode transition simulation results are also updated. 2. Sent to S&A for review, if no problem, should be able to delivery to alpha customer.
WW21 | Eric | Chen Xinyu | 2016/3/25 |  | 1.5 | 16 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | 1. Finished the LPI2C Ultra-Fast mode use case, and got data. 2. Discussed with PE/BACES to work out a easy way for PE to collecting data on Bench, which is get use case configurations by PTD pin groups set by the Labview on PC. Use button to enter into different measurement stage.
WW21 | Eric | Chen Xinyu | 2016/4/22 |  | 1.5 | 1 | i.MX | i.MX6RT | Feasibility | Plan | Q4'16 | Documentation - Others |  | 1. Reviewed PRD v0.2 and ADD v0.1. Provide several comments like: 1) why need both ENC and QTimer module, QTimer already has the Quadrature decoder feature 2) Request S&A to figure out the clearly clock tree and power domain (include sub-power-domain) as a table 3) Request for the performance target, especially for the marketing required application use case. 4) Request to have power mode mapping between the Core Platform and SoC 2. Collecting the Debug Probe tool and boards requirements for SE team.
WW21 | Eric | Chen Xinyu, Terry Lv | 2016/5/18 |  | 2 | 2 | Kinetis K | KS22F256N | Launching |  |  | Documentation - RM |  | 1. The KS22 RM first Chinese version (Partly from chapter 1-18) has been released on the Website. 2. Reviewing the Chinese version of KS22 RM part2 on the DMAMUX/DMA. Plan to finishe Part2 by end of May 3. Reviewing the Chinese version of KS22 RM part2 on the FMC. The translation quality is poor. Need to spend more time on it. Currently 40 review commits are raised.
WW21 | Eric | Wang Ben | 2015/11/23 |  | 2 | 65.5 | Kinetis E | MT512P | Execution | Alpha customer Support 6/1 | Q1'16 | System Engineering |  | 1.DAPlink issue could be reproduced by SW team, they are still debugging the issue,it seems to be related to the MDM-AP flash-ready issue,which was reported to design team.The MSD flash programming gets stuck at a certain point waiting for an MDM-AP mass erase to complete, but the operation never completes. 2.SDK team reported the DAC output function on pin on TWR-KE18F are easily damaged during test.They said 2 of 5 boards are broken.Got the damaged board and verified the DAC output pin is truely broken down.But the pin other functions are ok.Did some test on a new board, but did not duplicate this issue.Will follow up to see if it will happen again. 3.Ported IRDA demo from SDK1.3 to SDK2.0 and uploaded to the MT512P usecase repository.TWR board IRDA circuit validation does not covered by SDK team in demos or examples.
WW21 | Eric | Wang Ben | 2016/4/19 |  | 2 | 8 | Kinetis E | MT512P | Execution |  | Q1'16 | System Cases-BLDC demo |  | 1.BLDC demo porting is on-going.Coding is 100% done.Single TWR board debug and test completes. After TWR-MC-LV3PH board is ready,will do intergration test.
WW21 | Eric | Chen Yonggang | 2016/5/19 | 2016/5/19 | 1.5 | 1.5 | Kinetis E | KE15Z | Execution | TSI demo board design - PCB Layout - 5/27 | Q4'15 | Documentation - Errata | MT256P 1.1 TO on 5/19 with the metal fixed IO for PESD. QMS signoff to 4.0 stage | Updated MT256 Errata: ERR010355: Access to the reserved address(40056008~40056fff) won't cause hard fault. 0xERR009380: Reading FlexIO register when FlexIO functional clock is disabled results in a bus hang.
WW21 | Eric | Chen Yonggang | 2016/3/28 |  | 1 | 19 | Kinetis E | KE15Z | Execution | TSI demo board design - PCB Layout - 5/27 | Q4'15 | Board - Design |  | Supported TSI EVB PCB Layout which is under development by Jimmy, finished the draft layout, and will send out for review 5/23.
WW21 | Eric | Chen Yonggang | 2016/5/9 |  | 2 | 3 | Kinetis E | KE15Z | Execution | TSI demo board design - PCB Layout - 5/27 | Q4'15 | Documentation - Application Notes |  | Writing Appnotes for ADC calibration, 80% done, discussed and studied the calibration algorithm with IP owner.
WW21 | Richy | Howard Liu, Liu Zhen | 2015/7/16 |  | 4 | 90.5 | Kinetis E | MT512P | Execution |  | Q3'16 | System Cases |  | Debug sensor-less PMSM demo based on HVP platform, and the motor can run basically now. Solved some problems in debug process. Next step is to optimize code and write FCC test document.
WW21 | Richy | Richy Ye | 2016/4/27 |  | 1.5 | 3 | i.MX | i.MX6RT | Feasibility |  | Q4'16 | System Cases |  | Completed two block diagrams of 4-motor control user case on i.MX6RT for next week product council review.
WW22 | william | wang Peng | 2016/3/25 |  | 1 | 1 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases |  | Review the TSI demo board, add the some comments to improve the signal and GND integrity, also has a discussion with designer to align the comments.
WW22 | william | GuoJia | 16/3/2015 |  | 4 | 13 | Kinetis L | KL28 | Execution |  |  |  |  | 1. Meet some issue when making the LPI2C slave demo code. AM0F & RDF is always set for each byte transfer, which is not reasonable. 2. For L5K MK USB certification, VBUS output is 4.95V, it is OK. But the result of signal quality is not improved after reworking the board. We are doubting this is caused by the test wire. Alfred will make a further test in lab.
WW22 | william | Wang Hao | 2016/5/25 | 2016/5/26 | 2 | 12 | Kinetis K | K4TV | Plan | Execution | July 21st |  | Planning summit | Attend K4TV planning summit and present Apps team plans to support use case and datasheet. Main use case for K4TV includes: Coremark and while(1) for power estimation and performance; performance monitor check with FlexSPI and local cache, CAUv3 validation. Main gap for supporting this is no performance monitor block guide received yet and no specific CAUv3 use case requested from system team.
WW22 | william | YangXi | 16/3/2015 |  | 1 | 12 | Kinetis L | KL28 | Execution |  |  | Documentation - Application Notes | doc update: | KL28’s document update: 1. AN5231: Clock management and distribution in KL28, update comments from doc team and approve to publish. 2. TWR-KL28Z UG, update comments from doc team and approve to publish 3. AN: Getting started with KL28 dual core: put to doctracker, it will not publish currently.
WW22 | william | Jia Ding | 2016/5/23 |  | 3 | 3 | Kinetis L | KL28 | Execution |  |  | System Cases |  | Ported the Flexion 8080 LCD code to a LCD panel with ILI9325 driver device, and a LCD panel with ILI9341 driver. Got started to write an application note based on one of the LCD panels.
WW22 | Eric | Wang Ben | 2015/11/23 |  | 3.5 | 69 | Kinetis E | MT512P | Execution | Alpha customer Support 6/1 | Q1'16 | System Engineering |  | 1.DAPlink issue root cause is still under investigation.SW team also got new board and samples to do further test. 2.DAC output pin damage issue on TWR-KE18F could not be reproduced by test team and us.Asked them to do more test during SDK GA release. 3.Checked with validation team on the alpha customer corner cases, all the test cases have been validated ok.During test, found one lpi2c module issue. An errata e10364(LPI2C sends STOP condition if transmit FIFO is empty on completion of a master-receive transfer) has been raised in design PDM. 4.Revised TWR-KE18F schematic from rev A to A1,updated openSDA reset capacitor from 0.1uF to 1000pF, made it consistent with FRDM-KE15Z.Uploaded the latest BOM to Agile to start materials purchasing. 5.Prepared the TWR-KE18F FCC certification software. Meanwhile the code for HVP-KE18F is also ready. Shipped two boards to thrid party to do FCC certification. 6.Shipped two boards of TWR-KE18F to USA and Rožnov SE team for local support. 7.Suport marketing to collect materials(SW,HW,document) for alpha customer promotion.Wrote the quick start guide for TWR-KE18F.
WW22 | Eric | Wang Ben | 2016/4/19 |  | 1.5 | 9.5 | Kinetis E | MT512P | Execution |  | Q1'16 | System Cases-BLDC demo |  | 1.Did intergration test with TWR-KE18F and MCLV3PH board. Motor could start and run correctly.BLDC demo porting is basically done. Will do longer test to see if any issues. 2.Next,plan to revise the application note from MA512 to MT512P, since both the hardware and software are changed.
WW22 | Eric | Chen Xinyu | 2016/3/25 |  | 0.5 | 8.5 | Kinetis E | MT512P | Execution |  | Q1'16 | Documentation - Data Sheet |  | 1. Updated the DS with Shawn and William's comments. 2. Updated the DS with IO specification of PAD delay and rasing/falling timing.
WW22 | Eric | Chen Xinyu, Terry Lv | 2016/5/18 |  | 1.5 | 3.5 | Kinetis K | KS22F256N | Launching |  |  | Documentation - RM |  | 1. Finished the DMAMUX/DMA chapters review. 2. Finished FMC chapter review. Submit 20 new comments.
WW22 | Eric | Chen Xinyu | 2016/4/22 |  | 4 | 1 | i.MX | i.MX6RT | Feasibility | Plan | Q4'16 | Documentation - Others |  | 1. Reviewed the 2nd version of ADD. No big problem found, but still need S&A to delivery more information like clock tree, power domain relationship, etc. 2. Reviewed the EVK board diagram, raised several comments. Suggest to add OpenSDA circuit for easy of use, raise concerns on the core board power supply can be powered by one single USB or not, several peripherals need to be added, like SPDIF, CAN. 3. Consult with US KUltra Apps leader, Xiaodong, Richy team and ECOVACS FAE for the real use cases. Drafted the use case plan and Application Note plan. 4. Research on the competitors products like STM32F7, SAM-V70 and TI AN335x. STM32F7 has the best ecosystem including solution of RTOS, Filesystem, stacks, GUI and Tools. We still have big gap on the software and tools delivery reqruiements in the PRD. To promote such M7 high performance chip without open source ecosystem like Linux, still need lots of work to do to build ecosystem by us and 3rd party.
WW22 | Eric | Chen Yonggang | 2016/5/9 | 2016/5/30 | 2 | 5 | Kinetis E | KE15Z | Execution | TSI demo board design - PCB Layout - 5/27 | Q4'15 | Documentation - Application Notes |  | Finished ADC calibration Appnotes, sent to core team for review.
WW22 | Eric | Chen Yonggang | 2016/3/28 |  | 2 | 21 | Kinetis E | KE15Z | Execution | TSI demo board design - PCB Layout - 5/27 | Q4'15 | Board - Design |  | Reviewed TSI EVB layout, re-allocate TSI channel and SPI pins, fixed TSI signal cross talk problems and improved GND plane placement for EMC performance.
WW22 | Eric | Chen Yonggang | 2016/5/25 | 2016/5/25 | 0.5 | 0.5 | Kinetis E | KE15Z | Execution | TSI demo board design - PCB Layout - 5/27 | Q4'15 | Alpha Customer Support |  | Supported KE class in US FTF. There're 43 attendees join the KE class in FTF, including Electrolux. On FAQ part, the customer interest mostly at the new TSI capability.
WW22 | Richy | Howard Liu, Liu Zhen | 2015/7/16 |  | 3 | 95.5 | Kinetis E | MT512P | Execution |  | Q3'16 | System Cases |  | 1, FCC test document and related project files have been sent to Audix technology company for test. 2, Optimized code and added other function in code. pre-study one paper of current reconstruction with one shunt which is searched on IEEE, will realize it on KE18 platform next week.
WW22 | Richy | Richy Ye | 2016/4/27 |  | 1 | 4 | i.MX | i.MX6RT | Feasibility |  | Q1'17 | System Cases |  | 1, Completed traceability matrix sheet review and gave the comments. 2, Discussing the 4 motors control use case enablement, the key issue is the board support, no conclusion is gotten now.
WW23 | william | Wang Hao | 2016/5/30 |  | 2 | 14 | Kinetis K | K4TV | Plan | Execution | July 21st | System Cases |  | Review both FlexSPI and QuadSPI block guide to check differences between these two modules and any chance to reuse existing QuadSPI code. Identify use cases for running FlexSPI. Still have not received reply from design team for performance monitor block guide.
WW23 | william | GuoJia | 16/3/2015 |  | 5 | 18 | Kinetis L | KL28 | Execution |  |  |  |  | Finished the LPI2C use cases, and finished the AN draft for LPI2C quick guide.
WW26 | william | Jia Ding | 2016/5/23 |  | 3 | 6 | Kinetis L | KL28 | Execution |  |  | System Cases, Documentation |  | Completed the FlexIO 8080 LCD demo for the application note, which support 8-bit and 16-bit bus width. Still working on writing the application note.
WW23 | william | Jia Ding | 2016/6/3 |  | 0.5 | 0.5 | Kinetis L | KL28 | Execution |  |  | System Engineering |  | Reviewed the getting started video script for marketing team. Given about a dozen a comments.
WW23 | william | wang Peng | 2016/3/25 |  | 1 | 1 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-TSI evaluation board |  | Have a meeting with team to review comments, and also review the updated layout and finalize it.
WW23 | Eric | Chen Xinyu | 2016/3/25 |  | 0.5 | 9 | Kinetis E | MT512P | Execution |  | Q1'16 | Documentation - Data Sheet |  | Collecting the AUTO I/O design owner's feedbacks to MT512P DS. Most of the comments have been accepted. Few of them need to discuss with System and Design later.
WW23 | Eric | Chen Xinyu, Song Juanjuan | 2016/3/25 |  | 3.5 | 19.5 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | 1. Finished the LPSPI Adder program. 2. Got the LPSPI draft adder data under different functional clock and baud rate. 3. Writing the function of getting adder configurations from pin set by tester, which would be used by PE. 4. During LPSPI Adder program development, found one SDK API issue. Ask SW owner to fix.
WW23 | Eric | Chen Xinyu | 2016/4/22 |  | 0.5 | 6 | i.MX | i.MX6RT | Feasibility | Plan | Q1'17 | Documentation - Others |  | Continue to research on the competitors products like STM32F7, SAM-V70 and TI AN335x.
WW23 | Eric | Chen Xinyu, Terry Lv | 2016/5/18 |  | 4 | 7.5 | Kinetis K | KS22F256N | Launching |  |  | Documentation - RM |  | 1. The KS22 RM Part2 review (Chapter 19-30) has been done. 2. Reviewed the Part3 DSPI chapter.
WW23 | Eric | Wang Ben | 2015/11/23 |  | 2 | 71 | Kinetis E | MT512P | Execution | Alpha customer Support 6/10 | Q1'16 | System Engineering | 2.HVP-KE18F FCC test failed. This issue exists even when KE18F MCU has no code, only pre-installed openSDA firmware. So the root cause should be the hardware ,not related to software. Current workaround is if we add a magnetic ring on the USB cable, it could pass FCC test. The root cause analysis is under discusstion with Rožnov team. | 1.DAPlink debug in on-going. SE team re-built the DAPlink proejct, found the root cause of MSD function fail at 5V was due to the SWD timing issue.After optimized, this issue was fixed and verifed ok on several TWR boards. Another issue still exists is the warning/errors window pop up when download code with IAR.SW team is still investigating on it. 2.HVP-KE18F FCC test failed. This issue exists even when KE18F MCU has no code, only pre-installed openSDA firmware. So the root cause should be the hardware ,not related to software. Current workaround is if we add a magnetic ring on the USB cable, it could pass FCC test. The root cause analysis is under discusstion with Rožnov team. 3.Aligned with core team, the ownership of motor contorl reference demos will be transftered from China SE team to Roznov team. They will cover all the BLDC,PMSM and ACIM demos both on TWR-KE18F and HVP-KE18F. We will still own the 3in1 reference. 4.Supported Japan FAE on software environment setup for KE18F.
WW23 | Eric | Wang Ben | 2016/4/19 | 2016/6/3 | 1.5 | 11 | Kinetis E | MT512P | Execution |  | Q1'16 | System Cases-BLDC demo |  | 1.Finished BLDC demo porting and testing.All the function works well. Three SDK JIRA tickets raised before were fixed by SW team. 2.Revised the BLDC appnote for MT512P, but it will not publish since the ownership was transftered to Roznov team.
WW23 | Eric | Wang Ben | 2016/2/1 |  | 1 | 7 | S08 | MC9S08SU16 | Execution | Marketing launch 6/10 | Q1'16 | System Engineering |  | 1.Reviewed and signed off the RM Rev2 for marketing launch. Found some doc issues, which are fixed by document team. 2.Generated the errata report for SU16. The only Errata is the PDB issue, VERFH damage issue is removed. 3.CW team reported they could not access the whole SRAM area(768B), but only 256B. The root cause is the samples PE sent them has IFR bit issue, which did not open the other 512B. Confirmed the samples they shipped to us for reference board build also have this issue. They will ship out the new samples.
WW23 | Eric | Chen Yonggang | 2016/3/28 |  | 3 | 24 | Kinetis E | KE15Z | Execution | TSI demo board building - 7/2 | Q4'15 | Board - Design |  | Finished PCB layout review. Updated schematic and released schematic/layout in Agile system on schedule to start board building.
WW23 | Eric | Chen Yonggang | 2016/6/3 | 2016/6/3 | 0.5 | 0.5 | Kinetis E | KE15Z | Execution | TSI demo board building - 7/2 | Q4'15 | Alpha Customer Support |  | 1. Jap FAE is going to hold a Flash Access Cotrol seminar for Mitsubishi Inverter project. Answered FAE's questions on Flash about the read margin and double phrase FTFE command. 2. FAE You Dawei visited Nanjing Diehl and held a KE+ & TSI seminar, customer requirements include (1). IEC61000-4-6 performance, customer needs pass 6V, 3S test standard by end customer; (2) Quick response: 0.1s for each key; (3) need DMA support to fetch TSI channel data quickly. Answered FAE's questions on these customer requirements to help FAE prepare the seminar, and checking with Marketing whether we can send 1pcs (MA512) TSI EVB board to customer to test the 4-6 performance.
WW23 | Richy | Howard Liu, Liu Zhen | 2015/7/16 |  | 2 | 96.5 | Kinetis E | MT512P | Execution |  | Q3'16 | System Cases |  | 1) Prepared the 4 heatsinks and contacted 3rd party for customizing the inductors for new 3in1 power stage boards. 2)Had a look at the SDK2.0, not only the code structure is changed, but also some head files is removed and not supported any more, such as fsl_bitaccess.h and xxx_extension.h. The motor control code controls the module resisters directly by using the bit operation macros defined in these files. So all low level initialization code need re-coding. .(Howard Liu) 3)Assist Wang Ben to do some related work about FCC certifation. (Alex liu)
WW24 | William | Wang Hao | 2016/5/30 |  | 0.5 | 14.5 | Kinetis K | K4TV | Plan | Execution | July 21st | Documentation - Data Sheet |  | Prepare draft datasheet to include items need to be collected on K4TV.
WW24 | william | GuoJia | 2016/10/6 |  | 1 | 1 | Kinetis L | KL28 | Execution |  |  | OOBE | TWR-KL28Z production missing OOBE demo | FRDM-KL28Z production missing OOBE demo. Uploaded updated FSW to Agile with OOBE firmware and installation guide included. Preparing OOBE workflow and checklist to share with other team members to prevent this from happening again.
WW24 | william | YangXi | 2016/10/6 |  | 1 | 1 | Kinetis L | KL28 | Execution |  |  | OOBE | TWR-KL28Z production missing OOBE demo | TWR-KL28Z production missing OOBE demo 1. Uploaded updated FSW to Agile with OOBE firmware and installation guide included.
WW24 | william | Jia Ding | 2016/6/8 |  | 2 | 1 | Kinetis L | KL28 | Execution |  |  | System Engineering |  | 1. Prepared materials for the getting started web pages, including video scripts, hands on code, screenshot of tool configurations, OpenSDA firmware, etc. 2. Found the default OOBE of the Freedom and Tower boards are incorrect. Worked with team members to figures out the workaround. 3. Found there's some issue with the J-Link V2.1 firmware. When opening a terminal tool after re-powering the board, it would take a while to connect the port and the baud rate would not match (Tera term), or the connection would fail (Putty). The baud rate needs to be configured again (Tera term), or the terminal need to be opened again (Putty). Worked with team members and found there's an update on Segger's website which could solve this issue. Delivered this new update to marketing team for the launching.
WW24 | Eric | Wang Ben | 2015/11/23 |  | 1.5 | 72.5 | Kinetis E | MT512P | Execution | Alpha customer Support 6/30 | Q1'16 | System Engineering |  | 1.PE/TE reported LU failed issue on 64LQFP, if 10uF capacitor added on board between VDD (pin7&pin8) to GND (pin10), LU could pass.Suggest them to trial run more cases with 1uF/0.1uF capacitor to verify LU result. 2.DAP-link issue debug is on-going. SW team feedback they could reproduce the IAR download issue, guess the root cause may be related to IAR tools itself, they will ask help from IAR for further analysis. 3.Reworked one HVP-KE18F board with two capacitors to connect two GND planes. Shipped the board with HVP-KV31 to third party to try FCC test again. 4.Answered several questions from Japan FAE on hardware&software comparasion between MA512 and MT512P.They are concerned about the TWR board and SDK software changes between SDK1.3 and SDK2.0.
WW24 | Eric | Wang Ben, Chen Xinyu, Chen Yonggang | 2016/6/10 |  | 1.5 | 1.5 | Kinetis E | MT512P | Execution |  | Q1'16 | System Cases-Peripheral Adder |  | 1.Start coding for the peripheral adder use case on RTC,LPIT and LPTMR module. 2. Start coding for the LPI2C peripheral adder use case. 3. Drafted peripheral adder cases for ADC and CMP.
WW24 | Eric | Wang Ben | 2016/2/1 |  | 1.5 | 8.5 | S08 | MC9S08SU16 | Execution | Marketing launch Q4'16 | Q1'16 | System Engineering |  | 1.Got the new samples from PE, verified the IFR bit issue is resolved,whole 768bytes could be accessed. Will ship the new samples and reference board to factory to do rework. 2.Supported motor control team intenally on software environment setup and debug for SU16.
WW24 | Eric | Chen Xinyu | 2016/3/25 |  | 1.5 | 10.5 | Kinetis E | MT512P | Execution |  | Q1'16 | Documentation - Data Sheet |  | 1. Updated the DS with comments from I/O owner, S&A. 2. Finished the LPI2C performance and timing test code for BACES.
WW24 | Eric | Chen Xinyu | 2016/4/22 |  | 0.5 | 6.5 | i.MX | i.MX6RT | Feasibility | Plan | Q1'17 | Documentation - Data Sheet |  | Reviewed the 6ULL datasheet, which would be reused for i.MX6RT. Rasied comments in the DS for what need to be updated by which team.
WW24 | Eric | Chen Xinyu | 2016/5/18 |  | 1.5 | 9 | Kinetis K | KS22F256N | Launching |  |  | Documentation - RM |  | Finished review of KS22 RM Part3, chapters 43/44
WW24 | Eric | Chen Yonggang | 2016/6/6 | 2016/6/6 | 0.5 | 0.5 | Kinetis E | KE15Z | Execution | TSI demo board building - 7/2 | Q4'15 | Documentation - Data Sheet |  | Updated Datasheet by removing slew rate data as MT256 doesn't support this feature.
WW24 | Eric | Chen Yonggang | 2016/6/7 | 2016/6/8 | 1 | 1 | Kinetis E | KE15Z | Execution | TSI demo board building - 7/2 | Q4'15 | Alpha Customer Support |  | 1. There's NXP customer training event scheduled on July.15th in Singapore, which is target to customer R&D engineers. The KE15Z TSI will be added as a session in this event. Support the Regional Marketing Travis Heng about the training slides and touch demo setup together with NPI Marketing Neil. 2. Electrolux team in Stockholm (Sweden) is evaluating KE15Z256 on a Dishwasher HMI. Sent 30pcs 64LQFP samples to customer per Marking Fraser Mchenry's request.
WW25 | William | Jia Ding | 2016/6/3 |  | 2 | 4.5 | Kinetis L | KL28 | Execution |  |  | System Engineering |  | Reviewed the getting started web pages. Provided suggestions for the review versions.
WW25 | William | Jia Ding | 2016/5/23 |  | 3 | 9 | Kinetis L | KL28 | Execution |  |  | Documentation - Application Notes |  | Completed the FlexIO 8080 application note. Will share to review and submit soon.
WW25 | william | GuoJia | 2016/6/6 |  | 3 | 2 | Kinetis L | KL28 | Execution |  |  | Documentation - Application Notes |  | 1.Made the OOBE workflow and checklist to share with team members. 2.Made the use case for LPSPI slave application, about 30% finished.
WW25 | william | GuoJia | 2016/6/6 |  | 2 | 6 | Kinetis L | KL28 | Execution |  |  | Documentation - Application Notes |  | AN5301 -Using LPI2C on KL28 final review finished, and voted for publish.
WW25 | william | wang Peng | 2016/6/10 | 2016/6/17 | 2 | 2 | Kinetis E | MT512P | Execution |  | Q1'16 | System Cases-peripheral adder code |  | Finish lpuart and lpftm adder code, and upload to git.
WW25 | william | Wang Hao | 2016/5/30 |  | 2 | 16.5 | Kinetis K | K4TV | Plan | Execution | July 21st | Documentation - Data Sheet |  | Generated draft datasheet and send to core team for review.
WW25 | william | YangXi | 2016/6/3 |  | 1 | 1 | Kinetis L | KL28 | Execution |  |  | System Engineering |  | Reviewed the getting started web pages. Provided suggestions for the review versions.
WW25 | Eric | Wang Ben | 2015/11/23 |  | 1 | 73.5 | Kinetis E | MT512P | Execution | Alpha customer Support 6/30 | Q1'16 | System Engineering |  | 1.Had a separate meeting with system,design,PE/TE and QA to further discuss the 64LQFP LU issue. Test have been done to confirm that with 0.1/1/10 uF, all the LU test could pass w/o current limit setting.But SE team still raised concerns for the LU performance on customer side and would like to see if we can simulate the LU condition on EVB. IO ESD expert Michi said he would try to reproduce the issue on EVB, but on his opinion we could consider the LU test is passed based on current situation. 2.SW team thought the existing DAPlink issue is related to IAR toolchain, so we sent mail to IAR to explain the issues in detail and waiting for their feedback. 3.Discussed and came to agreement with Sammy that HVP-KE18F FCC test will be done and regarded as "pass" with a USB cable w/ Ferrite. Third party will do some test on HVP-KV31 to help us to identify the root cause later. 4.Answered Japan FAE some questions about SDK2.0 drivers.
WW25 | Eric | Wang Ben | 2016/6/10 | 2016/6/20 | 3 | 4 | Kinetis E | MT512P | Execution |  | Q1'16 | System Cases-Peripheral adder |  | 1.Finish three peripheral adder use cases of RTC,LPIT and LPTMR.
WW25 | Eric | Chen Yonggang | 2016/6/10 | 2016/6/17 | 3 | 4 | Kinetis E | MT512P | Execution |  | Q1'16 | System Cases-Peripheral adder |  | Finished peripheral adder use cases of ADC and CMP.
WW25 | Eric | Chen Yonggang | 2016/6/7 |  | 2 | 2 | Kinetis E | KE15Z | Execution | TSI demo board building - 7/2 | Q4'15 | Alpha Customer Support |  | 1. Sent 30pcs 64LQFP samples to FAE Mats Henriksson located in Sweden to support Electrolux evaluating. Got good news from Electrolux, the KE15Z Touch application is starting to work and is apparently much stronger than the S08PT version.The problems are around the sw library which is still not completely developed and Roznov team is working on that. 2. Communicated with Hangzhou FAE about Fotile IH cooker development status, and DFAE will visit customer to get more informantion and promote KE15Z on 6/21
WW25 | Richy | Howard Liu, | 2015/7/16 |  | 1 | 97.5 | Kinetis E | MT512P | Execution |  | Q3'16 | System Cases |  | MT512P NPI: 1) Went on porting the code to use SDK2.0 head files. Changed the folder structure to compatible with SDK2.0.
WW26 | William | Wang Hao | 2016/5/30 |  | 2 | 18.5 | Kinetis K | K4TV | Plan | Execution | July 21st | System Cases |  | Got Macronix SPI flash spec, plan to use their EVB for evaluating FlexSPI module; review QuadSPI driver in KSDK and check how much can be reused for FlexSPI.
WW26 | william | GuoJia | 2016/6/6 |  | 3 | 3 | Kinetis L | KL28 | Execution |  |  | Documentation - Application Notes |  | Finished the LPSPI use case test and draft for AN Using LPSPI on KL28.
WW26 | william | GuoJia | 2016/6/6 |  | 2 | 2 | Kinetis L | KL28 | Execution |  |  | Documentation - Others |  | Prepared and gave an online training for FAE team, the topic include the new feature on KL28. New features on system clock, LPSPI, SPI2C, FLEXIO are introduced in the training.
WW26 | william | Jia Ding | 2016/5/23 |  | 2.5 | 11.5 | Kinetis L | KL28 | Launching |  |  | Documentation - Application Notes |  | Modified the software package along with the FlexIO 8080 application note to make it compatible with KSDK 2.0.
WW26 | william | Jia Ding | 2016/6/24 |  | 0.5 | 0.5 | Kinetis L | KL28 | Launching |  |  | Training |  | Prepared the training slides on KL28Z FlexIO for FAE team.
WW26 | Eric | Chen Yonggang | 2016/6/20 | 2016/6/24 | 3.5 | 3.5 | Kinetis E | KE15Z | Execution | TSI demo board building - 7/2 | Q4'15 | Alpha Customer Support |  | 1. Answered Jap FAE question on WDOG, why writing TOVAL when disable WDOG in system init. As mentioned in RM, the new configurations take effect only when all registers including TOVAL are written once after reset. 2. Answered Jap FAE question on ADC calibration about how to do when calibration failed 3. Got touch library 2.0 from Roznov team, and it can be released to alpha cutomer for testing. 4. Supported TSI EVB board building. Provided board vendor the parts that they don't have, and confirmed with PE that the 1.1 sample will be sent out on 7/1 for TSI EVB board building and FRDM 1.1 version hand soldering. 5. Korea FAE reported reset problem when ran the flash demo in Keil for Samsung home appliance, dual inverter module with KE14F512 project. Supported FAE solve the reset problem by moving the flash operation code into RAM. But met another flash error bit set problem when execute flash erase sector command, under debugging.
WW26 | Eric | Chen Yonggang | 2016/6/24 |  | 1 | 1 | Kinetis E | KE15Z | Execution | TSI demo board building - 7/2 | Q4'15 | System Cases-KPET |  | Started KPET development for TSI, LPTMR and LPIT module, 10% done.
WW26 | Eric | Ben Wang | 2016/11/23 |  | 3.5 | 77 | Kinetis E | MT512P | Execution | Execution | Q1'16 | System Engineering |  | 1.Core team agree to make MT512P move forward with max speed up to 168MHz instead of 160Mhz in high speed run mode.All the documents should be updated.Team will continue to monitor the yield on coming wafer lots. 2.HVP-KE18F FCC test is done and regarded as "pass" with a USB cable w/ Ferrite, no schematic and layout change on production board.Rozonv team reported one issue that if using the JTAG/SWD interface on board instead of OpenSDA USB, code download to KE18F will be failed. Did some tests on HVP-KE18F, but did not reproduce this issue. Later got feedback from them that they have resolved the issue and could download code now,there must be some problem with software drivers on their side. 3.Fixed one schemaitc symbol issue and layout lib issue on TWR-KE18F Rev A1, update TWR-KE18F to Rev B and upload to Agile, it will go for production build. 4.Collected and delivered all the peripheral adder source code to BACES team, support them finish the peripheral adder test cases. 5. IAR starts to look into the DAPlink download issue, they request two more boards(TWR-KE18F and FRDM-KE15Z) from us. The boards have been shipped out, pre-installed the DAPlink firmware. 6. For 64LQFP LU issue, IO ESD expert Michi does not require us to do the additional experiment on EVB. Add one de-cap between VDD and VSS meets the LU test spec.PE committed to do another test on 100LQFP package, but only 64 pins bond out, others keep floating. They want to use this to compare with the result of 64LQFP.
WW26 | Eric | Ben Wang | 2016/6/24 |  | 1 | 2 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | Studied the KPET on-line tool and template code, will start pre-coding and test on FRDM-KE15Z.
WW26 | Eric | Ben Wang | 6/23'2016 |  | 0.5 | 0.5 | Kinetis K | KS22F256N | Launching |  |  | Documentation - RM |  | Finish review the PDB chapter, provided about ~40 comments.
WW26 | Richy | Howard Liu | 2015/7/16 |  | 1 | 98.5 | Kinetis E | MT512P | Execution |  | Q3'16 | System Cases |  | MT512P NPI: MT512P NPI: 1) Found the several potential replacements for the Op amps on the original 3in1 main boards that are obsolete. 2) PFC inductors are still manufactured and will be available for assembly later.
WW27 | William | GuoJia | 2016/6/27 |  | 2 | 2 | Kinetis L | KL28 | Execution |  |  | Certification - USB |  | Lab report both the host and device board is not working and mailed the two boards back to us. After checking root cause located. 1. For device board, the image inside KL28Z is spoiled, and it is fixed by re-programming. Informed test engineer how to avoid it from happening again. 2. For host board, a wire which is added in rework has been broken. It is fixed by reconnecting the wire. Lab report the eye diagram test fail by 5-meter USB cable. We also reproduced this issue in our lab. Later we are doubting this is related to the resistor cascaded in the D+ and D- signal. After a lot test, we found when we are using the 39 Ohm resistor, the test passed. Now, the two board after test has been mailed to Shenzhen lab for further test.
WW27 | william | GuoJia | 2016/6/28 |  | 2 | 2 | Kinetis L | KL28 | Launching |  |  | Documentation - Application Notes |  | Finished the draft for AN - Using LPSPI on KL28Z and sent out for review. But later found one issue that multi-IO is not supported in the SDK driver. Need to add a demo to access the flash which support 4-bit mode in the AN.
WW27 | william | Wang Hao | 2016/5/30 |  | 1 | 19.5 | Kinetis K | K4TV | Plan | Execution | July 21st | System Cases |  | Aligned with BACES team on board and header file schedule (around early Oct); continue with FlexSPI module usecase check.
WW27 | william | Jia Ding | 2016/5/23 |  | 2 | 13.5 | Kinetis L | KL28 | Launching |  |  | Documentation - Application Notes |  | Updated the FlexIO 8080 application note and the demo code based on team member's feedback, and submitted to doc-tracker.
WW27 | william | Jia Ding | 2016/6/29 |  | 1.5 | 1.5 | Kinetis L | KL28 | Launching |  |  | System Engineering |  | 1. Prepared quick started packages for FRDM-KL28Z and TWR-KL28Z72M. 2. Measured current adder of RTC and LPTMR, and found the RTC current are abnormal, larger than expected. Still looking for the cause.
WW27 | Eric | Ben Wang | 2016/11/23 |  | 2 | 79 | Kinetis E | MT512P | Execution | Execution OOBE --7/8 | Q1'16 | System Engineering | DAPlink issue is resolved by IAR and verfied ok, they will release a public zip patch on IAR website first, then do a public service pack after their vocation period in late Aug. | 1.TWR-KE18F and HVP-KE18F production board build started.Preparing the FAT and OOBE code for TWR.Roznov team will cover HVP-KE18F. 2.DAPlink issue is resolved by IAR and verfied ok, they will release a public zip patch on IAR website first, then do a public service pack after their vocation period in late Aug. 3.Marketing requested us to do a core mark comparsion test between HSRUN 160Mhz and 168Mhz .From the test result, we could see about 5% performance improvement when core clock increase 8Mhz.
WW27 | Eric | Ben Wang | 2016/6/24 |  | 3 | 5 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | 1.Finish coding and testing FTM module KPET use case.
WW27 | Eric | Chen Yonggang | 2016/6/29 |  | 2 | 2 | Kinetis E | KE15Z | Execution | OOBE code ready on 7/8 | Q4'15 | Board - OOBE |  | Developing FRDM-KE15Z OOBE code, 80% done.
WW27 | Eric | Chen Yonggang | 2016/6/27 | 2016/7/1 | 3 | 3 | Kinetis E | KE15Z | Execution | OOBE code ready on 7/8 | Q4'15 | System Engineering |  | 1. Found ADC long sample doesn't save power consumption during the peripheral adder test, reported this issue to ADC IP owner, and he confirmed it and will update ADC block guide accordingly. 2. Got MT256 1.1 samples, ran and passed simple tests like flash download, SCG clock switch, LPUART print, GPIO toggle. Will send the samples to factory for FRDM-KE15Z pilot and TSI EVB board building. Also gave 5pcs samples to Validation team for double check the silicon functions. 3. Electrolux started the KE15Z/TSI project, there're 5 or 6 engineers participating from Electrolux, across sites in Italy & USA. Customer's plan is to creat a technology demonstrator supporting TFT LCD and touch keys, and replace a Cypress that is currently used for Cap-Touch. 4. Submitted a disclosure in touch patent as a co-inventor.
WW27 | Richy | Howard Liu | 2015/7/16 |  | 1 | 98.5 | Kinetis E | MT512P | Execution |  | Q3'16 | System Cases |  | MT512P NPI: 1) PFC inductors and replaced Op amps are ready for assembly. Manufacture will assembly one board and run factory test first. Then ship the board to us. I'll test all functions then will assembly other boars if all tests are passed.
WW28 | William | Jia Ding | 2016/6/29 |  | 1 | 2.5 | Kinetis L | L5K | Launching |  |  | System Engineering |  | Measured current adder of RTC and LPTMR, and added code that used to wake up the device from VSS1 to make sure the IP running normal in the low power mode. The results seem normal and much smaller than baces team's results. Aligned within team and asked for baces team to measured again.
WW28 | William | GuoJia | 2016/7/4 |  | 0.5 | 0.5 | Kinetis L | KL28 | Execution |  |  | Certification - USB |  | 1.Prepare the FRDM-KL46 board for eye-diagram test. The test are planned to be finished in 7/11. 2.As the Allion engineer was in PTO last week, the test is delayed. They promised to give us the test report on 7/15.
WW28 | William | Guo Jia | 2016/7/4 |  | 4.5 | 4.5 | Kinetis L | L5K | Launching |  |  | System Engineering |  | Make LPSPI use case for multi-IO mode. Found one issue that in continuous mode, the dummy signal given out by LPSPI is not correct. Now I am waiting for design to clarify on it. Another issue I found is, when connecting to flash, and read a page in multi-IO mode, the output from SPI flash is not correct. I have contacted the engineer from the SPI flash company for help.
WW28 | william | Wang Hao | 2016/5/30 |  | 1 | 20.5 | Kinetis K | K4TV | Plan | Execution | Aug 11st |  |  | K4TV tapeout date delayed due to other project tapeout delay, new tapeout date being 8/11.
WW28 | Eric | Chen Xinyu, Lv Terry | 2016/5/8 |  | 0.5 | 0.5 | Kinetis K | KS22F256N | Launching |  |  | Documentation - RM |  | Reviewed the revised RM Part2 from 3rd Party based on our comments. There's still some comments not updated into this version, asked Vicky to check again.
WW28 | Eric | Ben Wang | 2016/11/23 |  | 2 | 81 | Kinetis E | MT512P | Execution | Documentation -- TWR user guide and AN | Q1'16 | Board - FAT Coding & test |  | 1.Finish OOBE/FAT coding and FSW document. 2.Reviewed and provided comments on TWR and HVP board QSG.Preparing writing the TWR user guide and AN of "Kinetis migration guide from KE0x to KE1x" next. 3.PE did the 100LQFP LU test with only stress the same pins/pads as LQFP64, the result is the same as LQFP64, it will still fail w/o de-cap between VDD and VSS.Michi suggest to do further tests to add back the power supply pins to see the difference.
WW28 | Eric | Ben Wang | 2016/6/24 |  | 3 | 8 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | 1.Finish coding and testing FlexIO UART KPET use case.
WW28 | Eric | Chen Yonggang | 2016/6/29 |  | 2 | 4 | Kinetis E | KE15Z | Execution | KPET ready on 7/15 | Q4'15 | Board - OOBE |  | 1. Finished FRDM-KE15Z OOBE code. 2. Finished 43pcs FRDM-KE15Z board manual resoldering with 1.1 KE15Z samples. Provided FSW/FAT files and DAP-LINK firmware for board factory test, and found DAP-LINK drag/drop issue on 20pcs boards while the other 20pcs board without this issue. The root cause is under debugging.
WW28 | Eric | Chen Yonggang | 2016/6/24 |  | 1 | 3 | Kinetis E | KE15Z | Execution | KPET ready on 7/15 | Q4'15 | System Cases-KPET |  | Finished LPTMR KPET code development, and developing TSI and LPIT.
WW28 | Eric | Chen Yonggang | 2016/7/8 | 2016/7/8 | 1 | 1 | Kinetis E | KE15Z | Execution | KPET ready on 7/15 | Q4'15 | System Engineering |  | 1. Submitted a ticket (TKT307951) in DesignPDM to improve ADC block guide on calibration chapter. 2. All chip level PESD testing on 1.1 sample are completed, the test result shows that the positive PESD damage level is +8KV and the negative PESD damage level is around -6KV.The 1.1 sample test result is much better than the previous 1.0 sample.
WW28 | Richy | Howard Liu | 2015/7/16 |  | 3 | 1900/4/11 | Kinetis E | MT512P | Execution |  | Q3'16 | System Cases |  | MT512P NPI: 1) Created the new workspace with new folder structure to remove the independence on the KSDK release. All references to the macros defined in the xxx_extension.h files were removed since this head file will not be provided in the SDK any more. Finished the code porting to use the KSDK2.0 head files.
WW29 | william | wang Peng | 2016/3/25 |  | 1.5 | 4 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | Complete the coding and debug of CMP and PDB,upload to git.
WW29 | william | Guo Jia | 2016/7/11 |  | 3 | 6 | Kinetis L | L5K | Launching |  |  | Certification - USB |  | 1. Host test passed, and Allion has sent out the report. 2. Device test failed, as on the VBUS a capacitor with the value between 1uF to 10uF is necessary, but we are using 0.1uF in the design. In fact a 4.7uF capacitor is the best choice for the test. Reworked a board with 4.7uF capacitor and sent out to Shenzhen lab for test. Two 4.7uF capacitor were also mailed out so the Allion engineer can add it on the board for test.
WW29 | william | Guo Jia | 2016/7/11 |  | 2 | 8 | Kinetis L | L5K | Launching |  |  | Documentation - Application Notes |  | Make the use case for accessing the SPI flash. Found one issue and need to be clarified by design. When in continuous mode, after TXMSK is set to be 1, it would not go back to 0 automatically after one frame is sent out, and the communication keeps until exit continuous mode.
WW29 | Eric | Ben Wang | 2016/11/23 |  | 2 | 83 | Kinetis E | MT512P | Execution | Documentation -- TWR UG ready on 7/31 | Q1'16 | System Engineering | 3.The root cause of DAPlink MSD drag/drop issue on TWR-KE18F and FRDM-KE15Z has been addressed.It is not related to DAPlink firmware itself, but due to the resistor value on reset circuit is too small,which make the level shifter works abnormally.After we update the the resistor from 100ohm to 2.2Kohm, the issue is resolved. | 1.PE did further LU test on 100LQFP with Michi's suggestion to add back the power supply pins. The result shows the high current happened in IDD test.The test report is under review by Michi and core team. 2.Since KE18F max frequency is changed to 168Mhz , TWR-KE18F needs to do the radiated emissions test again.Update the FCC software and ship the board to Audix Lab. No need to do it for HVP-KE18F. 3.The root cause of DAPlink MSD drag/drop issue on TWR-KE18F and FRDM-KE15Z has been addressed.It is not related to DAPlink firmware itself, but due to the resistor value on reset circuit is too small,which make the level shifter works abnormally.After we update the the resistor from 100ohm to 2.2Kohm, the issue is resolved. 4.SDK team reported another two issues when use IAR download code with DAPlink: a)After code is downloaded,we could not use external reset button to reset chip for the first time, but only with POR. b)When IAR choosing "custom reset strategy" configuration by default, it can not halt the MCU during code downloading,which means the previous programmed code in flash will execute once during new code downloading. Reproduced the issues and found out the workaround, the two issues are supposed to be related to IAR IDE because with Keil it did not happen. And I definitely find some issues in IAR KE18F.dmac and KE1xZ7.dmac files.We need IAR to fix the two issues in next release. 5.Working on the QMS workflow,it has to signoff to stage 5.0.
WW29 | Eric | Ben Wang, Chen Xinyu, Song Juanjuan | 2016/6/24 |  | 7.5 | 15.5 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | 1. Finished coding and testing FlexIO SPI KPET use case. 2. Finished the RTC KPET use case. 3. Porting the LPUART KPET use case to BACES board, and deliver to BACES owner to have a basic test. 4. Learning the KPET backend database XML format. 5. Checking the BACES IDD test program, and figure out how many BACESLINE IDD cases need to be added for KPET.
WW29 | Eric | Terry Lv | 2016/7/11 |  | 5 | 4 | Kinetis K | KS22F256N | Launching |  |  | Documentation - RM |  | Finish UART and LPUART chapters translation review. 211 review comments committed.
WW29 | Eric | Chen Xinyu | 2016/3/25 |  | 1.5 | 12 | Kinetis E | MT512P | Execution |  | Q1'16 | Documentation - Data Sheet |  | 1. Finished the LPI2C performance and timing program, and deliver to BACES. 2. Co-work with BACES to verify the LPI2C test results, now we still failed to pass the Fast+ mode under 400pF bus load. Suggest to change the Rp to re-test, waiting for BACES results. 3. Update the DS with BACES test results for Vpor, Vhys and also some data from I/O DS. 4. Go through the TBD items, most of them can be covered by on-going BACES and ATE test. But still have GAP on the ADC linearity Min/Max value, which ATE does not have plan for MT512P, and no data for us to reuse. Discussing with BACES/TE for the solution.
WW29 | Eric | Chen Yonggang | 2016/7/11 | 2016/7/13 | 2 | 5 | Kinetis E | KE15Z | Execution | TSI EVB software/appnotes ready 8/15 | Q4'15 | System Cases-KPET |  | Finished TSI, LPTMR KPET test code
WW29 | Eric | Chen Yonggang | 2016/7/13 | 2016/7/15 | 3 | 3 | Kinetis E | KE15Z | Execution | TSI EVB software/appnotes ready 8/15 | Q4'15 | System Cases-KPET |  | 1. Updated FRDM-KE15Z schematic for production board, change the reset resistor from original 100ohm to 2.2k ohm to fix DAP-LINK drag/drop issue. 2. Got 20pcs TSI EVB boards and verified the basic board functions including self-mode, mutual-mode touch keys, 7-seg LED display. Next milestone is to finish TSI EVB software development and finish TSI appnotes writing.
WW29 | Richy | Howard Liu | 2015/7/16 |  | 1 | 1900/4/12 | Kinetis E | MT512P | Execution |  | Q3'16 | System Cases |  | MT512P NPI: 1) Tested the new 3in1 main board on PTV daughter board. Two motors rotated successfully. But PFC always cause system reset after enabling PFC PWM. Tested the main board on DSC with PTV daughter board, got the same result. When running old 3in1 main board with DSC daughter card, the board was damaged during power on. 2) Shipped the two damaged 3in1 board to new board manufacturer, ask them for help repair the boards. 3) Continue to test the new 3in1 board and check the issue of PFC resetting the system this week.
WW30 | william | Guo Jia | 2016/7/11 | 2016/7/22 | 3 | 9 | Kinetis L | L5K | Launching |  |  | Certification - USB | Both HOST and DEVICE certification passed. | Shot all the hardware issues on the boards. And will make a check list and it will be applied in future USB certification.
WW30 | william | Guo Jia | 2016/7/11 | 2016/7/22 | 1.5 | 9.5 | Kinetis L | L5K | Launching |  |  | Documentation - Application Notes |  | 1.For the LPSPI use case, got the feed back from design that after set TXMSK, need to clear it by SW, or LPSPI would keep sending dummy bytes. In application, it would bring some trouble. I am doubting this is a design flaw, need to be confirmed by design. 2. For the TRIGMUX use case, some concept is not expressed well in our RM. Especially the connection with DMA MUX. Need to make an AN for it.
WW30 | william | wang Peng | 2016/3/25 |  | 2.5 | 6.5 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | Finish the coding of CRC adder, and finish the draft data collection of CRC,CMP and PDB, share the test data and related doc to BACEs team.
WW30 | Eric | Chen Xinyu | 2016/3/25 |  | 1 | 13 | Kinetis E | MT512P | Execution |  | Q1'16 | Documentation - Data Sheet |  | 1. Updating the DS with comments from different team. 2. Co-work with BACES for the LPI2C peripheral adder data collection. 3. Discuss with PE/TE/BACES on the current TBD data in both MT256/512P. Ask owner to provide data. Now TE/PE is commit to develop the RAMP ATE program for ADC linearity test, and we will have Min/Max data weeks later. Other TBD is still under testing.
WW30 | Eric | Chen Xinyu, Song Juanjuan | 2016/7/18 | 2016/7/22 | 2.5 | 2.5 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Engineering |  | Tested the LPSPI performance and timing on FRDM-KE15Z board. The LPSPI SCK can up to 24/36Mhz, both master and slave work correctly. Also the timing (SCK rising/falling, data hold time, etc) is matched with the SPEC. Will check with IP owner and system on this result.
WW30 | Eric | Ben Wang, Chen Xinyu, Cao Nan, Chen Yonggang | 2016/6/24 |  | 7.5 | 47.5 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | 1. Learning the KPET backend database XML format. 2. Adding the 11 IDD cases we need for KPET into the BACES idd test code with coremark support. 3. Porting adder program to BACES board with configuration support. Providing each peripheral's configuration in doc. 4.Finish FlexIO I2C KPET use case.Found one SDK2.0 driver issue of FlexIO, the JIRA ticket number is KPSDK-11678.
WW30 | Eric | Ben Wang | 2015/11/23 |  | 2 | 85 | Kinetis E | MT512P | Execution | Documentation - TWR UG ready 7/31 | Q1'16 | Documentation - Others |  | 1.Finished signoff QMS workflow to stage 5.0. 2.Reviewed the updated PB and CN version of DS, provided comments and feedback to marketing. 3.HVP-KE18F daplink firmware released by SW team, verified ok and intergrated into FSW. 4.Writing the UG of TWR-KE18F.
WW30 | Eric | Chen Yonggang | 2016/7/18 | 2016/7/20 | 4 | 6 | Kinetis E | KE15Z | Execution | TSI EVB software/appnotes ready 8/15 | Q4'15 | System Cases-KPET |  | 1. Developing demo software on TSI reference board, 30% done, and verifying TSI features like sensitivity boost, proximity features. Found the shield feature can't work, checking with TSI IP owner. 2. Sent 2pcs FRDM-TOUCH boards to customer Electrolux to support KE15Z evaluation. 3. Improved SCG FIRC data in MT256 Datasheet, only the 48MHz has 1% deviation with trimmed value, the other 52/56/60MHz hasn't been trimmed thus can't guarantee the 1% deviation. 4. Checked and released the final FSW files for FRDM-KE15Z production board testing.
WW30 | Eric | Fang Yizhou | 2016/7/18 | 2016/7/21 | 4 | 4 | i.MX | i.MX6ULL | Execution | Documentation-HUG,QSG,HDG,Power Consumption ready 8/16 | Q4'15 | System Engineering |  | 1. Request new parts in Agile. 2. Based on i.MX 6UL EVK Schematic, revise CPU, DDR and QSPI-Flash circuits of i.MX 6ULL EVK. Also revise schematic number, comments and other related things.
WW30 | Eric | Fang Yizhou | 2016/7/22 | 2016/7/22 | 1 | 1 | i.MX | i.MX6ULL | Execution | Documentation-HUG,QSG,HDG,Power Consumption ready 8/16 | Q4'15 | System Engineering |  | FCC PART15 ClassA test passed of i.MX 6ULL EVK board, including 30M-6G test and power supply test.
WW30 | Richy | Howard Liu | 2015/7/16 |  | 3 | 1900/4/15 | Kinetis E | MT512P | Execution |  | Q3'16 | System Cases |  | MT512P NPI: 1) During check on the issue of PFC resetting system, found two PFC inductors were soldered with incorrect pin-mapping. The different specification of new inductors causes the manufacturer soldering wrong pins, so the inductances were bypassed on the board. Asked board manufacturer shipping another board with fix. The root cause of system reset by enabling PFC was the RESET pin without pull-up on the DSC daughter card. The bad electromagnetic interference caused the false reset signal. 2) Studied the changes list between PTV and Rev 1.0. Some low-level peripheral initialization codes need modification for Rev1.0 chip. Alpha customer support: Japan FAE reported that the initialization trigger of FTM had different behavior between PTV and Rev1.0 in the FTM->PDB->ADC trigger path. After checking the information from Mitsubishi, there's no clue for the issue. Ask FAE to get the details of initialization code used by Mitsubishi.
WW31 | william | Wang Hao | 2016/5/30 |  | 1 | 21.5 | Kinetis K | K4TV | Plan | Execution | Aug 11st | System Cases |  | Plan to develop FlexSPI driver based on existing QuadSPI driver in KSDK, associated header file need to be created by SE team as header file delivered by BACES team is in different style than KSDK.
WW31 | william | Guo Jia | 2016/7/11 |  | 4 | 9 | Kinetis L | L5K | Launching |  |  | Documentation - Application Notes |  | 1. Finished draft of AN - Using LPSPI on KL28 and sent out for review. Updated the workaround for the limitation that continuous mode is not available for multi-IO mode. 2. AN - Using TRIGGER MUX on KL28 is going on.
WW31 | william | Guo Jia | 2016/7/25 |  | 0.5 | 1 | Kinetis L | L5K | Launching |  |  | Documentation - RM |  | Found some issue in the RM, and work with document team to correct it.
WW31 | Eric | Wang Ben | 2015/11/23 |  | 2 | 87 | Kinetis E | MT512P | Execution | Documentation - AN ready 8/20 | Q1'16 | System Engineering |  | 1.HVP-KE18F production factory test is done.Reviewed the test report is ok.Worked out single board FCC test code for HVP-KE18F,team will use the rework board to run FCC at Shanghai Murata FCC lab. 2.Finish writing the TWR-KE18F UG, under review by internal team. 3.Answerd FAE several questions about KE18F headfile.
WW31 | Eric | Ben Wang, Chen Xinyu, Cao Nan, Song Juanjuan | 2016/6/24 |  | 10 | 57.5 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | 1. Tested and recorded the KPET raw data of some modules: FTM,FlexIO Uart\I2C\SPI. 2. Learning the KPET backend database XML format. 3. Finished creating the chip files and some IP equation files. Successfully loading the chip information in the offline tool. 4. Learning the KPET uiLayout. 5. Refined the BASELINE IDD test program, and uploaded into the git repo. 6. Found the communication peripheral adder results are highly impacted by the external loading, like connected slave or not, have lacquered wire connected on the pin or not. Sent email to US Apps to know what exact test method they did on K22/KL27.
WW31 | Eric | Wang Ben | 2016/2/1 |  | 0.5 | 9 | S08 | MC9S08SU16 | Execution | Marketing launch Q4'16 | Q1'16 | Tools Support |  | 1.Per marketing request, did some tests on S08 production with IAR. We may need IAR to support SU16 to replace CW. 2.Answered several questions from DELTA RD about the SD8 GDU AMP usage and configuration.
WW31 | Eric | Fang Yizhou | 2016/7/18 | 2016/7/29 | 5 | 9 | i.MX | i.MX6ULL | Execution | Documentation-HUG,HDG,QSG,Power Consumption 8/16 | Q4'15 | System Engineering |  | 1. Revise the DQS Capacitors,eMMC, NAND, 24M crystal and company logo. 2. Give comments on the 6UL C4 version. Its DDR circuit and two capacitors need to be revised. 3. Compare every part, circuit and details of 6ULL A version and 6UL C4 version. Make sure both schematic work and align. 4. Give tips to layout guys about the difference of 6ULL A version and the 6UL C3 version. 5. Finish the 6ULL schematic A version.
WW31 | Eric | Chen Xinyu | 2016/3/25 |  | 0.5 | 13.5 | Kinetis E | MT512P | Execution |  | Q1'16 | Documentation - Data Sheet |  | 1. Updated the LPI2C performance and timing test results into DS. All I2C modes are supported. 2. Refined the LPI2C and LPSPI peripheral adder test program, and co-work with BACES to get data. Now the all of the peripheral adder under 25degree have been tested, except the RTC and LPTMR, which will be finished in WW32. 3. The ADC linearity testing is on going in PE side.
WW31 | Eric | Chen Yonggang | 2016/7/25 | 2016/7/29 | 6 | 12 | Kinetis E | KE15Z | Execution | TSI EVB software/appnotes ready 8/15 | Q4'15 | System Cases-KPET |  | 1. Developing demo software on TSI reference board, 50% done. Tested the proximity feature and found the best distance is 1cm, much worse than competitor 10cm. 2. Communicated with ADC IP owner and made the ADC calibration checking method clear, so the calibration related code won't block SDK GA release. ADC calibration appnotes AN5314 is available on nxp.com now http://www.nxp.com/doc/AN5314. 3. Updated datasheet CMP chapter, filled the correct typical/max data tested by PE/ATE. 4. Updated Clocking and CMP KE web training slides by adding keynotes. 5. Reviewed the schematic of the touch demo board that customer Electrolux developed based on KE15Z256, gave comments on TSI mutual channel arrangement, and mutual mode can work under 3.3V, so the 3.3V/5V level shift devices can be removed. 6. Answered Jap FAE questions on TSI for Toshiba refrigerator project. Toshiba is using Cypress CY8C4125 as touch sensor MCU for the door open feature, and customer want to know whether KE15Z supports 10cm thick overlay and 3cm distance proximity. 7. Answered Jap FAE question on KE1xF cache control that does cache need to be disabled from RAM. Provided FAE cache example code to show that KE1xF doesn't need to disable cache from RAM, but need to push any modified contents before disable cache, and invalidate before enable.
WW31 | Richy | Howard Liu | 2015/7/16 |  | 3 | 1900/4/18 | Kinetis E | MT512P | Execution |  | Q3'16 | System Cases |  | MT512P NPI: 1) Modified the low-level peripherals initialization codes for Rev1.0 chip and SDK2.0 release. The PWMs and their synchronization worked as correctly as the design expectation. Two PWMs with 180 degree phase shit were implemented also for interleave PFC. 2) During the system timing test, found that the MCU failed start on POR reset. If downloading image through JTAG and run, MCU worked well. But system couldn't work after power up and must be reset more than twice by reset button. The issue check was still in process. 3) Found Channel(n+1) had no output in combine mode if setting COMP=0 that's same as channel(n) according to the RM document. Asked design team check it.
WW32 | william | Wang Hao | 2016/5/30 |  | 2 | 23.5 | Kinetis K | K4TV | Plan | Execution | Aug 11st | System Cases |  | Got CAUv3 library from design team, learning the assembly list file together with CAUv3 block guide.
WW32 | william | Jia Ding | 2016/8/1 |  | 4.5 | 4.5 | Kinetis K | K4TV | Plan | Execution | Aug 11st | System Cases |  | 1. Learned the FlexSPI module and the oct-flash device. 2. Made a simple tool used to generate device header file from the XML file that stores the registers' information.
WW32 | william | Guo Jia | 2016/7/11 |  | 2 | 10 | Kinetis L | L5K | Launching |  |  | Documentation - Application Notes |  | Finished final review for AN5320 - Using LPSPI on KL28, and now it is published.
WW32 | william | Guo Jia | 2016/7/11 |  | 2 | 2 | Kinetis L | L5K | Launching |  |  | System Cases |  | LPSPI maximum baudrate test. For LPSPI master, 48MHz loopback test fail. For LPSPI slave, the maxium baud rate I got is 24MHz. The limitation is brought by the short low level duty in the clock generated by master. Still in investigation.
WW32 | william | YangXi | 2016/8/1 |  | 2 | 2 | Kinetis L | L5K | Launching |  |  | System Cases |  | Porting FlexIO design challenge demo to KL28: 1. Using FlexIO to drive Futaba S3010 servo: porting completed and tested. On issue: because control Futaba S3010 need ~200Hz PWM, the FlexIO clock must be lower than 41.6Khz, so the only possible FlexIO clock source on KL28 is to use SOSC clock and external crystal need to be lower then 41.6Khz. 2. Using the FlexIO to control the Dallas/Maxim 1-wire bus: Porting ongoing, reset pulse and response phase is OK. next will test read/write byte sequence.
WW32 | Eric | Chen Xinyu | 2016/3/25 |  | 0.5 | 14 | Kinetis E | MT512P | Execution |  | Q1'16 | Documentation - Data Sheet |  | 1. Updated the I/O related Voh/ol, leak items according to PE results. 2. Get the ADC RAMP results from PE, need to do analysis.
WW32 | Eric | Chen Xinyu | 2016/4/22 |  | 1 | 7.5 | i.MX | i.MX6RT | Feasibility | Plan | Q1'17 | System Engineering |  | 1. Checking the peripheral reuse table, make a summary of what peripherals require us to learn more. Also describe the challenge would met to support i.MX6RT. 2. Checked the STM32F7 ecosystem, and bought a DISCOVERY board. Plan to study this board for use case development and how to reduce the board cost.
WW32 | Eric | Ben Wang, Chen Yonggang, Chen Xinyu, Cao Nan, Song Juanjuan | 2016/6/24 |  | 9 | 66.5 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | 1. Writing the test plan for BACES and TE/PE for the IDD baseline and peripheral adder. 2. Checking each peripheral adder test program, and test configurations. Found problems like high freq functional clock are not covered in some modules, asked owner to revise them. 3. Finished creating the chip files and some IP equation files , such as : ADC,CMP,CRC,LPI2C,LPIT,LPSPI,LPTMR,LPUART,PDB,RTC . Successfully loading the chip and IP modules information in the offline tool. 4.KPET uiLayout :ADC,CMP,CRC,LPI2C,LPSPI,LPTMR,LPUART,PDB.
WW32 | Eric | Wang Ben | 2015/11/23 |  | 2 | 89 | Kinetis E | MT512P | Execution | Documentation - AN ready 8/20 | Q1'16 | System Engineering |  | 1.FPT team report MT512P phantom part does not work.Checked IP request to the NVM team, no any phantom parts request statement out of MT512P.System has submitted the new request.FPT will proceed FW validation with current version, start from ww31, and complete by ww34. No impact for superset part launch. 2.Got 23pcs production board TWR-KE18F, verified two of them, all the functions work well. 3.MT512P will add two more erratas, one is LPUART, the other is WDOG.Design team is working on errata ticket generation in design PDM. 4.Reviewed the change list document between MA512 and MT512P provided by system. This document will be released to Mitsubishi.
WW32 | Eric | Wang Ben | 6/23'2016 |  | 3 | 3.5 | Kinetis K | KS22F256N | Launching |  |  | Documentation - RM |  | Finish review the TPM, PIT,LPTMR,RTC chapters, provided about ~60comments.
WW32 | Eric | Fang Yizhou | 2016/8/1 |  | 3.5 | 3.5 | i.MX | i.MX6ULL | Execution | Documentation-HDG 8/16 | Q4'2015 | Documentation - Others |  | 1. Finish the i.MX 6ULL Hardware User Guide Draft. Send for review. 2. Finish the i.MX 6ULL Quick Starter Guide Draft. Send for review. 3. Review 1-4 Chapters of the i.MX 6ULL Datasheet. Give 10 comments.
WW32 | Eric | Fang Yizhou | 2016/8/2 | 2016/8/3 | 1.5 | 1.5 | i.MX | i.MX6ULL | Execution | Documentation-HDG 8/16 | Q4'2015 | Certification - Others | Pass FCC Certification | Learn to prepare the i.MX 6ULL EVK FCC test. Process and pass the FCC PART15 ClassA test in Audix.
WW32 | Eric | Chen Yonggang | 2016/8/1 | 2016/8/5 | 5 | 18 | Kinetis E | KE15Z | Execution | TSI feature test done 8/31 | Q4'15 | System Cases-KPET |  | 1. Developing demo software on TSI reference board, 70% done. Tested TSI scan time and found the formula for mutual scan time calculation is wrong in RM, Designer has confirmed this problem and will update block guide. 2. Updated datasheet IO and SCG chapter, updated the Ileakage as 300nA according to IO specs. 4. Prepared for Webinar training of "Connect with Kinetis Training" which is on 8/10 5. BOSCH is looking at a Mutual Capacitance Touch project. Answered customer questions on Mutual touch sensing process and scan time calculation 6. The management had made an alignment, only KE TSI will be promoted in the future, no legacy touch. So they need a detailed test report. Plan to finish all TSI tests by the end of Aug, and hold a align meeting in early Sep.
WW32 | Richy | Howard Liu | 2015/7/16 |  | 4 | 1900/4/22 | Kinetis E | MT512P | Execution |  | Q3'16 | System Cases |  | "MT512P NPI: 1) The issue that MCU failed start on POR reset and needs resets more then twice by reset button was found. It was caused by the wrong startup configuration in the flash loader that boots system from flash and NMI pin high. In 3in1 system, the NMI pin is multiplexed with ADC input that's low after system reset. Now using .board file to overwrite the default flash loader boot configuration by booting from flash always. 2) Tested the system control timing of Rev1.0 silicon that's same as the design expectation. 3) Enabled the PDB sequence error interrupt to process the PDB sequence error that may cause the ADC measurements stop work. 4) In order to improve the FreeMASTER operation, implemented the LPUART FreeMASTER communication. 5) Rotated fan successfully. But the board was damaged while trying to rotate the compressor and fan at the same time. The same code run two motors well on the PTV silicon except the low-level code that's tested well also.
WW33 | william | Wang Hao | 2016/5/30 |  | 3 | 26.5 | Kinetis K | K4TV | Plan | Execution | Aug 11st | System Cases |  | Continue review CAUv3 library assembly, found it's compatible with mmCAU library and has similar API, making reusing KSDK mmCAU demo possible. Got confirmation from design that caching FlexSPI on K4TV is not possible, so checking cache hit ratio with performance monitor also not possible. Need re-evaluate performance monitor use case.
WW33 | william | Wang Peng | 2016/8/10 |  | 2 | 2 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases |  | Get TSI lib and porting code to RD-KE15Z-TSI board, now spring and slider can work well, others is on-going, also will prepare the EMC test(IEC64000-4-6) later.
WW33 | william | Guo Jia | 2016/7/11 | 2016/8/12 | 3 | 5 | Kinetis L | L5K | Launching |  |  | System Cases |  | LPSPI maximum baud rate test. 1. LPSPI master access external SPI flash @ 48MHz succeed. This is implemented by using fast IO pin and enable fast slew rate. 48MHz loop back also succeed. 2. For slave test, the maximum baud rate is 36MHz. As there is a delay introduced by LPSPI slave, 48MHz is not available. One key point here is, to reach 36MHz baud rate, need to set function clock to be 72MHz for LPSPI master. This would bring a 50% duty cycle clock. By this way, for both MODE 0 and MODE 1, 36MHz is OK. If set LPSPI function clock to be 96MHz, then MODE 0 would fail for 36MHz test. 3. The test is strongly layout related. If by two TWR board, the maximum board rate I can get is only 24MHz. If the LPSPI master and LPSPI slave are on the same board and placed quite close, I believe the result would be better.
WW33 | Eric | Wang Ben | 2015/11/23 |  | 3.5 | 92.5 | Kinetis E | MT512P | Execution | Documentation - AN ready 8/30 | Q1'16 | System Engineering | SDK team reported new issue of DAPlink on TWR-KE18F. MCU could not enter stop/vlps mode successfully after POR, but aborted unexpectedly. The issue could be reproduced, and root cause is still under investigation. | 1.All the TWR-KE18F and HVP-KE18F production boards have been in USA warehouse.Some boards have been shipped to third parties. 2.Support Korea FAE on Sumsung inverter project. Answered their questions about FTM and reviewed customer's the pin assignemnt chart and system block diagram. 3.Found one issue of PFC comparator circuit on 3in1 motor control DC. The VREF voltage will drop to unexpected low value.The root cause is vendor used the alternative part of OPAMP chip, they use MC33202 instead of MC33502.The input resistance of MC33202 is small and has big influence on the reference voltage of comparator. All the boards have been shipped back for re-work. 4.SDK team reported new issue of DAPlink on TWR-KE18F. MCU could not enter stop/vlps mode successfully after POR, but aborted unexpectedly. The issue could be reproduced, and root cause is still under investigation. 5.Prepared some software to test the phantom parts. Core team need SE to double confirm Flash, SRAM, FlexNVM and CAN interface work correctly on different phantom parts.
WW33 | Eric | Wang Ben | 2016/8/8 |  | 1.5 | 1.5 | Kinetis E | MT512P | Execution |  | Q1'16 | Documentation - Application Notes |  | Writing the AN of "Kinetis migration guide from KE0x to KE1x". 10% done.
WW33 | Eric | Fang Yizhou | 2016/8/1 |  | 2 | 8.5 | i.MX | i.MX6ULL | Execution |  | Q4'15 | Documentation - Application Notes |  | Writing application notes “Migration from 6UL to 6ULL” with Chen Bingkun. Send for review and revise accordingly.
WW33 | Eric | Fang Yizhou | 2016/8/1 |  | 3 | 8.5 | i.MX | i.MX6ULL | Execution |  | Q4'15 | Documentation - Others |  | 1. Spent 1.5 day learning about Hardware Development Guide of 6UL. Learn about high speed circuits design. 2. Revising and writing HDG for 6ULL, ongoing, 80% done. Revise according to 6ULL schematic. Adding HS200 design, USB ESD protection, ESAI, EPD chapters.
WW33 | Eric | Chen Xinyu | 2016/3/25 |  | 1 | 15 | Kinetis E | MT512P | Execution |  | Q1'16 | Documentation - Data Sheet |  | 1. Discussed with PE/TE on the ADC linearity results. 2. Continue to update the MT256/512P datasheet.
WW33 | Eric | Chen Xinyu | 2016/4/22 |  | 1.5 | 9 | i.MX | i.MX6RT | Feasibility | Plan | Q1'17 | System Engineering |  | 1. Analysis the i.MX6RT challenge to MCU SE. 2. Added more use cases into the Application Plan, like Camera viewfinder, QR decoder, UVC Camera. 3. Drafting the tasks list on both HW and SW side. 4. Checking what trainings are required for us to learn about i.MX HW/SW. 5. Checked the i.MX OBDS code, which can not be reused for 6RT. We should follow the MCU FSW way for hardware validation and testing.
WW33 | Eric | Chen Xinyu, Cao Nan, Song Juanjuan | 2016/6/24 |  | 9 | 75.5 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | 1. Finished and sent the KPET test plan to BACES/PE. 2. Requested TE to support IDD baseline test running in FLASH on the ATE platform. As we already provided the test code, TE would give out the binary requirement on next week. Also they will check how to setup the environment. 3.Update UI and IP files. There are some problems need the KPET Tool team to help.
WW33 | Eric | Chen Yonggang | 2016/8/8 | 2016/8/12 | 5 | 23 | Kinetis E | KE15Z | Execution | TSI feature test done 8/31 | Q4'15 | System Cases-KPET |  | 1. Developing demo software on TSI reference board, 80% done, finished self/mutual mode touch keys demo, developing anlog slider/rotary demo. As discussed internally, Wang Peng will help porting the touch library NT2.0 to the TSI EVB board, and conduct the -4-6 test in Shanghai Audix by the end of Aug. 2. Drafted test plan for TSI feature test covering EMC -4-6 test, basic features and various use cases such as salt water/glove/etc tests got from customers. Working on TSI feature test, finished self mode scan time, external intrinsic capacitance and sensitivity boost feature tests. Submitted TKT310394 to request Designer to update the document problem like calculation formula, register descriptions error found during the TSI feature test. 3. Finished the Webinar training of "Connect with Kinetis Training" on KE15Z and TSI topic, around 66 attendees from Sales/FAE/DFAE team worldwide. Answered questions and got positive feedbacks online, and the most frequently asked question is about the improvement done by the new TSI compared to the previous one on KL/PT. 4. Sent 2pcs FRDM-TOUCH boards and touch library NT2.0 to Jap FAE and supported touch demo software setup. Jap FAE is evaluating KE15Z TSI for customer Toshiba and Panasonic Refrigerator project. FAE has a plan to show TSI demo to Panasonic in middle of September. 5. Reviewing KS22 RM Chinese translation
WW33 | Richy | Howard Liu | 2015/7/16 |  | 4 | 1900/4/26 | Kinetis E | MT512P | Execution |  | Q3'16 | System Cases |  | MT512P NPI: 1) Op amp used in the KE1xF daughter card was 33202, that has small input resistance to cause the reference voltage changed. Shipped all daughter card to factory to reword. 2) Found and fixed the configuration bug of internal comparator 2 that always disables the comparing function, as a result the over-current projection for the compressor really doesn't work at all. 3) Found the selecting reference voltage for 8-bit DAC in the comparator module given in the RM doc is totally wrong that causes the comparing function doesn't work correctly and over-current protection function is disabled in some cases. The issue was conformed by design team and RM doc will be updated later. 4) Rotated fan and compressor successfully with the new board. FPC also works, but if running PFC even with fan and compressor stopped, the system will hang after a while. Had deep investigation and found that the system entered the bus fault ISR when issue happened. If running the code from RAM, the issue disappears. It'll be further investigated.
WW34 | william | Wang Hao | 2016/5/30 |  | 1 | 27.5 | Kinetis K | K4TV | Plan | Execution | Aug 11st | System Cases |  | Found reusable header file content from Ultra and K3S for FlexSPI and CAUv3 module. Still checking performance monitor use case.
WW34 | william | Wang Peng | 2016/8/10 |  | 3.5 | 5.5 | Kinetis E | KE15Z | Execution | TSI feature test done 8/31 | Q4'15 | System Cases |  | Try to unsderatnd TSI lib and porting code to EVB board to get to work well, also try to add some variable for Freemaster to monitor electrodes change, so that we can check the impact during IEC61000-4-6 test. Also the debug of isolated circuit is on-going.
WW34 | william | Jia Ding | 2016/8/1 |  | 1.5 | 6 | Kinetis K | K4TV | Plan | Execution | Aug 11st | System Cases |  | Finished part of the header file the startup files based on KL28/K82's correspond files from SDK2.0 for system case pre-codding.
WW34 | Eric | Wang Ben | 2015/11/23 |  | 2.5 | 95 | Kinetis E | MT512P | Execution | Documentation - AN ready 8/30 | Q1'16 | System Engineering |  | 1.Go on testing and discussing the DAPlink issue on TWR-KE18F with SW team. SDK team has added this as the known issue in release notes. 2.Got the phantom parts and verified the functions of CAN communication, Flash, RAM,FlexNVM and EEPROM read,write and program are all ok. The updated flash firmware works well. 3.Final datasheet is starting signoff for CAB, all the test items are closed except the VHBM limit, it will be reviewed by Michi and decided when he comes back. 4.Final Errata is generated and under review by core team.
WW34 | Eric | Wang Ben | 2016/8/8 |  | 2.5 | 4 | Kinetis E | MT512P | Execution |  | Q1'16 | Documentation - Application Notes |  | Writing the AN of "Kinetis migration guide from KE0x to KE1x". 60% done.
WW34 | Eric | Fang Yizhou | 2016/8/1 |  | 2.5 | 11.5 | i.MX | i.MX6ULL | Execution |  | Q4'15 | Documentation - Others |  | Finished the HDG for i.MX6ULL. Revise IBIS model. Add HS200 chapter.Revise USB OTG2 signals. Revise EPDC and ESAI feature descriptions. Sent for review and revised according comments.
WW34 | Eric | Fang Yizhou | 2016/8/1 |  | 0.5 | 11.5 | i.MX | i.MX6ULL | Execution |  | Q4'15 | Documentation - Application Notes |  | Finished the AN "migrating from 6UL to 6ULL". Revise according to review comments
WW34 | Eric | Fang Yizhou | 2016/8/19 |  | 1 | 1 | i.MX | i.MX6RT | Execution |  | Q1'17 | System Engineering |  | Starting preparing the HW board design. Now preparing the part selection. Setting up a table of all the peripheral chips, including manafacturer, reuse of IP, feature requirment, etc.
WW34 | Eric | Cao Nan, Chen Xinyu, Song Juanjuan | 2016/6/24 |  | 6 | 81.5 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | 1.Finished the LPSPI LPI2C UIlayout and equations.There are still some problems need the Tool team support. 2. Verifiying some cases on BACES board to co-work with BACES team. 3. Finished the IDD baseline program test on FRDM board. Generated the .s19 file and sent to TE team to try on the ATE platform. 4. BACES team has done the following mode KPET data collection: LPUART_Tx, FlexIO_UART_Tx, ADC, LPIT, LPTMR and LPSPI Master. Two problems found: 1) The trace length on BACES board is too long, bring in big impedance and big adder results. Suggest to test communication Tx IP, we cut off the pinout to reduce the impedance. 2) the IDD baseline under 3.3V would be higher than 5V, still confirming with Design. 5. The two UI problems: 1) Power supply voltage selection 2) clock naming change from MCG cannot be supported by current version. Requesting tool team to provide a temporary version for customer to use, then upgrade to new KPET version.
WW34 | Eric | Chen Yonggang | 2016/8/15 | 2016/8/19 | 5 | 28 | Kinetis E | KE15Z | Execution | TSI feature test done 8/31 | Q4'15 | System Cases-KPET |  | 1. Achieved 5cm proximity distance by TSI parameter tuning for the spring key, and 3cm for the proximity loop pad, without the shield enabled. The shield feature still can't work. Checked with Design, there's only one bit in TSI register TSI_MODE[S_SW_SHIELD] to enable shield. Design said the shield feature is not guranteed as it's just for alpha test. 2. Finsihed the mutual mode function test, and found the mutual mode basic and proximity functions don't work very well. Checked with TSI designer about the Mutual mode proximity feature, they didn't design/test proximity for mutual mode. Sent 1pcs MT256 TSI EVB to Design for double check the mutual functions.
WW34 | Eric | Chen Yonggang | 2016/5/18 | 2016/8/19 | 2 | 2 | Kinetis K | KS22F256N | Launching |  |  | Documentation - RM | KS22 RM Chinese version review completed | Finished review of chapters ADC, CMP and PDB in KS22 RM Part3. The KS22 RM translation task completed.
WW34 | Eric | Chen Xinyu | 2016/4/22 |  | 1 | 10 | i.MX | i.MX6RT | Feasibility | Plan | Q1'17 | System Engineering |  | 1. Reviewed the lastest version of PinMux. Compare the typical pin usage on EVB with KUltra and 6UL. 2. Discussed with core team on the memory card design for FPGA board. Asking detail requirement for this card.
WW34 | Richy | Howard Liu | 2015/7/16 |  | 1 | 1900/4/27 | Kinetis E | MT512P | Execution |  | Q3'16 | System Cases | Run fan, compressor and PFC simultaneously. The result shows that the KE1xF performance @168MHz is betten than MC56F84789 @ 100MHz | MT512P NPI: 1) The issue that system hang was fixed by reducing the flash clock. The system clock was set to 168MHz, the flash clock was reduced to 24MHz (Ratio is 7:1). Enabled the cache also. 2) Run the fan, compressor and PFC simultaneously. The next step is to tune the compressor control parameters. And wait for the 3in1 demo platform shipped from Roznov.
WW35 | William | Guo Jia | 2016/8/22 |  | 3.5 | 3.5 | Kinetis L | L5K | Launching |  |  | Training |  | Prepare the training slides for global marketing. The following contents are covered: 1. Smart IPs -FlexIO, RGB display/camera? -EMVSIM -LPSPI/LPI2C/LPUART/I2S, 4 wire SPI -Crystal-less USB -eDMA 2. Large memory In addition, made a test to prove that LPUART on L5K can reach baud rate as high as 24MHz.
WW35 | william | Wang Hao | 2016/5/30 |  | 0.5 | 28 | Kinetis K | K4TV | Plan | Execution | TBD |  |  | Baselined K4TV sample availability and initial silicon data collection target delayed due to Edelweiss mask release and limitation in ULL fab cycle time. Update in schedule pending confirmation in actual wafer start date.
WW35 | william | Wang Peng | 2016/8/10 |  | 4 | 9.5 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases |  | 1. Debug the isolated circuit, after rework the board and add one buffer on SWD_CLK signals, it can work well. 2. Try to tune the TSI parameters to improve its performance. 3. Do IEEC 61000-4-6 test on Audix, and which can pass 3V and 10V level test with normal touch operation.
WW35 | Eric | Wang Ben | 2015/11/23 |  | 1.5 | 96.5 | Kinetis E | MT512P | Execution | Marketing launch - 9/27 | Q1'16 | System Engineering |  | 1.Got a new version DAPlink from SW team, verified it still has stop mode entry issue. Waiting for their feedback. 2.VHBM data has been approved by Chris, all the DS items are closed and in signoff now. .
WW35 | Eric | Wang Ben | 2016/8/8 |  | 3.5 | 7.5 | Kinetis E | MT512P | Execution |  | Q1'16 | Documentation - Application Notes |  | Finish writing the AN of "Kinetis migration guide from KE0x to KE1x", under internal team review.
WW35 | Eric | Fang Yizhou | 2016/8/1 |  | 1 | 12.5 | i.MX | i.MX6ULL | Execution |  | Q4'15 |  |  | Self review schematic, HUG, HDG and QSG again. Give summary of the revising points. Finish my 6ULL tasks.
WW35 | Eric | Fang Yizhou/Shi Changhao | 2016/8/19 |  | 3 | 4 | i.MX | i.MX6RT | Feasibility |  | Q1'17 | System Engineering |  | Prepare the 6RT EVK part selection doc. Learn about 6RT ADD, CSI, SDRAM and other materials.
WW35 | Eric | Cao Nan,Song Juanjuan | 2016/6/24 |  | 6 | 87.5 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | 1.Verifiying some cases on BACES board and FRDM board to co-work with BACES team. 2.BACES team test the LPTMR under 3.3V ,the result shows the adder value is not stable under 3.3V. But under 5V the adder value is stable. 3.Finished flex_IO series equtions xml files and review other files.
WW35 | Eric | Chen Yonggang | 2016/8/22 | 2016/8/26 | 5 | 33 | Kinetis E | KE15Z | Execution | TSI feature test done 8/31 | Q4'15 | System Cases-KPET |  | 1. Worked together with TSI Designer and improved the mutual mode performance by configuring the key configuration: TSI_MULT1[M_TRIM2], which is not available in reference manual. Added notes in TSI AN and also asked IP owner to add notes in RM. 2. Working on TSI feature test and writing test report, 80% done. 3. TSI EVB(RD-KE15Z-TSI board) passed IEC61000-4-6 test in test lab Audix. The test result shows the KE15Z TSI can work normally under both 3V/10V test conditions, this is much better than home appliance customers expect.
WW35 | Eric | Chen Xinyu | 2016/4/22 |  | 2 | 12 | i.MX | i.MX6RT | Feasibility | Plan | Q1'17 | System Engineering |  | 1. Drafting the application plan for benchmarks of realtime and performance. For realtime, we can have RTOS benchmark for interrupt response latency, preemption performance. Also system wakeup time from Deep Sleep mode. Power efficiency is also need to be considered, like coremark per Watt. Performance benchmark is easy for ethernet, graphic use cases. 2. Discussed with Design team on the FPGA memory card requirement.
WW35 | Richy | Howard Liu | 2015/7/16 |  | 2 | 1900/4/29 | Kinetis E | MT512P | Execution |  | Q3'16 | System Cases |  | MT512P NPI: 1) Tuned the control parameters for compressor fast control loop to improve the system performance and studied the compressor control method transferred from Jason when he left NXP. 2) The 3in1 demo isn't shipped out this week. It has high risk to set up the demo fro China FTF.
WW36 | william | Wang Peng | 2016/8/10 |  | 1.5 | 11 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases |  | Make a low power wakeup user case base on NT2.0 library, has implement the basic funtion, need to test power consumption and further optimum.
WW36 | Eric | Wang Ben | 2015/11/23 |  | 2.5 | 99 | Kinetis E | MT512P | Execution | Marketing launch - 9/27 | Q1'16 | System Engineering |  | 1.ATE IDD test got different data with previous data on the new wafer lot, DS needs to update. 2.Firmware validation team reported RAM memory access issue when doing BootROM functional test with 256KB phantom part, the real SRAM size is 32KB (0x1FFFC000 – 0x20003FFF) in chip, but bootROM can only recognize 16KB (0x1FFFE000 – 0x20001FFF).It is caused by the gap between design/document team and ROM development team, ROM team developed bootloader code based on rev0 RM. But From RM rev0 to rev1, RAMSIZE decode in SIM_SDID register was updated based on soc design. An Errata generated for this issue and comments will be added in RM too. No impact to launch. 3.Support marketing guy to do multiple stuffs for marketing launch, including review the FTF slides, Chinese version DS, getting started video script, etc.
WW36 | Eric | Wang Ben | 2016/8/8 |  | 2 | 9.5 | Kinetis E | MT512P | Execution |  | Q1'16 | Documentation - Application Notes |  | 1.Collected the review comments and revised the AN of "Kinetis migration guide from KE0x to KE1x", summit to DocTracker. 2. AN of "How to use FlexMemory as D-Flash and EEPROM in KE1xF" is on-going.
WW36 | Eric | Wang Ben | 2016/2/1 |  | 0.5 | 9.5 | S08 | MC9S08SU16 | Execution | Marketing launch Q4'16 | Q1'16 | System Engineering |  | 1. Internal technical support motor control team member on their software development on SU16. Help to identify the root cause of GDU AMP can NOT sample the bus current, and the PDB lock mechanism with ADC behavior. Found some new doc issues in RM, added comments there.
WW36 | Eric | Fang Yizhou/Shi Changhao | 2016/8/19 |  | 4 | 7 | i.MX | i.MX6RT | Feasibility |  | Q1'17 | System Engineering |  | 1. One day training of high speed circuit and discussion about 6RT in Shanghai. 2. Finish the 6RT EVK pinmux V1.0 of our team. Deliver for review. 3. Prepare the FPGA board. Learn about the proFPGA materials.
WW36 | Eric | Cao Nan，Song Juanjuan | 2016/6/24 |  | 5 | 92.5 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | 1.Verifiying some cases on BACES board and FRDM board to co-work with BACES team. 2.Focused on the baseline value(3.3V) in different mode. 3.Took the test results to the KPET database.Now, LPIT ,LPUART, PDB, RTC had been finished. 4.ATE overlay file for IDD baseline test is created by USA TE, TJN TE would verify it this week.
WW36 | Eric | Chen Xinyu | 2016/4/22 |  | 3 | 15 | i.MX | i.MX6RT | Feasibility | Plan | Q1'17 | System Engineering |  | 1. Discussing with SW/Validation team for the validation board requirements. 2. Reviewed the EVK pinmux plan. 3. Summarize and sent the 3rd party support request to NPI marketing, like emWin, audio codec support for 6RT.
WW36 | Eric | Chen Yonggang | 2016/8/29 | 2016/9/2 | 5 | 38 | Kinetis E | KE15Z | Execution | TSI Test Report on 9/13 | Q4'15 | System Cases-KPET |  | 1. Finished the TSI feature test including the basic functions, sensitivity, proximity, metal plate, liqiud tolerance, and glove operation test. Reviewed the draft test report internally and sent the report to TSI design team for comments. 2. Preparing the TSI demo for the coming FTF show based on NT2.0 touch library, and find the NT2.0 example doesn't work well on the TSI EVB board, especially the rotary and slider is not correct which impacts on customer experience.Communicating with the touch library developer for improvements. 3. FAE reported that KE15Z doesn't support LVD voltage setting for 5V/3.3V power supply respectively. Checked with design that the KE15Z PMC is developed by Auto team which doesn't consider 3.3V power supply case by default.
WW36 | Richy | Howard Liu | 2015/7/16 |  | 3 | 1900/5/2 | Kinetis E | MT512P | Execution |  | Q3'16 | System Cases |  | MT512P NPI: 1) 3in1 demo has been in China customs for customs clearance. Hope to get it this week. 2) Deeply reviewed the code of torque compensation and the extended rotor flux observer in the compressor control on DSC. Got well understanding the algorithms as well as found issues of the wrapped libraries including the application adaptability, excessive memory used and performance optimization needed. Alpha customer support: Japan FAE reported that the first initialization trigger after starting the FTM by setting the FTM source clock was missed if INITTRIGEN =1 and ITRIG = 0. But the RM document says it generated. In 3in1 demo, the system timing starts and is synchronized with FTM initialization trigger, but the initialization trigger in the first PWM period is always skipped by special method. Sent the suggestion and how to do in 3in1 demo to Japan FAE.
WW37 | william | Wang Hao | 2016/5/30 |  | 1 | 29 | Kinetis K | K4TV | Plan | Execution | TBD |  |  | Silicon not tape out yet. BACES board on the way to SH team. Continue CAUv3 test case preparation.
WW37 | william | Wang Peng | 2016/8/10 |  | 1 | 12 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases |  | Find the TSI issue with self-mode in low power mode, which get the different count value between run mode and low power mode, discuss with design and confirm the issue is caused by vdd_3v is changed when MCU is in low power mode, submit one ticket(TKT312972) for tracking.
WW37 | Eric | Wang Ben | 2015/11/23 |  | 2 | 1900/4/10 | Kinetis E | MT512P | Execution | Marketing launch - 9/27 | Q1'16 | System Engineering |  | 1.PE updated the IDD data in DS. Now, Datasheet and Errata complete signoff by core team. Errata has been reviewed by Doc team and posted on KE1xF page of NXP website. Also finished reviewing CN version DS, provided about ~20 comments. 2.System request to do FOC benchmark test under different flash working frequency. The result shows with flash cache disable, higher frequency will get better performance as expected.But if cache is enabled, the frequency will have little impact. Current flash max speed on RM is 24Mhz, they want to extend to 26.67Mhz or higher. But current test pattern in ATE is 25Mhz, change it may bring schedule risk for launch.So it should be done after launch. 3.SW team feedback they have no time to support DAPlink issue,the owner ship will be transferred to Sadek's SE team.
WW37 | Eric | Wang Ben | 2016/8/8 |  | 1 | 10.5 | Kinetis E | MT512P | Execution |  | Q1'16 | Documentation - Application Notes |  | 1. AN of "How to use FlexMemory as D-Flash and EEPROM in KE1xF" is on-going,80% is done.
WW37 | Eric | Wang Ben | 2016/2/1 |  | 2 | 11.5 | S08 | MC9S08SU16 | Execution | Marketing launch Q4'16 | Q1'16 | System Engineering |  | 1. Revised BLDC use case demo code and test on SU16. It works ok. 2. Reviewed and signoff the latest RM.
WW37 | Eric | Yizhou Fang/Changhao Shi | 2016/8/19 |  | 5 | 12 | i.MX | i.MX6RT | Feasibility |  | Q1'17 | System Engineering |  | 1. Memory part selection for 6RT EVK, Validation board and FPGA board. 2. Learn and figure our proFPGA extension board features. Preparing 6RT FPGA board design requirement and part selection. Meeting with IC team and confirmed about requirements.
WW37 | Eric | Cao Nan, Song Juanjuan | 2016/6/24 |  | 7 | 99.5 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | 1.Verifiying some cases on BACES board and FRDM board to co-work with BACES team. 2.Took the test results(5V) to the KPET database.Now,ADC, FlexIO_I2C, FlexIO_SPI, FlexIO_UART, FTM, LPIWC, LPSPI, LPTMR, LPIT , LPUART, PDB, RTC, CRC had been finished.The Baces team will be test CMP and TSI IPs next week. For UIlayout, use the raw data instead of fitting data. 3.CMP module consume more power when in High speed mode and DAC OFF. 4.The current consume was not continuous .Tested current consume from 3.0V to 5.0V and the step value is 0.1V with different Clcok Source , Power mode.There is a big current gap(about 0.5ma) between 3.3V and 3.4 in the wait mode(FIRC,LPFLL,SOSC).When the chip in the stop mode, the current gap gone.
WW37 | Eric | Chen Xinyu | 2016/4/22 |  | 4 | 19 | i.MX | i.MX6RT | Feasibility | Plan | Q1'17 | System Engineering |  | 1. Clarified the SAI multi-channel AN requirements with marketing and system. It should be a multi Tx/Rx data line support with same BCLK and FS. So the audio codec used on validation board should support two I2S bus. Changed the SAI use case accordingly. 2. Summerize the topics need to be discussed with different functional team on planning summit. 3. Investigating the Real Time benchmark method. May need to develop a test suite for 1) latency from timer interrupt to ISR execution 2) latency from timer interrupt to high priority task running wakeup by this interrupt 3) external GPIO interrupt response latency during the high system loading
WW37 | Eric | Chen Yonggang | 2016/9/5 | 2016/9/9 | 5 | 43 | Kinetis E | KE15Z | Execution | TSI Test Report on 9/13 | Q4'15 | System Cases-KPET |  | 1. Finalized the TSI test report according to the comments collected from review meeting. Held a training on the new TSI features and performance to share the knowlege got from the TSI test. 2. Finished the signage of touch demo for FTF China. 3. GuangZhou Chigo currently used our PA60 in A/C and have been MP. Customer will kick off a new project, and customer is interesting in KE15, especially in the enhanced TSI module and 5 UARTs. Communicated with FAE about the customer information and introduce KE15Z features, sent 1pcs FRDM-KE15Z board to support customer evaluate KE15Z. 4. Sent 2 FRDM-KE15 boards to customer Electrolux in Italy to support them evaluate KE15Z.
WW37 | Richy | Howard Liu | 2015/7/16 |  | 4 | 1900/5/2 | Kinetis E | MT512P | Execution |  | Q3'16 | System Cases |  | MT512P NPI: 1) Received the 3in1 demo. Due to the small power compressor used for refrigerator, the 3in1 board needs rework to reduce the current scale of measurement for compressor. Reworked the board for 3in1 demo by changing the current shunt resistors and resistances of opamp. 2) Fan rotated successfully. Tried to have compressor working but failed. Continue to rotate the compressor this week. Alpha customer support: Japan FAE reported that the first initialization trigger after starting the FTM by setting the FTM source clock was missed if INITTRIGEN =1 and ITRIG = 0. But the RM document says it generated. The issue was confirmed by design team while FTM works in the CPWM mode. There's no such issue in the combine mode. The design team is still simulating the other modes for this issue.
WW38 | william | Wang Hao | 2016/5/30 |  | 2 | 30 | Kinetis K | K4TV | Plan | Execution |  | System Cases |  | Updated Fabout time and engineering sample time changed to 12/2/2016 and 12/26/2016 respectively. Going through CAUv3 test cases, plan to add them when template project for K4TV is ready this week.
WW38 | william | Jia Ding | 2016/8/1 |  | 3 | 9 | Kinetis K | K4TV | Plan | Execution |  | System Cases |  | Completed the header file the startup files based on KL28/K82's correspond files from SDK2.0 for system case pre-codding.
WW38 | william | Wang Peng | 2016/8/10 |  | 2 | 12 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases |  | Finish the measurment of low power IDD with TSI wakwup, it is about 480uS for self mode, and 520uA for mutual mode, and deliver the low power wakeup demo to software team, expect to add this demo to NT2.0 library.
WW38 | Eric | Chen Xinyu | 2016/4/22 |  | 2 | 21 | i.MX | i.MX6RT | Feasibility | Plan | Q1'17 | System Engineering |  | 1. Enabled the libjpeg on MAPS-KS22 to read a jpeg file from SD card and display on LCD. This is to check the feasibility of enabling libjpeg on i.MX6RT for graphic use cases. 2. Reviewing the ADD v0.3. 3. Checking for benchmark tool for RTOS by searching uCOS, FreeRTOS, ThreadX and Nuttx codes.
WW38 | Eric | Chen Xinyu | 2016/9/14 | 2016/9/14 | 0.5 | 0.5 | Kinetis K | KS22F256N | Launching | Launching |  | System Cases |  | Added the libjpeg, FlexIO emulating dual I2S Tx and USB audio 2.0 Speaker+Mic use cases into the use cases pool. Code pushed on the pool git repo.
WW38 | Eric | Wang Ben/Song juanjuan | 2016/11/23 |  | 2 | 1900/4/12 | Kinetis E | MT512P | Execution | Launching | Q1'16 | System Engineering |  | 1.Continue to test and verify the DAPlink issue with Sadek's team. 2.Support Japan's FAE answer the D-Flash operation questions. 3.Tested the ADC function under VDD=VDDA=5V and VREFH=2.5V, the spec item VREFH guaranteed by Design in DS is verified ok. 4.Customer Mitsubishi faced one issue about the FTM initial trigger.There is difference between RM description and actual chip behavior when INITTRIGEN =1 and ITRIG = 0. IP owner has done simulation to confirm that,and he is simulating more other FTM modes (Input Capture, Output Compare, EPWM, COMBINE PWM) to check the RTL behavior now.
WW38 | Eric | Chen Yonggang | 2016/9/12 | 2016/9/16 | 5 | 48 | Kinetis E | KE15Z | Execution | Touch demo for FTF on 9/28 | Q4'15 | System Cases-KPET |  | 1. Completed final version of TSI feature test report and had a review meeting with top management from different teams. 2. Finished the signage of touch demo for FTF China. Preparing the touch demo for FTF based on the RD-KE15Z-TSI and FRDM-TOUCH boards. 3. Shipped 2 FRDM-KE15 boards to Electrolux in Italy to support their evaluation on KE15Z. 4. Got encouraging feedback from the Electrolux team in Stockholm on KE15 in Dishwasher. Customer Electrolux has done some initial testing and results on S/N ratio, sensitivity and current injection are very promising and much better than was achieved on S08 based designs. More tests planned for October.
WW38 | Eric | Cao Nan, Song Juanjuan | 2016/6/24 |  | 5 | 1900/4/13 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | 1.The test result (except TSI) form BACES team had been wrote to the KPET database(5V). 2. Dynamic association the result with different clock source and power mode. Maybe we have to test some new case with clock source(SOSC 8M SIRC 8M) and power mode(VLP mode). 3.Tested MT512 in wait mode , also had the current gap(3.5V – 3.6V , about 0.5ma).Tested MT256 in different mode(Disable LPO Disable, Flash Disable and FLASHDOZE Disable) , there is still a the current gap. 4.Update UIlayout.
WW38 | Eric | Wang Ben | 2016/8/8 | 2016/9/14 | 1.5 | 12 | Kinetis E | MT512P | Execution | Launching | Q1'16 | Documentation - Application Notes |  | 1. AN of "How to use FlexMemory as D-Flash and EEPROM in KE1xF" is done. Summitted to Doc tracker.
WW38 | Eric | Terry Lv, Shi Changhao | 2016/9/13 | 2016/9/14 | 2 |  | Kinetis W | KW41 | Launching |  |  | Tools Support |  | Lierda want us to provide a tool to adjust the KW41 output power and test connection radius of at least 50 meters. Porting per application to latest 1.0.2 BLE release. There’are some OSA and Framework changes on 1.0.2 BLE release. So need to debugging the tool. The tool will be sent to Lierda in one or two days.
WW38 | Eric | Yizhou Fang/Changhao Shi | 2016/8/19 |  | 3 | 15 | i.MX | i.MX6RT | Feasibility |  | Q1'17 | System Engineering |  | 1. Finish 6RT FPGA board memory part selection. Confirmed with IC and System team. Give tips about SEMC pinmux. 2. 6RT EVK pinmux 0.2 updated. Reserved GPIO for boot mode pins. 3. Finished preliminary schedule for i.MX6RT FPGA/VATION/EVK boards and continue for part selection
WW38 | Richy | Howard Liu,Sutter Zhou | 2015/7/16 |  | 2 | 1900/5/2 | Kinetis E | MT512P | Execution |  | Q3'16 | System Cases |  | KE1xF 3in1 Demo on FTF China: 1) The startup of compressor still failed after trying the different parameters of startup. Even the compressor rotated successfully sometimes, its startup actually didn't work at all. After accidental rotating, the position estimated by the extended BEMF DQ observer wasn't good even at the speed of 2000RPM. So the traditional startup cannot work for refrigerator compressor. 2) Ported the new startup algorithm of compressor used in refrigerator project with new position observer. The compressor can start up successfully now. Tuned the parameters to have demo run well. 3) PFC worked well. The total power of demo is small, about 350W. The DCbus current is small even fan and compressor run simultaneously. The current scale on 3in1 interleave FPC is 10A for each path, so the pfc current is showed as sinusoidal wave with very small amplitude. 4) Shipped the demo to Shenzhen for FTF China.
WW39 | william | Wang Peng | 2016/8/10 |  | 2 | 14 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases |  | BACEs find the TSI_adder code has big adder current when trigger TSI, and also confirm it can up to 8mA in my side, however, TSI low power demo don't have bigger currents(just more 500uA), maybe the different configuration result it, and try to find the root cause.
WW39 | william | Jia Ding | 2016/8/1 |  | 4.5 | 13 | Kinetis K | K4TV | Plan | Execution |  | System Cases |  | Studied the FlexSPI module and the oct-flash device. Finished part of the FlexSPI driver based on the KSDK2.0 framework.
WW39 | william | Wang Hao | 2016/5/30 |  | 2 | 14 | Kinetis K | K4TV | Plan | Execution |  | System Cases |  | Start precoding for CAUv3 module based on KSDK2.0 based code framework.
WW39 | Eric | Wang Ben | 2016/11/23 |  | 3.5 | 1900/4/15 | Kinetis E | MT512P | Execution | Launching | Q1'16 | System Engineering |  | 1.Support launch marketing to do production launch stuff before FTF.All the KE1xF documents have been posted on NXP web page, including DS, RM, Errata, TWR UG and Application Notes. 2.System has officially raised CR to to change the test freq from current 25MHz to 26.67MHz. PE/TE and NVM team is evaluating the effort needed. 3.DAPlink issue on TWR-KE18F is still not resloved by Michal.He will deliver one "workaround" version of masking UID read.
WW39 | Eric | Wang Ben | 2016/6/24 |  | 1 | 16.5 | Kinetis E | KE15Z | Execution | Launching | Q4'15 | System Cases-KPET |  | 1.Revised ftm, flexio_uart,flexio_i2c, flexio_spi adder code to support 8Mhz/4Mhz/2Mhz/1Mhz functional clock source.
WW39 | Eric | Cao Nan | 2016/6/24 |  | 3 | 1900/4/16 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | 1.Dynamic association the result with different clock source and power mode. Maybe we have to test some new case with clock source(SOSC 8M SIRC 8M) and power mode(VLP mode). 2.Update UIlayout. 3.Revised LPI2C ,LPSPI, LPTMR , LPIT ,LPUART adder code to support 8Mhz/4Mhz/2Mhz/1Mhz functional clock source.
WW39 | Eric | Chen Yonggang | 2016/9/18 | 2016/9/23 | 6 | 54 | Kinetis E | KE15Z | Execution | Touch demo for FTF on 9/28 | Q4'15 | System Cases-KPET |  | 1. Finished touch demo tuning for FTF based on NT2.0 library. Fixed the bug of slider detector of the library and shared the solution to library developer to improve the NT2.0 touch library. 2. Updated KE15Z datasheet by adding STOP/VLPS current consumption with BIAS enabled/disabled options, and removing all ECC info per Marketing request. Now the DS is ready for KE15Z launch. 3. Supported BACES team finish the TSI KPET test. Under 5V power supply and triggered by 5ms LPTMR, the current consumption is around 180uA for TSI self mode and 2300uA for TSI mutual mode.
WW40 | william | Wang Peng | 2016/8/10 |  | 1.5 | 15.5 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases |  | Find the root cause of big current on TSI adder, which configure one TSI channel as GPIO and output high, and when trigger TSI, also see the similar waveform on this pad and get the big current(about 8mA), feedback to IP design to confirm it.
WW40 | william | wang Peng | 2016/3/25 |  | 1 | 7.5 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | Finish the adder code modification of ADC,CMP,PDB and CRC, support clock select so that get the adder with different function clock.
WW40 | william | Wang Hao | 2016/5/30 |  | 2 | 34 | Kinetis K | K4TV | Execution |  | 2016/8/12 | System Cases |  | Prepare slides for comparison between MMCAU and CAUv3 module. Spent time to study performance monitor inside Cortex A7 core for checking any similarity with K4TV PM module.
WW40 | william | Jia Ding | 2016/8/1 |  | 4 | 17 | Kinetis K | K4TV | Execution |  |  | System Cases |  | Continued the pre-coding of the FlexSPI drivers and demos. About 40% has been finished.
WW40 | Eric | Cao Nan | 2016/6/24 |  | 5 | 1900/4/21 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | 1.Finished the dynamic association the result with different clock source and power mode .We can write the new func clocks data to the database once the BACES team finished test. 2.TSI test result form BACES team had been wrote to the KPET database(5V). 3.Starting test the LPIT ,LPTMR adder value in 8M,4M,2M,1M. 4.Verifiying some cases on BACES board and FRDM board to co-work with BACES team and ATE test.
WW40 | Eric | Yizhou Fang/Changhao Shi | 2016/8/19 |  | 4 | 24 | i.MX | i.MX6RT | Feasibility |  | Q1'17 | System Engineering |  | 1. Planning summit. Deliver application plan and confirm questions to other teams. 2. i.MX6 RT agile part set up and review. 3. Start i.MX 6RT FPGA board design.
WW40 | Eric | Chen Yonggang | 2016/9/26 | 2016/9/30 | 6 | 60 | Kinetis E | KE15Z | Execution | TSI AN on 10/28 | Q4'15 | System Cases-KPET |  | 1. Attended Shenzhen FTF for touch demo. Many customer engineers came and watched the touch demo, including Haier, Glanz, etc. The customer requirements of touch MCU are low price and small package/flash size. 2. Debugged the big current consumption problem for the TSI mutual mode together with Design team, and found out the root cause is TSI IP pull down all Tx channels in mutual mode, which caused big current consumption when the related pin is configured as GPIO output high. Created the ticket TKT316157 in designPDM and TSI designer will fix this problem at the next IP version, but for now MT256 won't fix this problem immediately.
WW40 | Richy | Richy Ye, Li Shunan | 2016/4/27 |  | 1 | 6 | i.MX | i.MX6RT | Planning |  | Q1'17 | System Cases |  | Aligned with NPI marketer about motor control reference for 6RT, 3D printer with robot arm is proposed with 4 motors control on single chip. Completed the CCB slides to add the additional 6kUS$ for the proposed reference.
WW41 | Richy | 2015/7/16 |  | 2 | 1900/5/2 | Kinetis E | MT512P | Execution |  | Q3'16 | System Cases |  | MT512P NPI: Continued to write the application note for system timing design with KE1xF.
Note on K1: Author: format as below: <SE's task>-<Complete Date in MM/DD> Example: FRDM-Touch sch – 12/18

## Reference Design
Week | Team | Apps Engineer | Open Date | Close Date | Effort (man- days) | Total Effort | Family | Segment | Project | Reference Phase | Milestone Date | Progress record

## Others
Week | Team | Apps Engineer | Open Date | Close Date | Effort (man- days) | Total Effort | Item | Segment | Family | Part | Module | Tools | Request brief | Overal Progress | Input Source