## Customer Support
Week | Team | Apps Engineer | Effort (man- days) | Total Effort | Segment | Customer | Family | Part | Customer Phase | MP Date | Product | LTR ($M) | GIBC | Module | Tools | Request brief | Progress record | Root cause | Solution | Support Type | Input Source | Community Link (Mandatory)
WW18 | Sherry
WW18 | Sherry
WW18 | Sherry
WW18 | Sherry
WW18 | Sherry
WW18 | William
WW18 | william | wang peng | 1 | 4.5 | Industry | Mitsubishi | Kinetis L | MKL26Z256VLL4 | DI |  | circuit breaker | $0.28M | 1-1TFD5UD | GPIO |  | Customer feedback MCU fail to work when there are more noise on reset pin(removing decoupling capacitor on reset pin) | Design confirm the root cause, which is from reset assert during changing clock divider,then result in state machine deadlock, for external reset pin, there are two workaround for it, add RC circuit or enable reset pin digital filter, and for system reset, workaround is to disable the possible reset occur before change clock divider(say COP,LOC,LOL and LVD). also test L5K and KL8x, there are not similar issue. | New Requirement | Customization | General | FAE | https://community.freescale.com/message/628367?et=notification.mention
WW18 | william | wang peng | 3 | 3 | Industry | Senao | Kinetis W | KW40Z | DI |  | IoT gateway | 1.2 | 1-218W7NO | bootROM |  | Customer ask to provide to support boot loader on KW40Z | Porting boot loader code to support UART and I2C interface on KW40Z, complete debug and deliver to customer | New Requirement | Customization | General | AE
WW18 | william | wang peng | 1 | 1 | Industry | Johnson Health Tech | Kinetis E | KE04Z64 | DI |  | Treadmill |  |  | FLASH |  | customer fail to program flash with blank chip by J-Flash | Customer can program code to flash by IAR with J-link, but fail to setup connection by J-Flash when chip is blank chip, and after program code to flash by IAR, it can program well with J-Flash, debug and try more tests, it show the error message that can't measure CPU frequency when use J-Flash to try connection, maybe blank chip cycle to generate reset and result connection fail, mail to segger to check possible cause and further debug is on-going. | New Requirement | Customization | General | FAE
WW18 | William | Wang Hao | 2 | 4 | Consumer/Communication | Microsoft | Kinetis K | SC667334DC12 (K20-1M) | DI |  | Surface keyboard |  |  | USB | IAR | Find root cause for USB suspend/resume recover issue. | Confirmed from Melissa that Microsoft US team only has issue with host resume, they do not have problem with remote wakeup feature; communicated with Microsoft China we have remote wakeup demo under KSDK and confirmed it works well, request FAE help demo this feature to customer; got progress on where exactly failed for the suspend/resume cycle, found when issue occurred, host frame number register does not increment and there are error reigster bits set, design comment this could be related to host side problem. But later Melissa confirmed Microsoft does not use Kinetis part for host side and the issue should be on device side instead. Need more investigation if we have duplicated Microsoft issue. |  |  | Key | FAE (Xiong Yu)
WW18 | William | Wang Hao | 1 | 1 | Security | Landi | Kinetis K | K81 | DI | 2016-12-20 | MPOS-LD6 | 1.112 | 1-20SLJID | FLASH |  | Customer needed host side tool and associated source code for KBOOT. | Landi requested information on host side tool and associated source code for KBOOT, they plan to port the host side code to i.MX258 and use USB interface for programming K81. Suggest customer to check the blhost source code for Linux as reference. |  |  | Key | FAE (Fred Fu) | https://community.freescale.com/thread/390472
WW18 | William | Wang Hao | 0.5 | 0.5 | Security | Landi | Kinetis K | K81 | DI | 2016-12-20 | MPOS-LD6 | 1.112 | 1-20SLJID | ICS |  | Customer reported inaccurate IRC48M clock on PK sample and request our investigation. | Customer reported inaccurate IRC48M clock for PK sample which lead to inaccurate PLL clock and request us to check if there is risk duing mass production the clock will be inaccurate as well, this could lead to failed communication for UART. Currently this issue only discovered with PK samples, MK sample Landi received is fine. Checking with PE team if MK81 PK sample is programmed correctly the IFR values for IRC48M clock. |  |  | Key | FAE (Fred Fu) | https://community.freescale.com/thread/390472
WW18 | William | Guo Jia | 4 | 10 | Consumer/Communication | Microsoft | Kinetis K | SC667334DC12 (K20-1M) | DI |  | Surface keyboard |  |  | USB | IAR | Find root cause for USB suspend/resume recover issue. | 1. Work with design team to make the test based on K24 and L5K/K64. 2. Make a flow chart and a timing graph to illustrate how the test code is running. Finally we can draw the conclusion that the issue we reproduced based on Melissa's code is at the HOST side. The frame number is hold to be static when it goes to error, which shows the HOST is not working correctly. |  |  | Key | FAE (Xiong Yu)
WW18 | William | YangXi | 2 | 2 | Consumer/Communication | Honeywell HBS | Kinetis K | MK64FN1M | DI |  | HVAC control board | $0.495M |  | DMA | KSDK | Provide example code of receiving UART data via DMA with idle line interrupt | Customer need example code on UART eDMA transfer with IDLE line interrupt to help customer evaluate K64/K66 UART throughput for inter communication between two K64/K66 based control boards. use eDMA to receive data from TX board, use IDLE line interrupt to determine if each frame transfer completed, the frame has various data length. Complete evaluation code and send to FAE. One issue found: UART Rx FIFO must be disabled when using DMA to receive UART data. Otherwise, the received data will always read as a 0x00 when first enter idle line interrupt.
WW18 | William | Jia Ding | 3 | 7.5 | Industry | Nanjing Paneng | Kinetis K | K66 | Early Evaluation |  | FTU Relay | 0.163 | 1-1UXFMD7 | ADC |  | FAE reported that customer tested K66 with ADC and SDRAM functionality, and they found while SDRAM module is operated, the ADC result varies largely for a constant voltage input. | Measured more data under different configurations on FireBird-K602M. Share the data within team for review and discussion. |  |  | General | FAE(You Dawei) | https://community.freescale.com/message/633929
WW18 | William | Zhong Juying | 1 | 1 | Security | Zhinengguo | Kinetis L | MKL81 | DI |  | MPOS |  |  |  |  | Customer reported some questions on tamper detection and RSA algorithm | 1. anlayzed their debug error when key length was 1984 bit, it caused by input message length not key length. suggest customer to solve the issue on input message 2. verified a no padding support for RSA algorithm in Security system. solved the coding problem when debugging. | Ctm S/W defect | Customization | Key | FAE-May LI
WW18 | Eric | Shi Changhao, Terry Lv | 1 | 8 | Smart Grid | Waison | Kinetis M | KM34Z128 | Pilot |  | SINGLE-PHASE METER FOR THE CAMPUS | 200-300Ku/Y | GIBC:1-1N9N677 | AFE | IAR | Customer reported the issue that that the VLPS standby current is too high | 1) It is concluded that in the VLPS mode, if the factory limit the max current to 10uA, it will increase 4% yield loss, we have forwarded this information to the supporting team. |  |  | General | Sales(Joe Zhou)
WW18 | Eric
WW18 | Eric
WW18 | Eric
WW18 | Eric
WW18 | Eric
WW18 | Eric
WW18 | Richy | Ethan Cheng | 1 | 43.5 | WirelessConnectivity/IoT | Sysgration | Kinetis W | KW01 | DI |  | LF programming for Tire Pressure Monitor Sensors (TPMS) using KW01 + LF transmitter | $0.582 M | 1-1VL3TGP |  |  | Using KW01 for OTA firmware update of Tire Pressure Monitor Sensors | Introduced KW01 TPMS Over-the-Air software update demo to distributors and delivered this demo to FAE. Looking forward to customer’s feedback and more design-win socket at KW01. | New Requirement | Customization | BD Activity | FAE (Chiang Jason - R44828)
WW18 | Richy | Richy Ye, Wang Lingling | 4.5 | 24.5 | Digital Power | Artesyn Philippines | DSC | MC56F82748 | Early Evaluation |  | Digital power development platform |  |  |  |  | Tool box for automatic code generation from MATLAB | Modified the example tmf and added some relative m files to generate the executable file, a simple project of lighting LED through GPIO was tested, it works OK. More details about interrupt and algorithm handling will be considered in next step. |  |  |  | FAE (Audrey Eng - R43125)
WW18 | Richy | Jiang Dengyu, GaoXiang | 2 | 4.5 | Wireless Charger | FIT | WCT | MWCT1012CFM | DI |  | 15W 1COIL TX |  |  |  | CW10.6 | FIT reported charging issue when enable the QC function to switch the RX output to 9V or 12V output from 5V with load. | Updated the RX bus voltage settings according to different load and output voltage, and placed 10R resistors in series with RX communication caps to decrease the RX bus voltage spike. With the optimization the MP system is better compatible with quick charging system. Shipped the boards to FIT for customer’s test. |  | Customization | General | FAE (Beta Chen - B44998)
WW18 | Richy | Jiang Dengyu, Maohuan | 1 | 1 | Wireless Charger | Hitachi Maxell | WCT | MWCT1012CFM | Early Evaluation |  | 15W 1COIL TX |  |  |  | CW10.6 | Hitachi Maxell reported one MP TX failed after running several minutes when using two TX & HV RX boards supplied one load in parallel. | Researched and checked the test conditions with customer. And tested one MP TX with one HV RX board over half hours, the system is stable, then it's supposed the issue is caused by the paralleled system, we’ll do more tests to reproduce and research the issue. |  | Customization | General | FAE(Noriaki Masuda - B01926)
WW18 | Richy | Liu Zhen | 2 | 41 | Motor Control | Positec | Kinetis E | MKE02Z32 | DI |  | Electric tools | $0.36 M | 1-1SZM1NM |  | IAR | BLDC solution of KE02 | 1, Completed packing the critical algorithms into library based on HVP platform for future customer support, sent the software project to FAE for customer promotion. 2, Found the reason that zero-crossing point can’t be detected sometimes when state machine just enter into close loop, the reason is that the current recirculation period calculated in start up state machine is so long sometimes, and it can cover commutation period when state machine just enter into close loop. it's maybe caused by calculation overflow, details is under debugging. |  | Customization | General | FAE(Cherrish Liao - R65774)
WW18 | Richy | Liu Zhen | 1 | 2 | Motor Control | X_CAM | S08 | MC9S08SU16 | DI |  | DroneESC |  |  |  | CW10.6 | BLDC solution of S08 | Sent one chip which is programed using 5V as ADC Vref to customer to replace original chip. Customer report that 5V VDD can be obtained. Customer has shipped the modified hardware board to us. |  | Customization | General | FAE(Cherrish Liao - R65774)
WW18 | Richy | Zhao Ping | 0.5 | 29 | Wireless Charger | Delphi China | WCT | WCT1001A | MP | 2016.3 | 5W Automotive Power Transmitter |  | 1-UXG1IX |  |  | Tessy integration issue | Tessy integration issue that read wrong data sometimes is not fixed. Their engineer came to our office for support. I checked their project and ran it without Tessy environment. I wrote 8 bytes data to the specific location, but the data were modified before read it. So there must be some wrong in their code, suggest them to check code. | New Requirement | Customization | General | FAE (Yu Ningning - B45276)
WW18 | Richy | Zhao Ping, Richy Ye | 0.5 | 29.5 | Wireless Charger | Delphi US | WCT | WCT100xA | Early Evaluation |  | Automotive low power dual-mode wireless transmitter |  |  |  |  | API implementation | Supported customer how to change the UART port in code, it works now on customer side. Customer will ship 2-3 pcs of new boards to us for system test and future customer support. Also request customer if she will fund us to have pre-compliance test in WPC1603 meeting so that we can prepare for Visa application. | New Requirement | Customization | Professional Service | PM (Worthy Anna - B18818)
WW18 | Richy | Zhao Ping, Richy Ye | 0.5 | 12.5 | Wireless Charger | Omron Japan | WCT | WCT1001A | MP |  | WCT-5WTXAUTO | 13M |  |  |  | Coil peak voltage protection for PMA | 1, SoW wasn't still fixed and signed. Provided the professional support effort summary to PM for customer communication about support hours purchasing in SoW. 2, Answered customer's questions about coil voltage protection on community. | New Requirement | Customization | Key | FAE (Noriaki Masuda-B01926)
WW18 | Richy | Richy Ye, Jiang Dengyu, Mao Huan | 1 | 45 | Wireless Charger | LGIT | WCT | MWCT1012CFM | DW |  | 15W 1COIL TX | $1.70 | 1-FFWPV2 |  | CW10.6 | Customer want a solution of WPC+PMA based on WCT1111 | LGIT sent their binaray files with quick wireless charging for debugging; downloaded it to customer's board and it can work well, the quick wireless charging can be enabled when charging Samsung S6 Edge+; but the debug console couldn't work, have requested more information about the SCI settings. | New Requirement | Customization | Key | FAE( Kate Lee - B45752)
WW18 | Richy | Wang Dechang, Jiang Dengyu, Wang Li | 2 | 91 | Wireless Charger | LG CTO | WCT | WCT1003A | Early Evaluation |  | 15W_TXAUTO |  |  |  | CW10.6 | Board bringup and full function debug. | 1. Updated the F/W with seperated power protection function as customer required. Now the power protections in lib can be controlled indenpendently; 2. Checked the SPI issue contineously. As cusomter described, the Tx opened the coil2 falsely when phone is on coil0, which lead to the SPI to interrupt. I checked the issue with our S6 phone and Tx, but it can't be reproduced. I consider that the DDM is impacted by SPI ISR, which makes the DDM delay to demodulate the SS packet, and open the wrong coil. The debug work for this issue is on going. | New Requirement | Customization | General | FAE (Kate Lee - B45752)
WW18 | Richy | Wang Dechang, Jiang Dengyu, Wang Li | 2.5 | 15.5 | Wireless Charger | PLDS | WCT | WCT1001A | Early Evaluation |  | 15W_TXAUTO |  |  |  | CW10.6 | Support customer debug. | 1.Debugged the code on customer's platform, now the timer and PWM basically works, and seems right. Since there are two PWM modulations are used in their topolgy, so the PWM control code need to be modified. Now the debug work is ongoing. | New Requirement | Customization | General | FAE (Beta Chen - B44998)
WW18 | Richy | Kevin Cheng | 1 | 1.5 | Digital Power | GE Energy | DSC | MC56F827xx | Early Evaluation |  | AC/DC module |  |  |  |  | PWM implementation | Customer gets the PWM waveform for 1st boost channel and asked implementaton suggestion of 2nd boost channel control. Explained to customer the phase delay between boost channel need calculates by software and guidance CAS engineer provide the delay through QTimer. Studing interleaved CrM PFC paper for delay count calculation. |  | Customization | General | FAE (Zhuang Chao - B50031)
WW18 | Richy | Zhou Xuwei | 1 | 56.5 | Motor Control | TCL | DSC | MC56F82723 | DI |  | Refrigerator |  |  |  | CW10.6 | Customer received a new batch of boards for BMG089NHMV tests on refrigerators. But there're 3 sets out of 20 that don't work properly. | There're over-current and open-phase errors indicated by LED on those malfunctioned boards, while the other 17 boards work well. Helped customer to debug these boards, it turned out the problem lies on the daughter cards. I suspect there are cold joints or bad components on the boards. Customer will carry on the debugging, but I haven't got any feedback yet. |  | Customization | Key | FAE (Larry Yang - B47306)
WW18 | Richy | Zhou Xuwei | 1.5 | 39 | Motor Control | Delta HA | DSC | MC56F82746 | DI |  | BPM Washing machine |  |  |  | CW10.6 |  | 1). Helped Stanley to demonstrate the performance of my preliminary non-HFI code on Delta's washing machine. They can't add too much water into the drum due to some restraints in their lab. The test was conducted under some loading. The performance of 300RPM is much better than 150RPM. The drum runs rather bumpy during the startup at 150RPM. The startup solution is very similar to the one used in refrigerator, so there's an speed overshoot during the startup, which Delta doesn't quite approve. 2). Gave an online training to Delta and ADS of Avnet about the architecture of the firmware, the structure of the observers and the startup implementation. Delta is very interested in our flux observer used in the startup. They won't start to make a new board until the code is finalized to some extent on our HVP. They'll continue to test my code on their washing machine and they'll start to implement their own algorithm on their platform. |  | Customization | Key | FAE (Stanley Huang - B42861)
WW18 | Richy | Zhou Xuwei | 2 | 2 | Motor Control | TopXGun | Kinetis V | KV3x | Early Evaluation |  | ESC for Quadcopter |  |  |  | IAR | TopXGun is a manufacturer of quadcopters, who's seeking an FOC solution for the motors on ESC. | Received a motor with blade from the customer and had it mounted on a platform. I used KV3x with KMS to drive this motor on the tower system. The motor can be started with 1 second, but there's a possibility that the startup may fail. Had a discussion with Adam from LineStream via mails, the large cogging torque of this motor may be the main reason of unstable startup, and the performance may get better if startup current can be increased. The current is limited by the tower board, so I'm not able to do the test. |  |  | General | FAE (Larry Yang - B47306)
WW18 | Richy | Kevin Cheng | 1.5 | 11.5 | Motor Control | Huawei | Kinetis V | MVK56F512 | Early Evaluation |  | PMSM Electricity Generator |  |  |  | KSDK | PWM features support | Change the FreeMASTER interface for Huawei internal evaluatoin. Compared dead time logic between eFlexPWM and FTM, the difference is eFlexPWM accept various dead time source(PWM posedge, PWM negedge, EXT_A/B trigger), FTM dead time logic posses PWM posedge dead time insertion capability only. |  | Customization | Key | FAE (Roger Fan - R30375)
WW18 | Richy | Zhong Ji | 4 | 35.5 | Motor Control | Aucma | DSC | MC56F82728 | DI |  | VF Air-conditioner | 0.19 | 1-1F47TEV |  | CW10.6 | 2in1 soluiton of outdoor A/C unit | 2in1 timing development for Aucma has been completed of 95%. The pwm for compressor was controlled by SM1,SM2,SM3. SM1 SM2 was synchronized by SM3.The PFC pwm was controlled by SM0. the PWM frequency of compressor is 6K, and the one of PFC is 18K. The synchronized signals of PFC came from SM1VAL4 & SM2VAL4 & SM2VAL5. the ADC trigger signal came from SM0VAL2 &SM0VAL3. The current of compressor select the 1st of ADC EOS result corresponding to SM0VAL3 trigger. The offset of compressor select the 3rd of ADC EOS result corresponding to SM0VAL2 trigger. The SM1VAL5 compare Isr was used for delaying to start ADC sampling which can be ensured to avoid the trigger signal lost at the beginning of start stage. there still has a problem that is ADC trigger sequency is not right. |  | Customization | General | FAE (Mark Gou-B17936)
WW18 | Richy | GaoXiang | 0.5 | 0.5 | Digital Power | Delta | DSC | MC56F84543 | DI |  | Digital Power Supply |  |  |  | CW10.6 |  | Customer met problem when flashing code include an illegal address, the chip can't be programmed at all on customer’s board. Verify the same chip on NXP demo board, code can be download successfully, and compare the schematic but found no difference. Continue to found the root cause. |  | Customization | General | FAE (Moris Hsu-B18800)
WW18 | Richy | Li Shunan | 1.5 | 24 | Motor Control | Hikvision Hangzhou | DSC | MC56F84766 | DI |  | Dual stepper motor driver in camera gimbal |  |  | System | CW10.6 |  | Received the PCB board. After hardware debug, now the board can run one motor well. The dual stepper driver code is under developing. | New Requirement | Customization | General | FAE - Zhuang Chao
WW18 | Richy | Richy Ye | 0.5 | 1 | Digital Power | Huawei | DSC | MC56F82743 | Early Evaluation |  | Board Mounted Power |  |  |  |  | Chip features comfirmation | Had call about technical requirement details with customer R&D. Customer will develop 3/4 brick AC/DC BMP, the power consumption, package size and price are the key consideration for device selection against TI TMS320F29032/22. Provided device comparison sheet among NXP KV44, MC56F827xx and TI TMS320F28032/22 to customer for decision making. MC56F827xx is the best choice for this platform although customer target ARM strategy for her MCU supplier. | New Requirement | Customization | General | FAE (Roger Fan - R30375)
WW18 | Richy | Richy Ye, Zhou Xuwei, Zhong Ji | 1 | 1
WW18 | Richy
WW18 | Richy
WW18 | XD | Liu weiping | 2 | 12 | ePOS/Security | wtmec | Kinetis K | K81/KL81 |  |  | ePOS |  |  | EWM | IAR | Customer found some questions about EVML1 timing when they used 27.12M crystal on the EMVSIM board. | 1)We found the card clock divided from 27.12 can work normally on our tower k81 board. 2) The issues reported by custom caused by wrong way of calculation for those timings. (We must calculate some time out with the clock numbers rather than time) |  |  | Key | Yanrong Fu(yanrong.fu@nxp.com)
WW13 | XD | Liu weiping | 1.5 | 1 | Security | 智能果 | Kinetis L |  | Early Evaluation |  | USB CCID reader |  |  |  | IAR | 1. Porting the USB CCID driver to KSDK1.3. 2. Support customer for their product. | 1. Customer reported they can't run RSA in 1984bit with SECLIB. 2. We correct some issue in their modifications then the RSA in 1984bit run successfully.
WW18 | XD
WW18 | XD
WW18 | XD
WW18 | XD
WW18 | XD
WW18 | XD
Note on U57: Author: General Customer Support

## Apps Lead
Week | Team | Apps Engineer | Open Date | Close Date | Effort (man- days) | Total Effort | Family | Project | NPI Phase | Next Apps Milestone | TO Date | Enablement Task | Highlight/Lowlight/Issues/Risks | Progress record
WW18 | Sherry
WW18 | Sherry
WW18 | Sherry
WW18 | William
WW18 | William | Wang Hao | 2016-03-21 |  | 1 | 6 | Kinetis K | K4TV | Feasibility | Plan | July 21st | Documentation - Others |  | Finished review v0.7 ADD document, estimated validation task for K4TV include run mode max frequency K4TV can achieve, power consumption under run and low power modes, CAUv3 and performance monitor function check.
WW18 | william
WW26 | william
WW18 | william
WW18 | william
WW18 | william
WW18 | Eric | Chen Xinyu | 2016-03-25 |  | 0.5 | 6.5 | Kinetis E | MT512P | Execution |  | Q1'16 | Documentation - Data Sheet |  | Made a final datasheet item check list for the data must be re-tested on MT512P. Other values not marked for re-test can be reused either from MA512 or MT256P.
WW18 | Eric | Wang Ben | 2015-11-23 |  | 3.5 | 60.5 | Kinetis E | MT512P | Execution | Alpha customer Support 5/11 | Q1'16 | System Engineering |  | 1.PESD FA test is on-going.PE submitted PATS request and shipped damaged samples to KLM FA lab, Sample num15 and num8 FA were finished and reports were sent to ATX team for further review. Meanwhile PE submitted PATS request for SN12 FA. 2.Got 30pcs 64LQFP samples from PE, reserve for future system level EMC test. 3.Enablement third party Segger reported one issue on TWR-KE18F. They found a very strange oscillating reset signal on board, and it does not work correctly. Support Segger engineer analyze and investigate the issue.We guess that the output drivers of the OpenSDA MCU are partially broken,because in software they experimentally changed the port configuration of the reset pin to "high drive strength". Sent a new board to them in order not to gate their enablement tools delivery. 4.Received 15pcs 3in1-KE18F boards, verifed they are ok to program flash and download code. 5.Received 30pcs HVP-KE18F boards, found soldering issue that OpenSDA K20 chip does not solder as its correct pin order. After vendor reworked them, they are ok to program firmware. Found another issue that HVP-KE18F could not be programmed standalone, but has to work with mother board. Because the VDDA voltage comes from mother board.The root cause is the PMC module is new design for Kinetis E+ ,which is different from former Kinetis E/L/V/K family. The VDDA not only used by Analog modules, but also the PMC module itself.So VDDA pin could not be floating.
WW18 | Eric | Wang Ben | 2016-04-19 |  | 1 | 2 | Kinetis E | MT512P | Execution |  | Q1'16 | System Cases-BLDC demo |  | 1.Revised the software directory and structure from SDK1.3 to SDK2.0. Coding started, 10% is done. The demo clock configuration and function is ok.
WW18 | Eric | Wang Ben | 2016-02-01 |  | 0.5 | 5 | S08 | MC9S08SU16 | Execution | Marketing launch 6/10 | Q1'16 | System Engineering |  | 1.Received 60pcs SU16 samples from PE. Did basic flash download test with SD8 CW service pack on SD8 EVB.It is ok. 2.Validation team verified the VREFH damage issue has been fixed on SU16.
WW18 | Eric | Chen Yonggang |  |  | 2 | 32 | Kinetis E | KE15Z | Execution | Alpha program support - 5/31 | Q4'15 | Alpha Customer Support |  | 1. Supported Jap FAE on KE15Z SDK test. Jap FAE started to test SDK ER(Early Release), and found some software issues for the bubble, ecompass demo. Helped FAE solve the issues. 2. Jap FAE visited Mitsubishi RAC(Room Air Conditioner) indoor unit team to promote KE15Z, and reported 2 customer requirements: (1) KE15Z STOP IDD is 20uA, while competitor Renesas is 4uA. (2) Mitsubishi needs 2KB EEPROM data with 1M of endurance, and they are using an external EEPROM device now. KE15Z supports 2K flexRAM for EEPROM emulation, so it's our advantage.
WW18 | Eric | Chen Yonggang |  |  | 2 | 12 | Kinetis E | KE15Z | Execution | Alpha program support - 5/31 | Q4'15 | Board - Design |  | Drafted the schematic of RD-KE15-TSI board and sent out for review.
WW18 | Eric | Chen Yonggang |  |  | 1 | 1 | Kinetis E | KE15Z | Execution | Alpha program support - 5/31 | Q4'15 | Documentation - Application Notes |  | Writing an AN for ADC calibration, 50% done.
WW18 | Eric
WW18 | Eric
WW18 | Eric
WW18 | Richy | Howard Liu | 2015-07-16 |  | 2 | 77.5 | Kinetis E | MT512P | Execution |  | Q1'16 | System Cases |  | MT512P NPI: 1) Got the 5 daughter cards of MT012P used for 3in1 reference demo system. Run the smoking test for the board using the 3in1 code. 2) Continued to check the issue that PFC unworkable with motors simultaneously. But there's still no further progress for this issue. I cannot do more test since there's only one 3in1 power stage board available.
WW18 | Richy
WW18 | Richy
WW18 | XD
WW18 | XD
WW18 | XD
WW18 | XD
WW18 | XD

## Reference Design
Week | Team | Apps Engineer | Open Date | Close Date | Effort (man- days) | Total Effort | Family | Segment | Project | Reference Phase | Milestone Date | Progress record
WW18 | Sherry
WW18 | Sherry
WW18 | Sherry
WW18 | William | Guo Jia | 2016-04-11 |  | 0.5 | 12.5 | Kinetis |  | KEED | Development |  | Review the layout and now the KEED daughter card PCB goes to manufacture.
WW18 | William
WW18 | William
WW18 | William
WW18 | William
WW18 | William
WW18 | William
WW18 | William
WW18 | William
WW18 | William
WW18 | William
WW18 | Eric | Shi Changhao, Terry Lv | 2015-11-16 |  | 6 | 65 | Kinetis W | WirelessConnectivity/IoT | Smart home with KW41 | Development |  | 1. Finished driver porting from KW41 to smart home board. 2. Added pin settings to smart home board. 3. Tested fxos8700cq, ecompass, RTC, TSI, power manager, hello world DEMO on smart home board. Fixed issues in these demos. Now all passed. 4. Added new Buzzer and temperature detection demos. 5. Writing driver for light sensor and humidity sensor. 6. Start to contact vendor for antenna test, expect to finish in May.
WW18 | Eric | Terry Lv | 2016-04-18 |  | 2 | 8 | Kinetis K | Consumer/Communication | KS22-MINIKIT | Testing |  | Finished KS22-MINIKIT Release package generation. The new release package was then delivered to test team for build test. Four issues were fixed in release package. Now build test all passed. KS22-MINIKIT release package is now under testing.
WW18 | Eric
WW18 | Eric
WW18 | Eric
WW18 | Eric
WW18 | Richy | Howard Liu, Richy Ye | 2014-09-20 |  | 0.5 | 35 | DSC | Motor Control | Sensorless FOC e-Sooter -MC56F82728 | Development |  | PM, h/w and application s/w status: - Arranged the visit schedule of IDH and Bosch persons. MC software status of development and test (From Roznov team): - Implementation of the new HFI control structure is in progress. The last unfinished control block is the digital representation of voltage control oscillator.
WW18 | Richy | Wang Dechang, Zhang Yangjie, Cao Nan, Richy Ye, Gao Xiang, Wang Lingling | 2015-08-06 |  | 10 | 385 | DSC | Digital Power | Golden Server Power-Totem Pole BLPFC | Design |  | 1, Continued to optimze the PF value, the prototype can reach 0.9958 at 110Vac/3A input and 0.9908 at 220Vac/3A with the rectifier mosfet synchronized feature. 2, Builded the testing platform for both PFC and LLC prototypes, and the 2 prototypes can worked together by the PFC power good signal control, the whole system can load 300W power with good input PF value and low output voltage ripple. (highlight). 3, Found the PF value issue when power by the electricity grid, the input current will have some low frequency resonance , so the PI control parameters need be optimized to inhibit the abnormal resonance.
WW18 | Richy | Richy Ye, Wang Dechang, Jiang Dengyu, Kevin Cheng, Gao Xiang, Wang Lingling | 2015-03-23 |  | 3.5 | 182 |  | DSC | Digital Power |  | Golden Server Power | 1, Continued to prepare for the release documentation of LLC project, about 85% completed. 2, Got 5pcs main transformer and auxiliary power supply transformer samples from Wurth. 3, Complete assemble one LLC board and basic function verified success. 4, Update the code by using one GPIO to identify the power on good signal from PFC board, LLC board can generally working together successfully with PFC board.
WW18 | Richy | Wang Dechang, Jiang Dengyu, Wang Li | 2015-11-25 |  | 2 | 43 | WCT | Wireless Charger | WCT-15WTXAUTO | Design |  | 1. Following 15W automotive TX layout design; 2. Sent the NFC circuit's layout document to Jeremy for further check and got his positive feedback.
WW18 | Richy | Jiang Dengyu, Mao Huan | 2014-10-04 |  | 5 | 459 | WCT | Wireless Charger | WCT-15W1COLTX | Development |  | 1. Supported on-site debugging at Eurofins; the issue that 4 Samsung phones can't be initialized can be solved by appying one round digital ping instead of two; however, the interruption issue with two Samsung phones couldn' t be reproduced; still waiting for detailed test report for furthur analyze. 2. The issue that PWM terminate for about 4ms in negotiation phase is caused by unproper setting of ping state when fault occurs; the code optimization is ongoing, need more tests.
WW18 | Richy | Zhao Ping | 2015-01-12 |  | 1 | 74.5 | WCT | Wireless Charger | WCT-5WTXAUTO, WCT1001A/WCT1003A | Development |  | WCT service pack cannot be found on website. Now this service pack is in CW update pack. Modified the corresponding part of application user guide for GA4.0 release.
WW18 | Richy | Gao Xiang | 2015-02-01 |  | 1 | 178 | WCR | Wireless Charger | WPR1500 LDO/BUCK MPRX | Development |  | Continue to debugging the power loss estimation of WPR1500-Buck board, start to verify the new calibrated curve on different boards.
WW18 | Richy | Liu Zhen, Dingwenshuang | 2016-03-10 |  | 1 | 14 | S08 | Motor Control | DroneESC | Design |  | PCB Gerber file has been sent to Zhanfa, communicated with them to fix some problems through e-mail and telephone.
WW18 | Richy | Ding Wenshuang Liu Zhen | 2015-08-26 |  | 2 | 90 | Kinetis E | Motor Control | Low Cost PMSM sensorless solution-MKE02Z64 | Documentation |  | Added FreeMASTER graphical user interface control page for this reference design,It works well through test. Added related introduction in the application note.
WW18 | XD | haidong | 2016-01-04 |  | 5 | 49.5 | Kinetis W | WirelessConnectivity/IoT | SmartHome | Development |  | Make Demo application more stable: Add CoAP Server in the iOS APP to receive the notification from Thread node. Stop/Start the iOS CoAP server when the iOS APP enter suspend or be active from suspend. Add mDNS unicast response from Thread node to make iOS APP Thread node discovery more reliable. Two main issues from Thread stack impact this APP stability: Sometime Thread network create failed on the border router. Sometime border router dose not forward or lost the packet from Thread node to the outside network.
WW18 | XD
WW18 | XD
WW18 | XD
WW18 | XD
WW18 | XD
WW18 | XD
WW18 | XD

## Others
Week | Team | Apps Engineer | Open Date | Close Date | Effort (man- days) | Total Effort | Item | Segment | Family | Part | Module | Tools | Request brief | Overal Progress | Input Source
WW18 | Sherry
WW18 | Sherry
WW18 | Sherry
WW18 | Sherry
WW18 | William
WW18 | William | Wang Hao | 2016-04-29 |  | 0.5 | 0.5 | K60-2M tamper pad pullup resistor value need update. |  | Kinetis K | K60-2M | DryICE |  | K60-2M tamper pad pullup resistor value need update. | Simon from design team commented that K60-2M tamper pads actually implemented as standard IO pad instead of dedicated tamper pads with large pull up resistor, datasheet value for tamper pads pullup resistor should be changed to lower values. Also there is no passive filter on K60-2M tamper pins. Need to created errata to notify customer. | Design (Simon)
WW18 | William | Jia Ding | 2016-04-25 | 2016-04-27 | 2 | 2 | KL28Z FlexIO demo for CES |  | Kinetis L | KL28Z | FlexIO |  | Provide FlexIO demos for CES 2016 | Assembled another set of the FlexIO camera demo boards for CES. Mounted the boards into a acrylic box. Validated the QR decoder firmware.
WW18 | William
WW18 | William | YangXi | 2016-04-25 | 2016-04-25 | 1 | 1 | Update KE training slide according to feedback |  | Kinetis E | MT512P | bootROM |  | Update KE training slide according to feedback | Update KE Training slide (FlexCAN, Boot ROM) according to US SE team feedback. Correct some script pronunciation such as (I2C -> I square C) and some typo.
WW18 | William | Zhong Juying | 2016-04-25 | 2016-04-29 | 4 | 4 | add B-163 ellipse curve parameters support into security system of k81 |  | Kinetis K | MK81 | LTC |  | Maya from Secure MCU and Authentication IC FAE in Japan want to add B-163 ellipse curve support in security system of k81 | 1. analyzed the calculate modular inverse fail, it caused by no modular inverse API for binary polynomial in application layer. 2. packaged the APIs for binary polynomial mathmetics in application layer. 3. prepared the testing data and tested the APIs for bgf2m_add_mod, bgf2m_mul_mod, bgf2m_mod_inv, bgf2m_mod_exp, bgf2m_gcd and etc. 4. adjusted the codes according to debug result, will go on to debug
WW18 | William
WW18 | William
WW18 | William
WW18 | William
WW18 | Eric | Chen Xinyu | 2016-04-25 | 2016-04-26 | 1.5 | 1.5 | LPIT training slides for KE_Web_training |  | Kinetis E |  | LPIT |  | Make training slides for KE_Web_training. | Finished writing the training slides of LPIT module.
WW18 | Eric
WW18 | Eric
WW18 | Eric
WW18 | Richy | Howard Liu | 2016-04-21 |  | 1 | 1 | 3in1 system timing design documentation |  | DSC | MC56F84789 |  |  | Application Note for 3in1 system timing design on MC45F84789 | Drew some slides to be used in the document. 20% done
WW18 | Richy | Wang Li | 2016-04-27 |  | o.5 | 0.5 | WCT1111 test |  | WCT | WCT1111 |  | CW10.6 | WCT1111 test for customer evaluation | 1. Tested the WCT1111 for the faults occurred at overlap area reported by customer, the over voltage fault and internal fault. These issues are related to MP Rx. It can be solved by applying new coil on BUCK MP Rx. 2. Released the F/W with disabled Q measurement function as customer required.
WW18 | Richy | Ding Wenshuang Liu Zhen | 2016-04-08 |  | 3 | 12 | FTF Demo support |  | Kinetis E | MKE02Z64 |  | IAR | KE02 PMSM sensorless demo preparation for FTF. | 1,Solved some bugs existed in the project. 2,Finished developing the HTML control page based on VBScript, it works well through test. 3,Shipped the related hardware to United States. 4, Writed a document which include a detailed introduction about how to setup and run this demo, sent it with the project code to Mark Houston.
WW18 | Richy | Kevin Cheng | 2016-04-22 |  | 2 | 3 | Marketer Support - On the fly programming |  | DSC | MC56F84789 |  | CW10.6 | The on the fly feature demonstration and specification collection | Introduce the filed patent details to HP server power team. Customer accept our solution for on-the-fly programming, extra PWM demos is required to reinforce EE engineer confidence. Customer suggest we improves below items for better EMS performance, 1) flash key protection, 2) low VDD protection, 3)program counter run out protection. The primary competitor is TI UCD3138.
WW18 | Richy | Li Shunan | 2016-04-19 |  | 3 | 7 | Develop the HTML control page of Freemaster interface of MAPS Dual servo demo for the 2016 FTF |  | DSC | MC56F84789 |  | CW10.6 |  | Complete the HTML control page based on VBScript. Now user can operate the demo by clicking the graphical buttons.
WW18 | Richy
WW18 | XD | Chu Hongdong | 2016-01-28 |  | 5 | 34 | Implement PKHA example code |  | i.MX |  |  |  |  | Complete initial version of PKHA example code, prepare packages to share the code with customers.
WW18 | XD | Yang Zhao | 2016-04-28 |  | 4 | 4 | Secruity |  | Kinetis K |  |  |  |  | 1,Learn the knowledge about the smart card :the IOS7816-4 profile 2.Learn the project of seclib_demo and start to port the code to KSDK 2.0.
WW18 | XD
WW18 | XD
WW18 | XD

## List_Def
Team | Segment | Family | Part | Customer Phase | Reference Phase | NPI Phase | Module | Tools | Root cause | Solution | Support Type | Source | Enablement Task
KM | Automotive | S08 | i.MX53 | Early Evaluation | Design | Concept | USB | KSDK | Ctm S/W defect | Fix - Erata/JIRA | General | FAE | Documentation - Data Sheet
Sherry | Consumer/Communication | CF | KM34Z64 | DI | Development | Feasibility | ADC | PEx | Ctm H/W defect_D | Workaround | Key | BD_MKT | Documentation - Errata
Manish | Industry | DSC | KM34Z256 | DW | Integration | Plan | I2C | MQX | EMC | Customization | Professional Service | NPI_MKT | Documentation - RM
Lily | eReader | Kinetis L | KM34Z128 | Pilot | Reference Release | Execution | SPI | Linux | Design issue | Demo/Reference | Leverage | Sales | Documentation - Application Notes
Robin | Security | Kinetis E | KL17 | MP | SoW | Launching | TSI | Android | Design limitation | Benchmark | BD Activity | Unknown | Documentation - Others
Richy | Wireless Charger | Kinetis M | KM14Z64 | DL | Lib Release |  | AFE | WinCE | RM defect |  |  | CQI | System Cases
William | Motor Control | Kinetis V | ​MK60DN512 |  | Documentation |  | GPIO | CW10.6 | DS defect |  |  |  | System Engineering
Eric | Digital Power | Kinetis K | MC56F82313 |  | Testing |  | ENET | IAR | System improvement |  |  |  | Board - Design
XD | WirelessConnectivity/IoT | Kinetis X | MC9S08PT16AVLD |  |  |  | QTimer |  | Driver issue |  |  |  | Board - FAT Coding & test
| Smart Grid | Kinetis W | MK64FN1M |  |  |  | JTAG |  | Ref board issue |  |  |  | Board - Document
| Industry-Touch | i.MX | MWCT1012CFM |  |  |  | FLASH |  | New Requirement |  |  |  | Certification - USB
| Industry-HomeAppliance | WCT | MKE02Z32 |  |  |  | UART |  | SW issue |  |  |  | Certification - Others
| Power | WCR | MC56F82723 |  |  |  | I2S | [5 empty] | Training
|  |  | MC9S08SD8 |  |  |  | DAC | [5 empty] | Alpha Customer Support
|  |  | KL16Z128 |  |  |  | FlexIO | [5 empty] | Tools Support
|  |  | KE18Z |  |  |  | LPIT | [5 empty] | Bug analysis support
|  |  | MKV10Z32VFM7 |  |  |  | LPTimer | [5 empty] | SDK Driver
|  |  | KE18F512VLL15 |  |  |  | LPTPM | [5 empty] | System EMC
|  |  | MC56F84789 |  |  |  | Flextimer | [5 empty] | System Cases-KPET
|  |  | MC9S08PA16AVWJ |  |  |  | PWT | [5 empty] | System Cases-BLDC demo
|  |  | MT512P |  |  |  | PDB
|  |  | KE15Z |  |  |  | PIT
|  |  | KL17Z32VFM4 |  |  |  | eFlexPWM
|  |  | MC9S08SU16 |  |  |  | DMA
|  |  | i.MX6RT |  |  |  | WDOG
|  |  | MC56F84543 |  |  |  | EWM
SIM
MCG
SCG
OSC
ICS
LLWU
RCM
PMC
SMC
SAI
RTC
CRC
CAN
ESDHC
ACMP
VREF
DryICE
RNGA/TRNG
CMT
QDecoder
AMP
DDR
LCD
KBI
FlexNVM
IRQ
FlexBus
CM0+
CM4
CACHE
OPAMP
bootROM
Note on L2: Author: General Customer Support
Note on L3: Author: Key Customer Support
Note on L4: Author: Professional Service
Note on E5: Author: pre mass production
Note on L5: Author: Leverage to general base from customer support
Note on N8: support enablement tools such as register header files validation, debugger svd file validation and etc
Note on N9: support PE/design to do bench test on bugs