## Customer Support
Week | Team | Apps Engineer | Effort (man- days) | Total Effort | Segment | Customer | Family | Part | Customer Phase | MP Date | Product | LTR ($M) | GIBC | Module | Tools | Request brief | Progress record | Root cause | Solution | Support Type | Input Source | Community Link (Mandatory)
WW20 | Sherry | T.C. Lun | 3 | 5 | Card Reader | Genvict (Shenzhen, Guangzhou) | Kinetis | KS16 | DI |  | POS Card Reader |  |  |  |  | EMC problem solving |  Customer found that the system cannot be passed 8kv air discharge ESD test after plugged the new Bluetooth module into the system. Visit the customer and understand the situation and do some modification during the visit. Some improvement after the modification but still cannot met the customer requirement.  After got special approval form customer high management team, the customer provide two units and send the portion of schematic and PCB information to me directly because customer is very concern their IP (i.e. the product is under development and before launch to the market).  Complete the review in this Saturday and Sunday and passed the report and related information to the customer directly. Suggested customer to modify the board based on my suggestion in the review report. And I will try my best to do the modification also but may not be enough free time to do it due to office movement. |  | hardware design review, evaluation report with recommendations | Professional Service | Regional Marketing Manager, Opal Li (opal.li@nxp.com)
WW20 | Sherry
WW20 | Sherry
WW20 | Sherry
WW20 | Sherry
WW20 | William
WW20 | William | Wang Hao | 2 | 2 | Consumer/Communication | Spreadtrum | Kinetis K | MK64FN1M | DI |  |  |  |  | SDHC | KSDK | Customer request help on SDIO driver communication with their WiFi chip. | Customer reported ADMA error when issuing SDIO commands to their WiFi chip, their code is based on KSDK SDHC driver. Spend time to check SDIO spec and customer code and the ADMA descriptor table content dump, found the main issue is customer forgot to disable MPU when issuing SD commands that requires data phase which needs to use ADMA to access cross bar switch. After disabling MPU, SDIO communication with WiFi chip can work. | Ctm S/W defect |  | General | FAE (Li Ke) | https://community.freescale.com/thread/391600
WW20 | William | Wang Hao | 0.5 | 0.5 | Industry | Honeywell | Kinetis K | MK64FN1M | Pilot |  | Home cube Wifi | 3.4 | 1-1DICFRP |  | KSDK | Customer request urgent support to resolve MCU hang issue under ESD test. | Customer request support to resolve MCU hang issue under ESD test, even manually reset with MCU reset pin does not recover. Onsite support customer, reviewed customer schematic and found they floated PTA4 pin which is both NMI and Ezport input and could lead MCU into NMI exception or Ezport mode under ESD event. Modified code to disable NMI/Ezport function on PTA4 and configure this pin to GPIO output with internal pullup, customer tried with more than three boards with each board undergo over 25 times 6KV contact discharge without hanging MCU, customer consider this workaround resolved their issue. | Ctm H/W defect_D | Workaround | Key | FAE (Li Ke)
WW20 | william | Wang Peng | 1 | 1 | Industry | OJ Electronics | Kinetis E | KE02Z | Pilot |  | ventilation(motor control) |  |  | EEPROM |  | Customer report there are less than 1% failure rate for EEPROM programming | Customer report there are less than 1% failure rate due to EEPROM programming, however, it can success after cycle power again, communicate with FAE and make a test code to try to deplicate it,but can't see the same issue with more times test, deliver the test code to FAE and ask customer share the customer's code and ship two bad boards for further analysis. | New Requirement | Customization | General | FAE
WW20 | william | wang Peng | 0.5 | 0.5 | Industry | Shaanxi Xieli Photo Electric Instrument | Kinetis L | KL02Z | DI | 2016-12-01 |  | 0.152 | 1-1ZYC5NV | ADC |  | customer find there are lower ENOB than datasheet | Provide one ramp rate test data of ADC module to customer for reference, also suggest customer to disable other module(say LED display) so as to reduce the noise, and configure ADC as 16bit mode and use software algorithm(FIR/IIR) to improve the performance, finally customer accept this solution and test data basically meet customer requirement. | New Requirement | Customization | General | FAE | https://community.freescale.com/message/642658#comment-642658
WW20 | William | Jia Ding | 4 | 13.5 | Industry | Nanjing Paneng | Kinetis K | K66 | Early Evaluation |  | FTU Relay | 0.163 | 1-1UXFMD7 | ADC |  | FAE reported that customer tested K66 with ADC and SDRAM functionality, and they found while SDRAM module is operated, the ADC result varies largely for a constant voltage input. | Performed detailed tests on Firebird-K602M and TWR-K65F180M boards, by using different ADC input sources, ADCK sources, reference sources, and accessing SDRAM/Flexbus/GPIO while ADC conversion. Also captured waveforms of the input signal and reference source in some of the test conditions. Found that not only SDRAM, but also Flex bus and GPIO could affect ADC results. Concluded that the issue is likely to be resulted from the rapidly toggling digital pins, rather than the digital IPs. Made a test report to show the test results and the conclusion. | System Improvement | Customization | General | FAE(You Dawei) | https://community.freescale.com/message/633929
WW20 | William | Zhong Juying | 0.5 | 0.5 | Security | BBPOS | Kinetis K | MK21F |  |  | mPOS |  |  |  |  | customer wanted to got codes and support on des with anti-DPA to pass DPA testing in PCI lab. | 1. prepared our des countermeasure release and delivered to FAE. 2. pointed out some notices on porting the countermeasure. |  |  |  | FAE - Yang Yu
WW20 | William | Zhong Juying | 0.5 | 0.5 | security | SEIKO EPSON | Kinetis | [8 empty] | customer wanted to know SHA1 performance of MMCAU | 1. shared the performance data in community 2. explained the performance graph. 2.1 OptAssyLib means optimized Assembly driver Library, C_Lib means C language driver library. CM4@100MHz+MMCAU, OptAssyLib is 30Mbps for SHA1 CM4@100NHz+MMCAU,C_lib is 18Mbps for SHA1 |  |  |  | https://community.freescale.com/thread/391712?sr=inbox&ru=209603
WW20 | William | Zhong Juying | 1.5 | 1.5 | Industry |  | Kinetis K | MK81FN256VLL1 |  |  | QR decoder |  |  |  |  | want to increase decode accuracy of QR decoder algorithm | 1. reseached the QR decoder algorithm from internet and analyzed the infomation in order to increase the decode rate, the rate most likely due to input picture quanlity. 2. carefully read the OV7670 datasheet to find out helpful features on picture quanlity. obtained sharpen(3F EDGE), de-noising(4C DNSTH), zooming(0C COM3) and lens compensation(62~66 and 94~95 LCC1~5 and LCC6~7) 3. supplied the information to Yang Xi for tunning the CCM(CameraCompact Module) 4. attend meeting with BD and FAE to discusses QR decoder improvement. |  |  |  | SE - Yang Xi
WW20 | William | william jiang | 0.5 | 0.5 | Industry | Delta | S08 | SC116002MTG(S08SF4) | MP |  | DC Fan | 4 |  | PWT |  | Customer requested to low VIH spec | Volume: 50K to 1M pcs/m. Delta met a problem that their DC Fan cannot recognize the speed command from their customer system which is 3.3V and found the signal level of their customer system does not meet our MCU VIH spec, so they requested NXP to lower VIH spec from 0.65VDD to 0.55VDD. Had meeting with sales, FAE, disty and Delta to clarify their problem and requirement. Communicated with IP design and PE team. Confirmed by IP design that it is not feasible as the design switch point is 50%VDD, plus min hysteresis of 6%, the VIH min is 0.53VDD. PE team helped to test it on ATE and failure rate is 283/284 pcs at 135C case temperature with VDD from 2.65V to 5.5V. However, Delta still want NXP to do more test on 2K pcs with lower temperatures: -10C, 0C, 60C, 80C, 105C with 80C & 0C as high priority. This will cost a lot of PE effort. After negotiation among marketing, sales and FAE as well as PE, PE will test only 200pcs at 0C and 80C, and see the result, then feedback to Delta, it will take 1 week | New Requirement | Customization | Key | FAE (Stanley Huang)
WW20 | William
WW20 | Eric | Wang Ben | 0.5 | 0.5 | Motor Control | Delta | S08 | MC9S08SD8 | DI | Q1'16 | DC FAN | 3.612M | 1-LV3K97 |  | CW10.6 | 1.Delta asked several questions about GPIO behavior on SD8.They are a)GPIO status when chip VDD is power-off, GND or floating?When chip is power-off, input another 6V voltage on GPIO pin,is there any risk or acceptable? b)What is max input current for one GPIO? c)Delta wants us to provide the IO internal structure chart. | Support FAE to answer above questions and got the IO structure chart from design to provide to Delta. |  |  | Key | FAE-Stanley Huang
WW20 | Eric | Wang Ben | 0.5 | 0.5 | Power | Delta | S08 | MC9S08PA16AVWJ | DW |  | Offline UPS | $336K | 1-1W7Z78L |  |  | 1.Delta asked a question about tolerance of PA16AVWJ temperature.They would like to use wave soldering to solder the MCU, from the document they download, it says the temperature is at 260C within 40seconds.They want to know if it would damage the chip when they put put this SOIC20W package to an environment which is over either 260C or 40s | Referred to some package and product engineers, they said we did not qualify parts for wave solder,but only test it in air. Feedback to FAE that customer should have to take some risk since we do not have qualified data. |  |  | General | FAE-Moris Hsu
WW20 | Eric
WW20 | Eric
WW20 | Eric
WW20 | Eric
WW20 | Eric
WW20 | Richy | Li Shunan | 3 | 32 | Motor Control | Hikvision Hangzhou | DSC | MC56F84766 | DI |  | Dual stepper motor driver in camera gimbal |  |  | System | CW10.6 |  | After on-site acceptance test, customer is satisfied with the performance of the dual stepper. Write a parameter table for customer, these parameters can be modified by FreeMASTER. In the next step, work with customer to develop the communication protocol between the host computer and the dual stepper driver. | New Requirement | Customization | General | FAE - Zhuang Chao
WW20 | Richy | Li Shunan | 1 | 5.5 | Digital Power | ZTE Nanjing | DSC | MC56F84789 | DI |  | On-board Digital Inverter | 462K | 1-1UH4UK9 | System | CW10.6 |  | Help customer to use a 32-bits ramp function to slow-down the current startup process. | New Requirement | Customization | General
WW20 | Richy | Richy Ye, Wang Lingling | 4 | 32.5 | Digital Power | Artesyn Philippines | DSC | MC56F82748 | Early Evaluation |  | Digital power development platform |  |  |  |  | Tool box for automatic code generation from MATLAB | 1,To solve the problem of interrupt function-call, created the driver block with s-function, a PIT controlled marquee program was tested ok. 2,Started to create the driver block of common used peripherals with s-function, which contains the basic indentification parameters and the module initialization is realized by PE. 3,Renewed the trail license to June 9.
WW20 | Richy | Gao Xiang, Zhou Xuwei | 0.5 | 1 | Digital Power | Delta Shanghai | DSC | MC56F84543 | DW |  | Medical power |  |  |  |  | Customer found MC56F84543 can't be re-programmed after flash code include illegal address on customer’s board unless removed external crystal. | Visited customer and found customer defined two dimensional array 16*15 and assigned wrong start address when using it, thus the illegal address pointed to stack area, consider there was also a 10us period interrupt, these conditions caused the failure of flash program. Suggested customer to use the "wait for device to power up at connect" function at CW10.6, thus can avoid system run to illegal area before code download and code flash successfully. |  | Workaround | General | FAE(Moris Hsu)
WW20 | Richy | Gao Xiang, Zhou Xuwei | 0.5 | 0.5 | Digital Power | Delta Shanghai | DSC | MC56F82748 | Early Evaluation |  | DC-DC |  |  |  |  | Suggest customer build board based on NXP DSC solution | Introduced the DSC key peripheral PWM ADC and internal crossbar to customer, demonstrated how to use SW function to optimize the VIN feedforward and VOUT dynamic performance, but customer insist NXP to provide the transfer function to compare the system frequency bandwidth result with TI and ADI. Provided LLC dynamic result to customer for reference. |  | Customization | General | FAE(Moris Hsu)
WW20 | Richy | Gao Xiang, Zhou Xuwei | 0.5 | 0.5 | Digital Power | Delta Shanghai | DSC | MC56F84543 | DW |  | Telecom Power |  |  |  |  | Latch up issue when ESD test or power on at short time after power off | Analysis the possible trigger condition of latch up to customer, consider MC56F84543 comply with AECQ100, latch up will occur when VDD exceed 1.5*Vmax or 1.5*Imax. Suggest customer to use 3.3V TVS and detail review the PCB layout, but they can't accept external protect solutions compare with chips from other companies. FAE will found DSC designer to get more detail information of latch condition. |  | Workaround | General | FAE(Moris Hsu)
WW20 | Richy | Zhou Xuwei, Zhong Ji | 7 | 190 | Motor Control | Deye | DSC | MC56F84789 | DI |  | VF Air-conditioner | 10 | 1-1S40I05 |  | CW10.6 | 3in1 soluiton of outdoor A/C unit | Two new boards from Deye were received and are being debugged. 1) One of board has problem in short circuit protection; the other is good. 2) Reconfigurate the ADC0 and ADC1 channels for PFC&Fan and Compressor in accordance with new ADC pins assignment. 3) Configurate the PWMASM3 module using XBAR to connect PWM trigger signal with PFC PWM input. 4) The normal board can run the compressor successfully in the air-conditioner system. Next step the extended flux observer library and TL online compensation library will be planted into project. |  | Customization | Key | FAE (Zhuang Chao-B50031)
WW20 | Richy | Kevin Cheng | 2 | 9 | Digital Power | Huntkey Shenzhen | DSC | MC56F84766 | Early Evaluation |  | HV industry LLC converter |  |  |  | CW10.6 | PWM generation for 3 phase LLC converter x 2 | Send out the demo code and slides for customer evaluatoin. It illustrates 1) frequency fine tune through Q31 format on PWMA and PWMB and 2)uses eFlexPWM external sync and force initialize to control phase delay between sub modules. |  | Customization | BD Activity | FAE(Roger Fan - R30375)
WW20 | Richy | Kevin Cheng | 0.5 | 2 | Digital Power | GE Energy | DSC | MC56F827xx | Early Evaluation |  | AC/DC module |  |  |  |  | CrM mode interleaved totem pole PFC control | Customer faces problems on 1) fast interrupt configuration and 2) DMA configuration for QTMER capture result movement. Provides an example that demonstration fast interrupt configuration and DMA configuration for PWM0B capture result movement. |  | Customization | General | FAE (Cherrish Liao)
WW20 | Richy | Wang Dechang, Jiang Dengyu, Wang Li | 1 | 93.5 | Wireless Charger | LG CTO | WCT | WCT1003A | Early Evaluation |  | 15W_TXAUTO |  |  |  | CW10.6 | Board bringup and full function debug. | 1. Finished the debug of SPI on customer's platform. The data sending and receiving functions work well in the tests, now the code is released for customer test. | New Requirement | Customization | General | FAE (Kate Lee - B45752)
WW20 | Richy | Wang Dechang, Jiang Dengyu, Wang Li | 4 | 17.5 | Wireless Charger | PLDS | WCT | WCT1001A | Early Evaluation |  | 15W_TXAUTO |  |  |  | CW10.6 | Support customer debug. | 1. Keep debuging the project. The timing and driver works well now. But the DCDC chip still can't work, and the rail voltage can't be output rightly. During the tests, there are some other strange issues happen, like the 3.3V is abnormal, and so on. The board debug is ongoing. | New Requirement | Customization | General | FAE (Beta Chen - B44998)
WW20 | Richy | Ding Wenshuang Liu Zhen | 1.5 | 10 | Motor Control | Zhanyu | Kinetis E | MKE02Z32 | DI |  | HVAC Fan |  |  |  | IAR | Sensorless PMSM solution debugging | 1,Released the fixed parameters in the hybrid flux observer lib,tested it with Mige motor in the lab,now the motor can run with calculated parameters with both DQ observer and hybrid flux observer. Have sent the code to FAE for different motor debugging on customer site. | New Requirement | Customization | General | FAE(Cherrish liao-R65774)
WW20 | Richy | Zhao Ping, Jiang Dengyu | 0.5 |  | Wireless Charger | Yanfeng Visteon | WCT | WCT1001A | DI |  | 5W Automotive Power Transmitter |  | 1-1PXZD81 |  |  | Digital ping voltage issue | Digital ping voltage is abnormal at the beginning of ping start, customer uses different parameters with reference design which is unreasonable, and inform customer to optimize the parameters. | New Requirement | Customization | General | FAE (Yu Ningning - B45276)
WW20 | Richy | Richy Ye, Mao Huan | 1 | 2 | Wireless Charger | Intesight | WCT | MWCT1012CFM | DI |  | 15W 1COIL TX |  | 1-22043ZR |  | CW10.6 | Customer wants to apply only MP charging control algorithm for both LP and MP charging | Released one version code with only MP charging control algorithm to customer; customer will handle potential problems that may cuased by tradoff. | New Requirement | Customization | General | FAE(Beta Chen-)
WW20 | Richy | Richy Ye, Jiang Dengyu, Mao Huan | 2 | 48 | Wireless Charger | LGIT | WCT | MWCT1012CFM | DW |  | 15W 1COIL TX | $1.70 | 1-FFWPV2 |  | CW10.6 | Customer want a solution of WPC+PMA based on WCT1111 | Found interruption issue when charging Samsung S6 Edge+ with certarin battery percentage and Z-gap; the noise on coil current is large, which results in DDM timeout; will do more optimization. | New Requirement | Customization | Key | FAE( Kate Lee - B45752)
WW20 | Richy | Wang Li, Mao Huan, Jiang Dengyu | 0.5 | 15 | Wireless Charger | Magic-Link | WCT | MWCT1012CFM | DW |  | Wireless Charger Transmitter |  | 1-1OU8JG3 |  | CW10.6 | Check customer's MP TX schematic. | Checked customer's schematic and gave some comments. Sent our design documents to customer for reference. | New Requirement | Customization | General | FAE(Yu Ningning - B45276)
WW20 | Richy | Ethan Cheng | 1 | 1 | WirelessConnectivity/IoT | Senao | Kinetis W | MKW40Z160VHT4 | DI |  | IoT gateway | $1.2M | 1-218W7NO |  | IAR | Kinetis Bootloader problem on KW40Z | Customer had problem on changing the application address of KW40Z Kinetis Bootloader for a big code size application. Supported customer find out the issue and solved the problem. | New Requirement | Customization | General | FAE (Chiang Jason - R44828)
WW20 | Richy | Ethan Cheng | 1 | 1 | ePOS/Security | Singular | Kinetis K | MK81FN256VLL1 | DI |  | mPOS | $0.129M | 1-210STHK |  | IAR | Software update question | Coach FAE integrate and build EMV_contact_L1_Pre-certification_on_KL81 software update patch. | New Requirement | Customization | General | FAE (Lin Kent-B41538)
WW20 | Richy | Zhao Ping, Richy Ye | 3 | 34 | Wireless Charger | Delphi US | WCT | WCT100xA | Early Evaluation |  | Automotive low power dual-mode wireless transmitter |  |  |  |  | Code size and analog ping questions | 1, Check how much space is remaining on WCT1001A. About 4.2KB is remaining for flash. When compiler optimization is disabled, flash is not enough. After freemaster function is disabled, 3.8KB is remaining. Sent code size information to customer. 2, Customer report coil 1 current adc counts is around 2800 during analog ping phase. This value is bigger than DC offset, so analog ping return value is limited to 10, which cause analog ping cannot detect any object. Explain analog ping process and suggest them to adjust ADC trigger position according to HW. 3, Answered questions about function logic and analog ping control, send 45 days license for customer temporary use. | New Requirement | Customization | Professional Service | PM (Worthy Anna - B18818)
WW20 | Richy | Richy Ye | 0.5 | 13.5 | Wireless Charger | Omron Japan | WCT | MWCT1001A | DW | 2018 | 5W Automotive Dual-Mode Power Transmitter |  |  |  |  | PMA support plan | Supported regional marketer about PMA SR1E support plan and certification for customer meeting. | New Requirement | Customization | Professional Service | FAE (Noriaki Masuda-B01926)
WW20 | Richy | Richy Ye | 0.5 | 0.5 | Wireless Charger | Haier |  | MWCT1012, MWPR1516 | Early Evaluation |  | Robot cleaner | $0.6M |  |  |  | Technical support | Customer is interested with our 15W wireless charger system for her robot cleaner. Supported customer about technical concerns from evaluation test results. | New Requirement | Customization | General | Sales (Tyrone Yang - B46014)
WW20 | Richy
WW20 | XD | Chu Hongdong | 5 | 9 | ePOS/Security | Landi | i.MX | i.MX6UL |  |  | ePOS | 500K | #1-1PPBZ7A | HAB,CAAM,SNVS,Dryice,BEE | Yocto | Implement security features. | Complete tamper detection driver and unit test code, send the package to Landi to verify the function. Check how to implement BEE function in Linux kernel. |  | Customization | Key
WW20 | XD
WW20 | XD
WW20 | XD
WW20 | XD
WW20 | XD
WW20 | XD
WW20 | XD
Note on U55: 作者: General Customer Support

## Apps Lead
Week | Team | Apps Engineer | Open Date | Close Date | Effort (man- days) | Total Effort | Family | Project | NPI Phase | Next Apps Milestone | TO Date | Enablement Task | Highlight/Lowlight/Issues/Risks | Progress record
WW20 | Sherry
WW20 | Sherry
WW20 | Sherry
WW20 | William | GuoJia | 2015-05-03 | 2015-05-05 | 3 | 5 | Kinetis L | KL28 | Execution |  |  |  |  | 1. For KL28ZEM-FRDM, as factory engineer mixed up the single core and dual core chips and they cannot distinguish them, made to code to detect if one board is single core or dual core. But factory engineer cannot program the code to board. Gave a remote debugging, the issue still not resolved. After going on site, found the root cause is, the JLINK driver of version 5.12 is not working. After retrieve to version 5.00, everything is OK. 2. Finished the test on the peripherals, found the three-color LED is not working correctly. Only two colors can be lighted on each board. But this issue is not seen when testing the 70 boards in factory. 3. Found 1 board on which the VADJ is 4.11V, all other board did not show this issue. But when K26 is not powered on, the VADJ is 3.58V, instead of 3.30V expected. When K26 is powered on, VADJ is 3.30V as expected. 4. Finished testing the KL28/K26 SWD interface on the 70 boards, all passed. 5. Found one issue that the pull-down resistor make the K26 go to EZPORT mode, so the SWD interface cannot be connected. This issue is fixed by removing the pull down resistor, as the test shows this does not affect the KL28 SWD connection, this workaround is applied to all the 70 boards.
WW20 | Eric | Chen Xinyu | 2016-03-25 |  | 1.5 | 12 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | Complete the coding of ADC adder use case, debug and verification is on-going.
WW20 | william | Wang Hao | 2016-03-21 |  | 1 | 8 | Kinetis K | K4TV | Feasibility | Plan | July 21st |  |  | Continue ADD and system register file review and prepare for planning summit.
WW26 | william | YangXi | 20/5/2016 |  |  | 0.5 | Kinetis L | KL28 | Launching |  |  | Documentation - Others |  | 1. Prepared FRDM-KL28Z QR decoder demo’s PPT to marketing 2. Verify USB_SRAM feature and aligned with design: a. USB_SRAM can be accessible only when USB clock gate is opened. b. USB_SRAM cannot be used as code space. USB_SRAM does not connected to Instruction bus.
WW20 | william
WW20 | william
WW20 | william
WW20 | Eric | Wang Ben | 2015-11-23 |  | 1.5 | 63.5 | Kinetis E | MT512P | Execution | Alpha customer Support 5/20 | Q1'16 | System Engineering | 1.PESD light emission FA result was done, aligns with IO expert’s failure theory.Further IO design optimization will be applied on MT512P IO structure. New IO library will be released with BE fix on 5/16, MT256P 1.1 TO on 5/20 based on that. | 1.PESD light emission FA result was done, aligns with IO expert’s failure theory.Further IO design optimization will be applied on MT512P IO structure. New IO library will be released with BE fix on 5/16, MT256P 1.1 TO on 5/20 based on that. 2.Continue test and debug the DAP-link issue, gave some clues and analysis results to SW team.Got one updated version with high drive strength enabled on all SWD pins, after test the drag MSD function still fail under 5V. 3.Prepared the FCC ACR document for TWR-KE18F.
WW20 | Eric | Wang Ben | 2016-04-19 |  | 2 | 6 | Kinetis E | MT512P | Execution |  | Q1'16 | System Cases-BLDC demo |  | 1.BLDC demo porting is on-going.Coding is 80% done.Will do system intergration debug and test later. 2.Found three SDK2.0 headfile and driver issues duing coding.Raised JIRA tickets in system and feedback to SDK team.The ticket numbers are KPSDK-10772,KPSDK-10797 and KPSDK-10798.
WW20 | Eric | Wang Ben | 2016-02-01 |  | 0.5 | 6 | S08 | MC9S08SU16 | Execution | Marketing launch 6/10 | Q1'16 | System Engineering |  | 1.P&E updated the CW service pack for SU16, verfied it is ok to download code to flash.
WW20 | Eric | Chen Yonggang | 2016-03-28 |  | 2 | 18 | Kinetis E | KE15Z | Execution | TSI demo board design - PCB Layout - 5/27 | Q4'15 | Board - Design |  | Finished LCD(Layout Consideration Document) writing to specify layout requirements. Finished all part library building in Agile system. Layout was started on May/09 and on-going by Jimmy, finished placement now.
WW20 | Eric | Chen Yonggang | 2016-05-02 |  | 1 | 2.5 | Kinetis E | KE15Z | Execution | TSI demo board design - PCB Layout - 5/27 | Q4'15 | Training |  | Supported FTF Austin Touch demo show. Helped Marketing Michael set up FRDM-TOUCH demo, and FreeMASTER GUI in the shortest time, as KE15Z Marketing Neil cancelled the trip to Austin.
WW20 | Eric | Chen Yonggang | 2016-05-09 | 2016-05-09 | 1 | 1 | Kinetis E | KE15Z | Execution | TSI demo board design - PCB Layout - 5/27 | Q4'15 | Documentation - Data Sheet |  | Conducted a meeting to update KE15Z datasheet with the existing data that BACES team tested. The ADC, DAC, IDD, IO, LPFLL and PMC chapters are updated after the meeting.
WW20 | Eric | Chen Yonggang | 2016-05-11 | 2016-05-11 | 0.5 | 0.5 | Kinetis E | KE15Z | Execution | TSI demo board design - PCB Layout - 5/27 | Q4'15 | Alpha Customer Support |  | Answered Jap FAE questions on TSI demo, FlexIO demo in KE15Z SDK ER. FAE want to know how to run the mutual TSI demo, and how to measure PWM output in FlexIO demo. Answered Jap FAE question about the feasibity to use KE14F header files and settings to debug KE18F device, as customer Mitsubishi target is KE14F, but they only have KE18F samples.
WW20 | Eric | Chen Yonggang | 2016-05-10 | 2016-05-10 | 0.5 | 0.5 | Kinetis E | KE15Z | Execution | TSI demo board design - PCB Layout - 5/27 | Q4'15 | Board - Design |  | Updated FRDM-KE15Z Schematic and Layout from A2 to B version for the 1Kpcs production board building. The schematic changes only include replace U13 MCU KE15Z and E1,E2 touch pads with the normal parts in Agile system. Sent out the latest schematic to SDK team for review.
WW20 | Eric | Chen Xinyu | 2016-03-25 |  | 0.5 | 7.5 | Kinetis E | MT512P | Execution |  | Q1'16 | Documentation - Data Sheet |  | 1. MT256P datasheet is under updating by BACES and Doc team. 2. MT512P datasheet has been generated a new version, which marked all the data which need BACES/TE/PE test to TBD. And later need to fill in the data which must be reused by MT256P when MT256P DS is ready.
WW20 | Eric | Chen Xinyu | 2016-03-25 |  | 2.5 | 14.5 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | 1. Finished the LPI2C adder use case for Standard, Fast, Fast+ modes. Got the LPI2C adder data on FRDM-KE15Z. Later will do the Ultra Fast mode use case. 2. Discussed with PE for the KPET data collection, Li Wen is learning about the use cases and how to collect data. We still need to co-work with PE to make KPET data collection task easier.
WW20 | Eric | Chen Xinyu | 2016-04-22 |  | 0.5 | 1 | i.MX | i.MX6RT | Feasibility | Plan | Q4'16 | Documentation - Others |  | 1. Reviewed PRD, raised some questions on the doc, SW, HW requirement. 2. Discussed on the SW delivery which may not ready for FreeRTOS support on some drivers. 3. Discussed on the HW plan.
WW20 | Richy | Howard Liu, Liu Zhen | 2015-07-16 |  | 5 | 86.5 | Kinetis E | MT512P | Execution |  | Q3'16 | System Cases |  | The FTM initialization trigger and external triggers are Ored together to generate one FTM trigger as an input of TRGMUX module in MT512P that's different from the MA512 PTV silicon. Changed the interrupt used for compressor control calculation since initialization trigger cannot be used as standalone trigger any more. (Howard Liu) Porting code from 3 in 1. it's finished now. debug is ongoing. (Alex Liu)
WW20 | Richy | Richy Ye | 2016-04-27 |  | 0.5 | 1.5 | i.MX | i.MX6RT | Feasibility |  | Q4'16 | System Cases |  | Had core team meeting to track the activities from different functional group. A question was raised about if the motor control can be implemented on FreeRTOS, and provided the BLDC motor control example code with MQX (High priority kernel interrupt used for motor control timer routine) on K60 to software team for feasibility evaluation.
WW20 | Richy | Richy Ye | 2016-01-25 |  | 0.5 | 9 | UHV | MU64 | Concept | Feasibility | Q3'16 | Features definition |  | MU64 entered into concept phase. Had meeting with product owner, analog design and systems/architecture to discuss the GDU design risk with HGx >20V, VBSx/VCP higher voltage (38V to 45V), and boot strap voltage with 8V/11V option.
WW20 | Richy
WW20 | XD
WW20 | XD
WW20 | XD
WW20 | XD
WW20 | XD

## Reference Design
Week | Team | Apps Engineer | Open Date | Close Date | Effort (man- days) | Total Effort | Family | Segment | Project | Reference Phase | Milestone Date | Progress record
WW20 | Sherry | T.C. Lun, Wang Peng, Yonggang Chen | 2015-10-22 |  | 1.5 | 27.5 | Kinetis E | Industry | MT512P (100-LQFP) NPI Microwave Oven EMC Test Platform | Design and Test |  |  Received the control board from our Shanghai and Suzhou team. Completed the surge test in original and our MT512P board and both are passed level 3 level. Sent the tested data to our Shanghai and Suzhou team. And some suggestion had been passed to the team also such as add the microwave power control, rotating disc need to run after the microwave power is turned on and timer to count the test time. Since there is no time to do the ESD evaluation. The ESD evaluation will be postponed after completed the office movement (i.e. around in June this year).
WW20 | Sherry
WW20 | Sherry
WW20 | William
WW20 | William | wang peng | 2016-01-04 |  | 1.5 | 15.5 | Kinetis E | Industry | Microwave oven | Design - EMC test |  | Go to Suzhou office to join the training of Surge from 3CTest, also do the surge test on Microwave oven, which can pass the level 3(+/- 2000V) test, also debug and solve the LED blinking issue during direct contact discharge test by enhanced software and hardware, document the EMC report and deliver to team.
WW20 | William
WW20 | William | YangXi | 2016-05-09 |  | 3 | 93 |  | Industry | QR decoder | Development |  | QR decoder software updated: 1. Improve image quality by enabling OV7670’s DSP, decode accuracy better than before. 2. Optimizing Fast Image Binarizer code, improve the decode rate from 6f/s to 8-9f/s Attend meeting with BD and FAE to discusses next step for this demo: including current solution update and prepare adaptor board design when new camera module(OV5648).
WW20 | William | Zhong Juying | 2016-01-01 |  | 2 | 2 | Kinetis K | Security | pure DES with DPA countermeasure | Integration |  | 1. finished to debug random number generation. 2. debugged the lptmr interrupt service function, it seemed that the interrupt couldn't be enabled. will find the cause. 3. debugged the des countermeasure algorithm functions, it seemed that it only run one time, then cpu entered to hardfault. will go on to debug.
WW20 | William
WW20 | William
WW20 | William
WW20 | William
WW20 | William
WW20 | William
WW20 | Eric | Shi Changhao, Terry Lv | 2015-11-16 |  | 7 | 82 | Kinetis W | WirelessConnectivity/IoT | Smart home with KW41 | Development |  | 1.Finished visiting antenna vendor for next step test and will continue the test while the point to point RF test firmware is ready. 2. Continue to support low level driver development from system level. 3. Finished sorting the improvement item list for REV2 board to now. 4. Create another reposotory smart_home_connsw for BLE connection software. 5. Run BLE, GENFSK, 802.15.4 examples on smart home board. All passed currently.
WW20 | Eric | Song Juanjuan, Chen Xinyu, Lv Terry | 2016-04-29 | 2016-05-13 | 3.5 | 6.5 | Kinetis K | Consumer/Communication | KS22-MINIKIT | Reference Release |  | 1. Finished testing the new generated SDK package, found one doc issue. Fixed and released a updated package. 2. Finished the HW/SW Users Guide. 3. Delivered the SDK package the UG to ucDragon.
WW20 | Eric
WW20 | Eric
WW20 | Eric
WW20 | Eric
WW20 | Richy | Wang Dechang, Zhang Yangjie, Cao Nan, Richy Ye, Gao Xiang, Wang Lingling | 2015-08-06 |  | 6 | 393 | DSC | Digital Power | Golden Server Power-Totem Pole BLPFC | Design |  | 1, Continued optimized the current sensing ciruits filter, decrease the filter bandwidth, achieved the parameter to relized the PF>0.99 with full load under the 110Vac and 220Vac input. . 2, Continued to calculate the controloop bode graphic for current digital control parameter. 3, Continued to solve the abnormal current waveform when powered by the power grid .
WW20 | Richy | Wang Dechang, Jiang Dengyu, Wang Li | 2015-11-25 |  | 2.5 | 47.5 | WCT | Wireless Charger | WCT-15WTXAUTO | Design |  | 1, Updated 15W automotive TX schematic for Delphi’s reference; 2, First round layout check with team and updated the comments to EDADOC according to team’s suggestions and wil share with team for further check after updated; 3, Exported updated bom for cost quotation;
WW20 | Richy | Richy Ye, Wang Dechang, Jiang Dengyu, Kevin Cheng, Gao Xiang, Wang Lingling | 2015-03-23 |  | 1 | 185 |  | DSC | Digital Power |  | Golden Server Power | Start to review the draft version release documentation of LLC project inside team.
WW20 | Richy | Gao Xiang | 2015-02-01 |  | 1 | 181 | WCR | Wireless Charger | WPR1500 LDO/BUCK MPRX | Development |  | Continue debugging WPR1516-NXPMP15 reworked receiver board, IIC communication could work correctly with external pull up resistor, FSK function works as a medium power receiver, System works well with MPTX at 5V/1.4A and 9V/1.4A, but ASK communication will fail when output voltage reach 12V and output current exceed 0.8A.
WW20 | Richy | Howard Liu, Richy Ye | 2014-09-20 |  | 3 | 38.5 | DSC | Motor Control | Sensorless FOC e-Sooter -MC56F82728 | Development |  | PM, h/w and application s/w status: - Went through the motor control software delivered by Roznov team. I'll reivew the code with Roznov team while I'm in Roznov next week. MC software status of development and test (From Roznov team): - Significant progress reached in development and implementation of new HFI method based on rotational injection. The position recognition part of algorithm works stable, no drift of estimated position observed. The next step will be implementation of magnet polarity detection in rotational HFI, because the original developed by Zbynek cannot be used.
WW20 | Richy | Jiang Dengyu, Mao Huan | 2014-10-04 |  | 1 | 461 | WCT | Wireless Charger | WCT-15W1COLTX | Development |  | 1. Got degug result with Samsung phones from Korea FAE, no charging interruption issue could reproduce; 2. Got 3 pecies of 15 1coil TX from IOP lab, updated f/w and prepared for next round certification;
WW20 | Richy | Zhao Ping | 2015-01-12 |  | 0 | 74.5 |  | Wireless Charger | WCT-5WTXAUTO, WCT1001A/WCT1003A | Development |  | A13 GA4.0 is released on website.
WW20 | Richy
WW20 | XD | haidong | 2016-01-04 |  | 5 | 58.5 | Kinetis W | WirelessConnectivity/IoT | SmartHome | Development |  | 1: Prepare SmartHome Thread demo for Thread Group Open House and take part in this open house. 2: Try to find the root cause for border router memory leak issue on SmartHome Thread demo.
WW20 | XD
WW20 | XD
WW20 | XD
WW20 | XD
WW20 | XD
WW20 | XD
WW20 | XD

## Others
Week | Team | Apps Engineer | Open Date | Close Date | Effort (man- days) | Total Effort | Item | Segment | Family | Part | Module | Tools | Request brief | Overal Progress | Input Source
WW20 | Sherry | T.C. Lun | 2015-05-01 |  | 2 | 59 | Equipment Transfer from Hong Kong to China and US | [5 empty] | Logistic |  Vendor had picked the boxes and stored in their office. Checked the boxes and hand carry out the confidential document immediately when the boxes arrived in the vendor. Now no any item or belonging in HK site.  All wooden boxes had been arrived in our Shenzhen new office but three boxes are too large and cannot be moved into the lift and our office. Travel to the new office and guide the mover how to take care the shielding room because any damage will degrade the shielding effectiveness. Spent over half-day to unpack those three boxes and move the shielding room to our office. Then the re-assemble had been arranged in next Monday.
WW20 | Sherry
WW20 | Sherry
WW20 | Sherry
WW20 | William
WW20 | William
WW20 | William | YangXi | 19/5/2016 | 20/5/2016 | 1 | 1 | find root cause of TWR-KE18 DAP-Link MSD functtion fail issue |  | Kinetis E | KE18 |  |  | The DAP-Link firmware MSD function only work under 3.3V, we set V_BRD = 5V, when drag image into MSD, the RESET signal will always be pulled down, when POR does not take effect. The new bin file did not update correctly. | Check the schematic and try to short SWD_DIO and SWD_CLK’s level shifter, and MSD function works in 5V. Then, checked the level shifter DS, found different operating voltage has different rising/falling rate, feedback to team and give possible workaround.
WW20 | William | Zhong Juying | 2016-05-13 |  | 0.5 | 0.5 | add B-163 ellipse curve parameters support into security system of k81 |  | Kinetis K | MK81 |  |  | Maya from Secure MCU and Authentication IC FAE in Japan want to add B-163 ellipse curve support in security system of k81 | 1. finished to add sect163r2 ellipse curve parameters support in security system. 2. finished to verified all of methmatics for binary polynomial 3. will to prepare the release package
WW20 | William
WW20 | William
WW20 | William
WW20 | William
WW20 | William
WW20 | William
WW20 | Eric | Terry Lv | 2016-05-09 | 2016-05-11 | 1.5 | 1.5 | Help to identify I2C double-buffered issue | Power | Kinetis W | KW40 | I2C | IAR | Help to identify I2C double-buffered issue | It is reported by customer that I2C on KW40 can't hold BUS in transmission. So in case of a long I2C IRQ, I2C will continue send SCL clocks to slave. The root cause is that the I2C version on KW40 don't have DFEN bit. So in receive mode, no matter master or slave will both read data automatically and the software read will not hold bus. Workaround is to use DMA or avoid long interrupt routine beyond one byte long. The later version has DFEn bit wich will block double buffer and hold but before read. KW41 is using _66 I2C version which has DFEN bit.
WW20 | Eric
WW20 | Eric
WW20 | Eric
WW20 | Richy | Ding Wenshuang Liu Zhen | 2016-04-27 | 2016-05-12 | 1.5 | 10 | FTF demo support |  | Kinetis E | MKE02Z64 |  | IAR | Support FTF demo | FTF application engineer report two issues about the low cost PMSM sensorless demo. The first issue is the demo can't correctly working on his side, The second is that he thought the lowest speed for this demo is too high.Helped him to set the demo correctly. Modified some parameters and added excitation current in the low speed range to increase BEMF,now the lowest speed can be up to 100rpm. Sent the code to FTF demo owner and no feedback yet.
WW20 | Richy | Ding Wenshuang | 2016-05-13 | 2016-05-13 | 1 | 1 | Marketer support-Motor control applications-KE02 |  | Kinetis E | MKE02Z32 |  |  | Sensorless BLDC slides preparing | Finished adding hardware part, design details and experiment test waveforms about initial rotor position detection and closed-loop startup into the the original slide deck.
WW20 | Richy | Zhao Ping | 2016-05-12 |  | 1.5 | 1.5 | Study IIC module and touch sensor in WCT1001A | Wireless Charger | WCT | WCT1001A |  |  | Study IIC module and touch sensor in WCT1001A | Study IIC module, and familiar with touch sensing process used in A13 Rev2 board.
WW20 | Richy | Mao Huan | 2016-05-11 |  | 1 | 1 | Had meeting with Denis and reviewed wireless charging project. | [6 empty] | Had meeting with Denis and reviewed wireless charging project.
WW20 | Richy | Richy Ye | 2016-05-11 |  | 0.5 | 0.5 | Air-conditioner compressor control solution promotion | Motor Control |  |  |  |  | Solution customer promotion material | Indian AE/FAE are looking for the air-conditioner compressor control solution for local market promotion. Provided the promotion materials of NXP 3in1 air-conditioner reference design on MC56F84789 to them.
WW20 | Richy | Richy Ye, Kevin Cheng, Ethan Cheng, Gao Xiang | 2016-01-01 |  | 0.5 | 3.5 | Digital power customer issues review | Digital Power |  |  |  |  | Bi-weekly review digital power customer issues with FAEs | Review digital power customer issues with FAEs, provide action/answer/advice for all open issues.
WW20 | Richy | Richy Ye | 2016-05-10 | 2016-05-13 | 1 | 1 | Sub-group community for motor control, digital power and wireless charging applications | [5 empty] | Private energy conversion community groups setup | Three private sub-groups are setup for motor control, digital power and wireless charging applications. My team is the owner to manage and track them, will improve the customer support efficiency especially for APAC region.
WW20 | Richy | Richy Ye, Howard Liu, Ding Wenshuang, Derek Wang, Mao Huan | 2016-05-11 | 2016-05-11 | 2.5 | 2.5 | Solution team meeting | [5 empty] | Energy conversion China team alignment | Have meeting with Denis about micro BL solution team chart and align the roadmap of energy conversion segment. Which is very fruitful to understand the role/responsibility and activities plan.
WW20 | Richy
WW20 | XD | Yang Zhao | 2016-04-28 |  | 5 | 14 | Secruity |  | Kinetis K |  |  |  |  | 1.Finsh proting the project and release the new code based on KSDK2.0. 2 .learn the knowledge of cryptography . RSA and ECC.
WW20 | XD | Liu Weiping | 2016-05-04 |  | 3.5 | 6.5 | Internal supporing for EMVL1 pre-certification on KSDK2.0 |  | Kinetis E | K21/K81 |  |  | For Passing the EVML1-precet on KSDK2.0 | 1. There was only one failed item in EMVL1 pre-cert on K21 KSDK2.0 project. But we can't find the cause about this failed item currently. 2. The last modifications has helped to fix most issues in cardsim test. There are also a few failed items in debugging. The issue of the big delay after ATR will need much more changing of the code structure. So there are some risks for longer the day of completion. (This issues was also reported by 联迪)
WW20 | XD
WW20 | XD
WW20 | XD

## List_Def
Team | Segment | Family | Part | Customer Phase | Reference Phase | NPI Phase | Module | Tools | Root cause | Solution | Support Type | Source | Enablement Task
KM | Automotive | S08 | i.MX53 | Early Evaluation | Design | Concept | USB | KSDK | Ctm S/W defect | Fix - Erata/JIRA | General | FAE | Documentation - Data Sheet
Sherry | Consumer/Communication | CF | KM34Z64 | DI | Development | Feasibility | ADC | PEx | Ctm H/W defect_D | Workaround | Key | BD_MKT | Documentation - Errata
Manish | Industry | DSC | KM34Z256 | DW | Integration | Plan | I2C | MQX | EMC | Customization | Professional Service | NPI_MKT | Documentation - RM
Lily | eReader | Kinetis L | KM34Z128 | Pilot | Reference Release | Execution | SPI | Linux | Design issue | Demo/Reference | Leverage | Sales | Documentation - Application Notes
Robin | Security | Kinetis E | KL17 | MP | SoW | Launching | TSI | Android | Design limitation | Benchmark | BD Activity | Unknown | Documentation - Others
Richy | Wireless Charger | Kinetis M | KM14Z64 | DL | Lib Release |  | AFE | WinCE | RM defect |  |  | CQI | System Cases
William | Motor Control | Kinetis V | ​MK60DN512 |  | Documentation |  | GPIO | CW10.6 | DS defect |  |  |  | System Engineering
Eric | Digital Power | Kinetis K | MC56F82313 |  | Testing |  | ENET | IAR | System improvement |  |  |  | Board - Design
XD | WirelessConnectivity/IoT | Kinetis X | MC9S08PT16AVLD |  |  |  | QTimer |  | Driver issue |  |  |  | Board - FAT Coding & test
| Smart Grid | Kinetis W | MK64FN1M |  |  |  | JTAG |  | Ref board issue |  |  |  | Board - Document
| Industry-Touch | i.MX | MWCT1012CFM |  |  |  | FLASH |  | New Requirement |  |  |  | Certification - USB
| Industry-HomeAppliance | WCT | MKE02Z32 |  |  |  | UART |  | SW issue |  |  |  | Certification - Others
| Power | WCR | MC56F82723 |  |  |  | I2S | [5 empty] | Training
|  |  | MC9S08SD8 |  |  |  | DAC | [5 empty] | Alpha Customer Support
|  |  | KL16Z128 |  |  |  | FlexIO | [5 empty] | Tools Support
|  |  | KE18Z |  |  |  | LPIT | [5 empty] | Bug analysis support
|  |  | MKV10Z32VFM7 |  |  |  | LPTimer | [5 empty] | SDK Driver
|  |  | KE18F512VLL15 |  |  |  | LPTPM | [5 empty] | System EMC
|  |  | MC56F84789 |  |  |  | Flextimer | [5 empty] | System Cases-KPET
|  |  | MC9S08PA16AVWJ |  |  |  | PWT | [5 empty] | System Cases-BLDC demo
|  |  | MT512P |  |  |  | PDB
|  |  | KE15Z |  |  |  | PIT
|  |  | KL17Z32VFM4 |  |  |  | eFlexPWM
|  |  | MC9S08SU16 |  |  |  | DMA
|  |  | i.MX6RT |  |  |  | WDOG
EWM
SIM
MCG
SCG
OSC
ICS
LLWU
RCM
PMC
SMC
SAI
RTC
CRC
CAN
ESDHC
ACMP
VREF
DryICE
RNGA/TRNG
CMT
QDecoder
AMP
DDR
LCD
KBI
FlexNVM
IRQ
FlexBus
CM0+
CM4
CACHE
OPAMP
bootROM
Note on L2: 作者: General Customer Support
Note on L3: 作者: Key Customer Support
Note on L4: 作者: Professional Service
Note on E5: 作者: pre mass production
Note on L5: 作者: Leverage to general base from customer support
Note on N8: support enablement tools such as register header files validation, debugger svd file validation and etc
Note on N9: support PE/design to do bench test on bugs