## Customer Support
Week | Team | Apps Engineer | Effort (man- days) | Total Effort | Segment | Customer | Family | Part | Customer Phase | MP Date | Product | LTR ($M) | GIBC | Module | Tools | Request brief | Progress record | Root cause | Solution | Support Type | Input Source | Community Link (Mandatory)
WW26 | Sherry
WW26 | Sherry
WW26 | Sherry
WW26 | Sherry
WW26 | Sherry
WW26 | William | Jia Ding | 0.5 | 0.5 | Industry | Manul Lab, FPC, Brilliants from Korea distributor | Kinetis K | K22, K64 | Early Evaluation |  | credit card with finger print recognition |  |  | SPI |  | FAE reported that the interval time between two continuous SPI frame is too long to affect the communication speed. | Run KSDK2.0 demo code on Freedom boards, and did not reproduced the issue. So inferred that it is resulted from customer's code. Provided suggestion about configuring SPI registers and using DMA method to access SPI FIFOs to fix the issue. The ticket has been fixed. | Customer code defect |  | General | FAE(Thomas Kang) | https://community.nxp.com/message/804987
WW26 | William | Wang Hao | 1 | 1 | Industry | TIC | Kinetis K | MK02 | [5 empty] | JTAG | KSDK | Customer reported PEMicro debugger disconnection problem when Kinetis go to stop mode under KDS. | Did some experiment with several Kinetis boards when MCU goes to stop mode and check KDS debugger behavior when using PEMicro debugger, found debugger disconnected on both Win7 and Win8 PC and this is before KDS plugin updated. If KDS plugin updated, debugger does not get lost, MCU can continue single step code when MCU waked up. | KDS plugin not updated | Customization | General | Mendoza Juan | https://community.nxp.com/message/630011#comment-630011
WW26 | William | Wang Hao | 1 | 1 | Consumer/Communication | Huawei | Kinetis K | MK82 | Early Evaluation |  | Finger print recognition |  |  |  |  | Customer need Kinetis MCU performance and power consumption data for finger print project. | Customer is evaluating MCU for their new finger print recognition project, K82 or KL82 is selected as candidate to connect with external FPC1022 chip. Main performance and power consumption data customer requested includes MCU low power wake up time, SPI read time for transferring 10K bytes of data, security algorithms supported and time to finish those algorithms, MCU power consumption under run and low power modes. Made spreadsheet to collect associated data for both K82 and KL82 and sent to customer. As customer has height requirement for final product, most likely they will choose K82 for its thin BGA package. |  |  | Key | BD (Wang Wei)
WW26 | william | Wang Peng | 1 | 1 | Industry | Delta | Kinetis E | KEA64 | DI |  |  |  |  | FLASH |  | customer feedback MCU is stall when run EEPROM sector erasing. | Also test this issue in my side, find it reproduce this same issue, further debug aand find the root cause is ESFC enabled, after disable it, this issue is removed,also contact design to clarify the ESFC bit. | New Requirement | Customization | General | FAE | https://community.nxp.com/message/803970?et=notification.mention#comment-803970
WW26 | william | Wang Peng | 0.5 | 0.5 | Consumer/Communication | SONY | Kinetis L | KL17Z32VFM4 | DI |  | Walkman | 1.1 |  | I2C |  | customer want to learn how to use high dirve for I2C confguration | Clarify the function of HDRS in I2C_C2 register and DSE in PORT_PCR, also introduce how to configure I2C high drive. | New Requirement | Customization | General | FAE | https://community.nxp.com/message/803962?et=notification.mention#comment-803962
WW26 | william | Wang Peng | 1 | 1 | Industry | GuangZhou HuaXin | Kinetis K | MK22FN256VLH12 | DI |  | IR-TOUCH |  | 1-1UH9T2X | USB |  | Customer feedback USB device don't get response when host send the command (GET DESCRIPTION) with zero length | Try to reproduce this issue with SDK code, but can't reproduce it, check with FAE and confirm the cause is from Windows driver, and customer develop their production on Android platform, also has the same issue, involve USB stack team to analysis it, and further debug is on-going. | New Requirement | Customization | General | FAE
WW26 | William
WW26 | William | YangXi | 0.5 | 0.5 | Digital Power | Artesyn | DSC | MC56F84xx (Nevis) | Early Evaluation |  | i.Hp (Power Supply) | 1M | 1NIHKSM | CAN |  | FlexCAN Rx Overrun | Customer is experiencing FlexCAN Rx overrun. Suggest customer to use CAN Rx queue or RxFIFO to dial with overrun issue, give them suggestion and pseudocode code on how to handling the Rx interrupt | Ctm S/W defect | Customization | General |  | https://community.nxp.com/thread/390940?q=MC56F84766CAN
WW26 | William
WW26 | William
WW26 | William
WW26 | Eric | Shi Changhao, Terry Lv | 2 | 22 | WirelessConnectivity/IoT | LG/VW | Kinetis W | KW41 | Early Evaluation |  | Car BLE/WIFI Dual Anteana System | 12M |  | Radio | IAR | Customer request to have a technical data sheet on BLE power consumption of KW41 | 2. Create a ADV and SCAN power test application on CC2650DK. The power consumption of CC2650 is much better than KW41. On the case of 40ms ADV, KW41 needs averaged 875uA. But CC2650 needs 495uA.
WW26 | Eric | Terry Lv | 0.5 | 0.5 | Consumer/Communication | Chanceux | Kinetis L | KL02 | Early Evaluation |  | MFi audio |  |  |  | KSDK | Customer build a KDS PEx project and the code size is around 13KB. Customer want to reduce the code size to 8KB. | 1. Build customer's project and the binary size is 14K. 2. Check Eric's comments and give more tips on removing OSA layer. |  |  |  |  | https://community.nxp.com/thread/395728
WW26 | Eric | Chen Yonggang | 0.5 | 0.5 | Industry | Avnet Distributor | Kinetis E | KE06 | Early Evaluation |  |  |  |  | FLASH | IAR | The MKE06 has the Erase Verify All Blocks and Unsecure Flash commands. Reading the manual it seems that both commands do the same (erase whole flash, verify and unsecure). Questions: 1) What is the difference between the 2 commands? 2) In what case would one command or the other be used? | Answered this question by describing the differences between the two flash commands and use cases. |  |  |  |  | https://community.nxp.com/thread/428386
WW26 | Eric | Shi Changhao/Terry Lv | 1 | 1 | Smart Grid | Newcapce | Kinetis M | KM34Z128 | MP |  | 1-PHASE 4-CHANNEL Meter | 100KU/Y |  | AFE | IAR | Customer want us to review their new schematic before MP | Customer already ordered 30K pcs chip and met a issue in MP that the chip locked when doing frequently programming. it is found that customer connect the reset signal directly to MCU instead of through the resistor and the reset circuit is not properly layout. right now we help customer to reveiw the new schematic and layout. | Ctm H/W defect_D | Customization | Professional Service | FAE(Yang Liang)
WW26 | Eric
WW26 | Eric
WW26 | Eric
WW26 | Richy | Zhou Xuwei | 2 | 8 | Motor Control | MONDE | DSC | MC56F82736 | DI |  | Air-conditioners for automobiles |  |  |  | CW10.6 |  | 1). MONDE made two boards out of the updated schematic, but still one phase current signal and the PWM input signal are assigned to inappropriate pins. Guided the engineer of MONDE to fix this problem in our lab. 2). Checked the motor control related functions of the boards in our lab to make sure they can work at the site of Benling. One amplifier was broken and one isolation chip was soldered upside down. 3). Onsite supported MONDE for compressor test at Benling. The current scale was increased to 40.04A but the PI gains for ASR stayed the same, which led to the startup failure caused by the a large torque current drop after the merge. Loading capability and startup capability were tested on the condensing system when we reduced the ASR gains, and the performance seemed to be OK. MONDE will continue the development of CAN bootloader and other peripheral functions. |  | Customization | General
WW26 | Richy | DingWenshuang | 1 | 12 | Motor Control | zhanyu | Kinetis E | MKE02Z32 | DI |  | HVAC-FAN |  |  |  |  | Debug PMSM sensorless solution based on custoemr's board. | Customer reported one issue that the motor can't switch to closed loop on their side.Tested the project with different parameter setting in the lab. No problem found. FAE will visit the customer and find the issue. | New Requirement | Customization | General | FAE(Cherrish Liao-R65774)
WW26 | Richy
WW26 | Richy
WW26 | Richy | Richy Ye, Jiang Dengyu, Mao Huan | 0.5 | 57 | Wireless Charger | LGIT | WCT | MWCT1012CFM | DW |  | 15W 1COIL TX | $1.70 | 1-FFWPV2 |  | CW10.6 | Customer want a solution of WPC+PMA based on WCT1111 | 1. LGIT will place 30Ku initial PO for 15W 1 COIL TX. 2.Received sniffer log of fast wireless charging issue when offset is about 5mm; request more information from Freemaster to anyalze. 3. Customer report that TX couldn't terminate charging immediatly when remove PMA ring; this case can be approved by adjust some threshold to filter some noise. | New Requirement | Customization | Key | FAE (Kate Lee - B45752)
WW26 | Richy | Zhao Ping | 1 | 37 | Wireless Charger | Delphi US | WCT | WCT100xA | Early Evaluation |  | Automotive low power dual-mode wireless transmitter |  |  |  |  | Debug console change and key fob for PMA | 1, Supported customer to change debug console from SCI1 to SC0, and guide how to connect FreeMASTER by JTAG. 2, Key fob for PMA was working well. Sent the code to customer for test. | New Requirement | Customization | Professional Service | PM (Worthy Anna - B18818)
WW26 | Richy | Zhao Ping | 0.5 | 23.5 | Wireless Charger | Omron Japan | WCT | WCT1001A | DW | 2018 | 5W Automotive Dual-Mode Power Transmitter |  |  |  |  | Release V4.0.2 SW | Release latest code with Omron's request. | New Requirement | Customization | Professional Service | FAE (Noriaki Masuda-B01926)
WW26 | Richy | Zhong Ji | 5 | 219.5 | Motor Control | Deye | DSC | MC56F84789 | DI |  | VF Air-conditioner | 10 | 1-1S40I05 |  | CW10.6 | 3in1 soluiton of outdoor A/C unit | 1)The document of compressor control debug experience is being written, including how to select TO bandwidth of extended flux observer, how to determine the PI value of load torque observer, the tip of move average filter without phase lag, the compensation ratio of torque online compensation, and the compressor startup method(85%). 2) Comment were added into the global variables of compressor control libraries source code, it is convenient for users to understand and how to use these variables. |  | Customization | Key | FAE (Zhuang Chao-B50031)
WW26 | Richy | Wang Li, Mao Huan, Jiang Dengyu | 1 | 18.5 | Wireless Charger | Magic-Link | WCT | MWCT1012CFM | DW |  | Wireless Charger Transmitter |  | 1-1OU8JG3 |  | CW10.6 | Require to check customer's design documents. | Applied heating mode and idle mode based on v3.0 for customer; did some tests and sent it to customer for test; | New Requirement | Customization | General | FAE(Yu Ningning - B45276)
WW26 | Richy | Wang Li, Jiang Dengyu, Wang Dechang, Richy Ye, Zhao Ping | 3.5 | 110 | Wireless Charger | LG CTO | WCT | WCT1003A | Early Evaluation |  | 15W_TXAUTO |  |  |  | CW10.6 | Board bringup and full function debug. | 1. Customer support for LG CTO MP AUTO project. The root cause of PMA reset issue is found. It is caused by the DDM runaway. The PMA DDM algorithm checks the valid signal when the point triggers the threshold. Under worst communication condition, the DDM may check every point in DDM buffer, which leads to the DDM ISR execution time be much longer. Since the interrupt nest is enabled, the other ISR request will break the DDM ISR, causing the DDM ISR runaway and system breakdown. By optimizing the DDM ISR time, the issue disappears in our tests. The F/W is updated for customer test now. 2. For the DDM decoding issue, the false decoding disappears with last firmware in customer test, but the update makes the power packet decoding be more difficult. With Li Gang's help, the judgement conditions are loosened for better power packet demodulation, and the firmware is updated for customer test. By now there is no feedback. | New Requirement | Customization | General | FAE (Kate Lee - B45752)
WW26 | Richy | Jiang Dengyu, Wang Li, Wang Dechang | 4 | 42.5 | Wireless Charger | PLDS | WCT | WCT1001A | Early Evaluation |  | 15W_TXAUTO |  |  |  | CW10.6 | Support customer debug. | 1, Adjusted the coil switching circuits parameters to optimize the performance; 2, Adjusted the TX coil with higher inductance to be compatible with MP LDO RX & MP BUCK RX, with the optimized coil and resonant parameters, PLDS 15W AUTO TX board can start up with MP LDO RX at 2A load and with MP BUCK RX at 3A load; 3, Recorded the changed system parameters and shared with FAE. 4. Released the firmware with latest changes for customer test; 5. For research, start to change the topology to half-bridge and check the performance. | New Requirement | Customization | General | FAE (Beta Chen - B44998)
WW26 | Richy | Liu Zhen | 1 | 5 | Motor Control | X-CAM | S08 | MC9S08SU16 | DI |  | Drone ESC |  |  |  | CW10.6 | ESC solution for SU16 | 1, Received reworked board provided by customer, over current fault always occur when run, the root cause is under debugging. 2, Sent one reference board to FAE to promote customer, demonstrate how to use the reference board to FAE on site. 3, Solved one issue FAE found. the issue is that communication between PC and reference board disconnect easily under debug environment. the root cause is that the clock of CPU and BDC is 40M, the BDM mode of Multilink can not support 40M. solved it by replacing 40M frequency by 20M frequency. |  | Workaround | General | FAE(Cherrish Liao-R65774)
WW26 | Richy | Liu Zhen | 0.5 | 0.5 | Motor Control | Positec | Kinetis E | MKE02Z32 | Early Evaluation |  | Electric drill |  |  |  | IAR | Electric drill solution for KE02 | Received electric drill customer provided. Customer want us to run the drill based on cropper's hardware board, but the hardware board is not adapted, there's no PWM signal on MOS tube. The reason is that the IPM drive capacity is not enough because the DC bus voltage is 20V. FAE has known the issue and will consult with customer to solve it. |  | Workaround | General | FAE(Cherrish Liao-R65774)
WW26 | Richy | Kevin Cheng | 1 | 10.5 | Digital Power | Huntkey Shenzhen | DSC | MC56F84766 | Early Evaluation |  | HV industry LLC converter |  |  |  | CW10.6 | project migrates incorrectly | Customer new a MC56F84766 project, it reuses settings in exmaple project. They faces different eFlexPWM behavior due to missed some init code out side of PEx. will send out the codes can't implement in processort expert for team's review then send to PEx team. |  | Customization | BD Activity | FAE(Roger Fan - R30375)
WW26 | Richy | Kevin Cheng | 1 | 1.5 | Digital Power | Delta HP Chungli | DSC | MC56F8246 | DI |  | 2.4KW power supply | 0.3M | 1-23XUN58 |  | CW8.3 | suggestions for iTHD improvement | support FAE prepares the nanoedge patch. | New Requirement |  | Key | FAE (Jiunn Yang - B45153)
WW26 | Richy | Kevin Cheng | 1 | 2 | Digital Power | Delta HP Chungli | DSC | MC56F82743 | DI |  | HP G11 Digital Power Platform | 0.3M | 1-23XTYT8 |  | CW10.6 | ram space not enough | optimize customer's calculation code by adding "register" on local variables, this reduced execution time by 21 percent. The calculation code is all about multiply and shift operation. The C code effiency is limited. Aligned with FAE about the necessary of assembly code writting, will prepare it later. | New Requirement |  | Key | FAE(Jiunn Yang - B45153)
WW26 | Richy | Richy Ye, Wang Lingling | 2.5 | 50.5 | Digital Power | Artesyn Philippines | DSC | MC56F82748 | Early Evaluation |  | Digital power development platform |  |  |  |  | Tool box for automatic code generation from MATLAB | 1.Verified the flexibility to use NXP algorithm library in simulink models with examples. 2.Researched the automatically download method of matlab, understood the process now, but it's hard to know the command of calling the exsiting software to download. | New Requirement | Customization | Key | FAE(Andrey Eng - B43125)
WW26 | Richy | Xiang Gao, Richy Ye | 0.5 | 2.5 | Wireless Charger | Amazon | WPR | WPR1516 | Early Evaluation |  | Wireless Charger |  |  |  |  | Wireless charing demo on amazon tab | Provide the wireless charging Rx cover stick on Amazon tab, which verified charging correctly under WIFI mode, provide the draft BOM cost result for evaluation. | New Requirement | Customization | General | Solution (Allen Lv-B42246)
WW26 | Richy
WW26 | Richy
WW26 | Richy
WW26 | XD | Hu Teng | 3 | 3 |  | LGE/VW | Kinetis W | KW41 | Early Evaluation | [7 empty] | BLE Data Throughput, theoritical effective throughput is 98.9kB/s, I have tested 81.3kB/s can be reached, further improvement can't be done because of stack or hardware issues, which have been reported to Romania R&D team
WW26 | XD | Liu weiping | 3 | 3 |  | 江苏怡丰通信设备有限公司 | Kinetis K | K81 | Customer Phase | [7 empty] | 1. assistant the customer analysis the failed items of emv-certification. 2. gave some suggestion to customer and help them passed all pre-certification.
WW26 | XD | Yang Zhao | 3 | 3 | Security | Landi | Kinetis K | k81 | [7 empty] | issue of seclib drivers | 1.help the engineer of Landi use our security stack : The api use of RSA 2 .Find a bug of our stack ,then build a new lib and send it to Landi |  | Customization | Key
WW26 | XD | Chu Hongdong | 3 | 10 | ePOS/Security | CCV | i.MX | i.MX6UL |  |  | ePOS |  |  | SIMv2 | Yocto | EMV L1 pre-certification with SIMv2. | CCV reported some issues about CWT error, give some suggestion to locate the problem, need analyze further to confirm whether it is caused by the precision of baud rate or some wrong settings. |  | Customization | Key
WW26 | XD | Chu Hongdong | 2 | 27 | ePOS/Security | Landi | i.MX | i.MX6UL |  |  | ePOS | 500K | #1-1PPBZ7A | HAB,CAAM,SNVS,Dryice,BEE | Yocto | Implement security features. | Fix the issue reported by Landi that interrupt is generated continually when tamper triggers and security boot is enabled, it is because SSM transits to soft fail state from trusted state in this situation. |  | Customization | Key
WW26 | XD
WW26 | XD
WW26 | XD

## Reference Design
Week | Team | Apps Engineer | Open Date | Close Date | Effort (man- days) | Total Effort | Family | Segment | Project | Reference Phase | Milestone Date | Progress record
WW26 | Sherry
WW26 | Sherry
WW26 | Sherry
WW26 | William
WW26 | William | wang peng | 2016-05-16 |  | 2 | 8.5 | Kinetis L | Industry | iPOS | Design - evaluation |  | 1. Visit customer(walkpos) to show the reference design of magnetic stripe reader,try all customer test cards, and for normal and strong card, customer think this is good, and for that weak magnetic card, identify rate is lower than customer's POS with hardware decoding, also it is not easy to operate current card slot , plan to order the standard card slot and improve decoding algorithm to do performance comparison later, and current identify rate is about 70%(weak magnetic card), expect to up to more 90%. 2. Rework "FRDM CVT" board, connect its card slot to TWR-KL82Z72M board, and get it work well.
WW26 | William
WW26 | William | YangXi | 20/6/2016 | 24/6/2016 | 3 | 109 | Kinetis K | Industry | QR decoder | Development |  | 1. 4 QR demo hardware and 2 adapter board send to FAE. And help them to assembly for demo show. Update QR decoder UG accordingly and put to dock tracker. 2. communicated with SK FAE and got them default and custom setting for Hi708. Try their auto exposure time setting, the image improve a little not much. 3. Got information from local FAE: a. One scanner vender use Hi704 module and interested in our decode algorithm. we are willing to provide the Hi704 sample and default register setting to us.
WW26 | William
WW26 | William
WW26 | William
WW26 | William
WW26 | William
WW26 | William
WW26 | William
WW26 | Eric | Terry Lv, Shi Changhao | 2015-11-16 |  | 2 | 122 | Kinetis W | WirelessConnectivity/IoT | Smart Home With KW41 | Development |  | 1. Add power adjustment, test duration and limitation test features to PER application. The application is now pushed. 2. Coding on our sensor tag application, 20% finished.
WW26 | Eric
WW26 | Eric
WW26 | Eric
WW26 | Eric
WW26 | Eric
WW26 | Richy | Wang Dechang, Zhang Yangjie, Richy Ye, Gao Xiang, Wang Lingling | 2015-08-06 |  | 6 | 425 | DSC | Digital Power | Golden Server Power-Totem Pole BLPFC | Design |  | 1， continued to optimized the control calculation optimization, use the fraction mode to get high calculation performance, the system can get better performance under the 20V voltage input , and all the control logic have moved to the new calculation platform, continue to debugging the system with higher input voltage. 2,Completed the Ishape introduce PPT to Huawei for reference, inclue 3 methods.
WW26 | Richy | Jiang Dengyu, Mao Huan, Richy Ye | 2014-10-04 |  | 0.5 | 476.5 | WCT | Wireless Charger | WCT-15W1COLTX | Development |  | 1. Released one version code to FAE with Samsung fast wireless charging; 2. Fixed the issue of LED when chargin Amazon box;
WW26 | Richy | Zhao Ping | 2015-01-12 |  | 3 | 81 | WCT | Wireless Charger | WCT-5WTXAUTO, WCT1001A/WCT1003A | Development |  | DDM sample point development. Find the DC offset crossing point of coil current to trigger ADC. Completed code to search the new trigger point, do some test with RX simulator and packet parsing is working well with three mode. Will test more RX to verify the new sample point performance.
WW26 | Richy | Wang Dechang, Jiang Dengyu, Wang Li | 2015-11-25 |  | 2 | 55 | WCT | Wireless Charger | WCT-15WTXAUTO | Design |  | 1. Checked WCT-15WAUTOTX layout documents; 2. Checked Omron WCT1111 multi coil TX schematic and give comments; 3. Released WCT-15WAUTOTX layout design documents as A080 in agile.
WW26 | Richy | DingWenshuang LiuZhen | 2015-08-26 |  | 1 | 92 | Kinetis E | Motor Control | Low Cost PMSM sensorless solution-MKE02Z64 | Documentation |  | Document team finished editing the application note, Reviewed the document and gave some comments to the editor.
WW26 | Richy | Liu Zhen, Ding Wenshuang | 2016-03-10 |  | 4 | 35 | S08 | Motor Control | SU16 - Drone ESC | Design |  | There are two start up methods we debugging currently. One is that start up is successful after many times test, but the start up period is long and start up noise is little big. The other is that start up is failed with very low probability, but the start up period is short and the start up noise is little small. the reason for failure of second method is under debugging.
WW26 | Richy | Gao Xiang | 2015-02-01 |  | 0.5 | 187 | WCR | Wireless Charger | WPR1500 LDO/BUCK MPRX | Development |  | Continue to build FreeMASTER GUI of receiver side.
WW26 | Richy | Richy Ye, Wang Dechang, Jiang Dengyu, Kevin Cheng, Gao Xiang, Wang Lingling | 2015-03-23 |  | 2 | 198 | DSC | Digital Power | Golden Server Power |  | Design | 1,Found the problem of the board lend to Cherrish , the connection of drive transformer was not stable. 2,Modified the sampling parameters of resonant current, under the condition of 380V input,it slightly improved the dynamic performance and especially in the no-load and full load switch the effect is obvious. However, when the input voltage is lower, such as 330V, the inner loop is not stable, so more consideration should be paide to the zero-pole configuration.
WW26 | Richy | Howard Liu, Richy Ye | 2014-09-20 |  | 1 | 49.5 | DSC | Motor Control | Sensorless FOC e-Sooter -MC56F82728 | Development |  | PM, h/w and application s/w status: - 1) Xiaoniu M1 was shipped. 2) Had meeting with Roznov team to align the requirement document for the next steps of the project and discuss how to do with the motor parameters measurement. Jaroslav will update the requirement document based on Howard's comments on the initial version then send Howard to translate for IDH&Bosch. The motor parameters measuring method will be documented also. 3) Checked with IDH what's set by the position of throttle. IDH told it was torque. but Roznov thought it might be the speed. It needs more investigation. MC software status of development and test (From Roznov team): Throttle control was modified. Instead of required torque the driver sets require power. Thus it is much more comfortable to maintain the constant speed with certain throttle position which was very difficult with setting of direct torque. Multiple road tests performed to evaluate the dynamic performance and the behavior. By setting the required power, there is also naturally limited allowable battery current, or the required power can be easily limited based on actual battery voltage. Even so it seems that on the original scooter the driver sets by throttle required speed. Howard will check with IDH S&D what is the industry standard for electric scooter.
WW26 | Richy
WW26 | XD | Hu Teng | 2016.6.20 |  | 2 | 2 | Kinetis W | WirelessConnectivity/IoT |  |  |  | Design a demo mixing Thread and BLE in one application, compilation successed, initialization failed
WW26 | XD
WW26 | XD
WW26 | XD
WW26 | XD
WW26 | XD
WW26 | XD
WW26 | XD

## Apps Lead
Week | Team | Apps Engineer | Open Date | Close Date | Effort (man- days) | Total Effort | Family | Project | NPI Phase | Next Apps Milestone | TO Date | Enablement Task | Highlight/Lowlight/Issues/Risks | Progress record
WW26 | Sherry
WW26 | Sherry
WW26 | Sherry
WW26 | William
WW26 | William | Wang Hao | 2016-05-30 |  | 2 | 18.5 | Kinetis K | K4TV | Plan | Execution | July 21st | System Cases |  | Got Macronix SPI flash spec, plan to use their EVB for evaluating FlexSPI module; review QuadSPI driver in KSDK and check how much can be reused for FlexSPI.
WW26 | william | GuoJia | 2016-06-06 |  | 3 | 3 | Kinetis L | KL28 | Execution |  |  | Documentation - Application Notes |  | Finished the LPSPI use case test and draft for AN Using LPSPI on KL28.
WW26 | william | GuoJia | 2016-06-06 |  | 2 | 2 | Kinetis L | KL28 | Execution |  |  | Documentation - Others |  | Prepared and gave an online training for FAE team, the topic include the new feature on KL28. New features on system clock, LPSPI, SPI2C, FLEXIO are introduced in the training.
WW26 | william | Jia Ding | 2016-05-23 |  | 2.5 | 11.5 | Kinetis L | KL28 | Launching |  |  | Documentation - Application Notes |  | Modified the software package along with the FlexIO 8080 application note to make it compatible with KSDK 2.0.
WW26 | william | Jia Ding | 2016-06-24 |  | 0.5 | 0.5 | Kinetis L | KL28 | Launching |  |  | Training |  | Prepared the training slides on KL28Z FlexIO for FAE team.
WW26 | william
WW26 | Eric | Chen Yonggang | 2016-06-20 | 2016-06-24 | 3.5 | 3.5 | Kinetis E | KE15Z | Execution | TSI demo board building - 7/2 | Q4'15 | Alpha Customer Support |  | 1. Answered Jap FAE question on WDOG, why writing TOVAL when disable WDOG in system init. As mentioned in RM, the new configurations take effect only when all registers including TOVAL are written once after reset. 2. Answered Jap FAE question on ADC calibration about how to do when calibration failed 3. Got touch library 2.0 from Roznov team, and it can be released to alpha cutomer for testing. 4. Supported TSI EVB board building. Provided board vendor the parts that they don't have, and confirmed with PE that the 1.1 sample will be sent out on 7/1 for TSI EVB board building and FRDM 1.1 version hand soldering. 5. Korea FAE reported reset problem when ran the flash demo in Keil for Samsung home appliance, dual inverter module with KE14F512 project. Supported FAE solve the reset problem by moving the flash operation code into RAM. But met another flash error bit set problem when execute flash erase sector command, under debugging.
WW26 | Eric | Chen Yonggang | 2016-06-24 |  | 1 | 1 | Kinetis E | KE15Z | Execution | TSI demo board building - 7/2 | Q4'15 | System Cases-KPET |  | Started KPET development for TSI, LPTMR and LPIT module, 10% done.
WW26 | Eric | Ben Wang | 2016-11-23 |  | 3.5 | 77 | Kinetis E | MT512P | Execution | Execution | Q1'16 | System Engineering |  | 1.Core team agree to make MT512P move forward with max speed up to 168MHz instead of 160Mhz in high speed run mode.All the documents should be updated.Team will continue to monitor the yield on coming wafer lots. 2.HVP-KE18F FCC test is done and regarded as "pass" with a USB cable w/ Ferrite, no schematic and layout change on production board.Rozonv team reported one issue that if using the JTAG/SWD interface on board instead of OpenSDA USB, code download to KE18F will be failed. Did some tests on HVP-KE18F, but did not reproduce this issue. Later got feedback from them that they have resolved the issue and could download code now,there must be some problem with software drivers on their side. 3.Fixed one schemaitc symbol issue and layout lib issue on TWR-KE18F Rev A1, update TWR-KE18F to Rev B and upload to Agile, it will go for production build. 4.Collected and delivered all the peripheral adder source code to BACES team, support them finish the peripheral adder test cases. 5. IAR starts to look into the DAPlink download issue, they request two more boards(TWR-KE18F and FRDM-KE15Z) from us. The boards have been shipped out, pre-installed the DAPlink firmware. 6. For 64LQFP LU issue, IO ESD expert Michi does not require us to do the additional experiment on EVB. Add one de-cap between VDD and VSS meets the LU test spec.PE committed to do another test on 100LQFP package, but only 64 pins bond out, others keep floating. They want to use this to compare with the result of 64LQFP.
WW26 | Eric | Ben Wang | 2016-06-24 |  | 1 | 2 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | Studied the KPET on-line tool and template code, will start pre-coding and test on FRDM-KE15Z.
WW26 | Eric | Ben Wang | 6/23'2016 |  | 0.5 | 0.5 | Kinetis K | KS22F256N | Launching |  |  | Documentation - RM |  | Finish review the PDB chapter, provided about ~40 comments.
WW26 | Eric
WW26 | Eric
WW26 | Eric
WW26 | Richy | Howard Liu | 2015-07-16 |  | 1 | 98.5 | Kinetis E | MT512P | Execution |  | Q3'16 | System Cases |  | MT512P NPI: MT512P NPI: 1) Found the several potential replacements for the Op amps on the original 3in1 main boards that are obsolete. 2) PFC inductors are still manufactured and will be available for assembly later.
WW26 | Richy
WW26 | Richy
WW26 | XD
WW26 | XD
WW26 | XD
WW26 | XD
WW26 | XD

## Others
Week | Team | Apps Engineer | Open Date | Close Date | Effort (man- days) | Total Effort | Item | Segment | Family | Part | Module | Tools | Request brief | Overal Progress | Input Source
WW26 | Sherry
WW26 | Sherry
WW26 | Sherry
WW26 | Sherry
WW26 | William
WW26 | William | Wang Hao | 2016-06-22 |  | 0.5 |  | USB Type-C |  | Kinetis L |  |  |  | USB Type-C feasibility on Kinetis kick off | Top management need us to check USB Type-C feasibility on Kinetis as well as iMX, US team gave training on USB Type-C knowledge, this week will give us training on exact implementation on LPC MCU for USB Type-C and PD protocol. For Kinetis, we may need to port associated code for feasibility check.
WW26 | William
WW26 | William | YangXi | 2016-06-21 | 2016-06-24 | 3 | 3 | KSS Chinese Translation review |  |  | KS22F256N | CAN |  | Finish review FlexCAN part. | Translation quality is bad, totally 85 comments added.
WW26 | William
WW26 | William
WW26 | William
WW26 | William
WW26 | William
WW26 | William
WW26 | Eric
WW26 | Eric
WW26 | Eric
WW26 | Eric
WW26 | Richy | Li Shunan | 2016-06-06 |  | 0.5 | 4.5 | Support 2016 DFAE Training |  | DSC | MC56F82723 |  | CW10.6 | Prepare the lecture | Complete the lecture and slides about drone gimbal driver.
WW26 | Richy | Li Shunan | 2016-06-02 |  | 2 | 4 | Prepare for KV reference design and KV customer support |  | Kinetis V | MKV42F128VLH16 |  | IAR | Learn Cortex-M4 | Read some documents about Cortex-M4.
WW26 | Richy | Ethan Cheng | 2016-06-20 |  | 3 | 3 | Study Kinetis security MCU |  | Kinetis K | K81/KL81 |  |  | Study Kinetis security MCU | Study EMV contact software package and security material for K81/KL81. Visited Taiwan PoS customers with Donnie Garcia, systems engineer came from Austin for PoS solution promotion.
WW26 | Richy | Mao Huan | 2016-06-20 |  | 1 | 1 | Meeting with Vaclav |  | WCT |  |  |  |  | Had meeting with vaclav to review wireless charging project
WW26 | Richy | Zhou Xuwei | 2016-06-20 |  | 2 | 2 | DFAE Training preparation |  | Kinetis V | KV3x |  |  | KMS training for DFAE | Prepared the slides of KMS hands-on for DFAE training based on the FTF slides. Walked through some of the labs in the hands-on on FRDM.
WW26 | Richy | Gao Xiang | 2016-06-20 |  | 2 | 2 | DFAE Training preparation |  | DSC | MC56F82748 |  | CW10.6 | LLC training for DFAE | Prepared the slides of NXP solution of LLC design for DFAE training
WW26 | Richy | Mao Huan | 2016-06-22 |  | 2 | 2 | Solution team project review |  | WCT |  |  |  |  | Had 1-1 meeting with SteveSteven Tateosian; had meeting with solution team member to review project.
WW26 | Richy | Wang Li | 2016-06-20 |  | 0.5 | 0.5 | Meeting |  | WCT |  |  |  | Meeting with FAE from Czech | 1, Took part in the meeting with the FAE Vaclav, who from Czech Republic, discussing the wireless charging projects.
WW26 | Richy | Howard | 2016-06-21 | 2016-06-23 | 3 | 3 | Solution team project review |  | DSC |  |  |  |  | Prepared the slides for the motor control solution reference projects used for the prject review. Had 1to1 meeting with Steve; Had meeting with China solution team to review the projects in the energy conversion segment.
WW26 | XD | Liu weiping | 2016-06-13 |  | 2 | 7 | POS solution |  | i.MX |  |  |  |  | 1. Reading the yocto documents.
WW26 | XD | Yang Zhao | 2016-06-23 |  | 2 | 2 | Secruity |  | Kinetis K |  |  |  | Evaluate our secruity stack on M0+ | 1,Porting the code of our stack to kl43. 2. Test the project and get the flash and ram size used, record the encryption and decryption. 3.Finish the project and test,Then send the project and test result to Dawei.
WW26 | XD

## List_Def
Team | Segment | Family | Part | Customer Phase | Reference Phase | NPI Phase | Module | Tools | Root cause | Solution | Support Type | Source | Enablement Task
KM | Automotive | S08 | i.MX53 | Early Evaluation | Design | Concept | USB | KSDK | Ctm S/W defect | Fix - Erata/JIRA | General | FAE | Documentation - Data Sheet
Sherry | Consumer/Communication | CF | KM34Z64 | DI | Development | Feasibility | ADC | PEx | Ctm H/W defect_D | Workaround | Key | BD_MKT | Documentation - Errata
Manish | Industry | DSC | KM34Z256 | DW | Integration | Plan | I2C | MQX | EMC | Customization | Professional Service | NPI_MKT | Documentation - RM
Lily | eReader | Kinetis L | KM34Z128 | Pilot | Reference Release | Execution | SPI | Linux | Design issue | Demo/Reference | Leverage | Sales | Documentation - Application Notes
Robin | Security | Kinetis E | KL17 | MP | SoW | Launching | TSI | Android | Design limitation | Benchmark | BD Activity | Unknown | Documentation - Others
Richy | Wireless Charger | Kinetis M | KM14Z64 | DL | Lib Release |  | AFE | WinCE | RM defect |  |  | CQI | System Cases
William | Motor Control | Kinetis V | ​MK60DN512 |  | Documentation |  | GPIO | CW10.6 | DS defect |  |  |  | System Engineering
Eric | Digital Power | Kinetis K | MC56F82313 |  | Testing |  | ENET | IAR | System improvement |  |  |  | Board - Design
XD | WirelessConnectivity/IoT | Kinetis X | MC9S08PT16AVLD |  |  |  | QTimer |  | Driver issue |  |  |  | Board - FAT Coding & test
| Smart Grid | Kinetis W | MK64FN1M |  |  |  | JTAG |  | Ref board issue |  |  |  | Board - Document
| Industry-Touch | i.MX | MWCT1012CFM |  |  |  | FLASH |  | New Requirement |  |  |  | Certification - USB
| Industry-HomeAppliance | WCT | MKE02Z32 |  |  |  | UART |  | SW issue |  |  |  | Certification - Others
| Power | WCR | MC56F82723 |  |  |  | I2S | [5 empty] | Training
|  |  | MC9S08SD8 |  |  |  | DAC | [5 empty] | Alpha Customer Support
|  |  | KL16Z128 |  |  |  | FlexIO | [5 empty] | Tools Support
|  |  | KE18Z |  |  |  | LPIT | [5 empty] | Bug analysis support
|  |  | MKV10Z32VFM7 |  |  |  | LPTimer | [5 empty] | SDK Driver
|  |  | KE18F512VLL15 |  |  |  | LPTPM | [5 empty] | System EMC
|  |  | MC56F84789 |  |  |  | Flextimer | [5 empty] | System Cases-KPET
|  |  | MC9S08PA16AVWJ |  |  |  | PWT | [5 empty] | System Cases-BLDC demo
|  |  | MT512P |  |  |  | PDB | [5 empty] | System Cases-Peripheral adder
|  |  | KE15Z |  |  |  | PIT
|  |  | KL17Z32VFM4 |  |  |  | eFlexPWM
|  |  | MC9S08SU16 |  |  |  | DMA
|  |  | i.MX6RT |  |  |  | WDOG
|  |  | KW41 |  |  |  | EWM
|  |  | K81/i.MX6UL |  |  |  | SIM
|  |  | KE06 |  |  |  | MCG
|  |  | KL02 |  |  |  | SCG
|  |  | KS22F256N |  |  |  | OSC
|  |  | K81 |  |  |  | ICS
LLWU
RCM
PMC
SMC
SAI
RTC
CRC
CAN
ESDHC
ACMP
VREF
DryICE
RNGA/TRNG
CMT
QDecoder
AMP
DDR
LCD
KBI
FlexNVM
IRQ
FlexBus
CM0+
CM4
CACHE
OPAMP
bootROM
Radio
Note on L2: Author: General Customer Support
Note on L3: Author: Key Customer Support
Note on L4: Author: Professional Service
Note on E5: Author: pre mass production
Note on L5: Author: Leverage to general base from customer support
Note on N8: support enablement tools such as register header files validation, debugger svd file validation and etc
Note on N9: support PE/design to do bench test on bugs