## Customer Support
Week | Team | Apps Engineer | Effort (man- days) | Total Effort | Segment | Customer | Family | Part | Customer Phase | MP Date | Product | LTR ($M) | GIBC | Module | Tools | Request brief | Progress record | Root cause | Solution | Support Type | Input Source | Community Link (Mandatory)
WW28 | Sherry
WW28 | Sherry
WW28 | Sherry
WW28 | Sherry
WW28 | Sherry
WW28 | William
WW28 | William | Wang Hao | 2 | 2 | Security | Landi | Kinetis K | MK81 | DI | 2016-12-20 | MPOS-LD6 | 1.112 | 1-20SLJID | bootROM | IAR | FAE reported problem with both plaintext image boot and encrypted image download with KBOOT and requested help. | FAE reported after downloading plaintext image with KBOOT to external QuadSPI flash, it cannot boot unless pressing reset button for manually reset board. He suspects this might be related to timing problem for KBOOT. Tried same steps on K80 tower board but cannot reproduce the issue FAE met. FAE also reported problem to download encrypted image to external QuadSPI and read back programmed keys at IFR address 0x20. Confirmed the same behavior on K80 tower board, later found failure to read key back at IFR address 0x20 is right behavior specified in K8x RM to keep those keys read back by hackers. And the security download feature only works on K81 or K82 which has LTC module, tower board has K80 silicon so cannot support this feature. Ask FAE to try with Freedom K82 board. |  |  | Key | FAE (Fred Fu) | https://community.nxp.com/message/808372 https://community.nxp.com/message/808288
WW28 | William | Wang Hao | 0.5 | 0.5 | Consumer/Communication | Microsoft | Kinetis K | MK60 | MP | [6 empty] | Customer reported big failure rate for oscillator output waveform level and request us investigate. | Pegatron Suzhou reported big failure rate (270 out of 650) for 8MHz external crystal waveform level. Expected waveform level is 1.1V from previous batch samples, while for current batch sample, output waveform level is only 0.89V which is less than their set threshold level (0.9V) for failure. Had meeting with Pegatron engineer to know detailed information for failure, requested to get board schematic for crystal connection and MCG initialization code. |  |  | Key | FQE (YiMeng Zou)
WW28 | william | Zhong Juying | 0.5 | 0.5 | Security | WuhanTianyu | Kinetis K | MK21D | DI |  | mPOS |  |  |  |  | customer reported a questions on VDDA, VDD1, VDD2 and VDD3 which of them is powered for mmCAU module. | searched materials and checked power supply with designer, sent the result to customer as below: VDD1, VDD2 and VDD3 don't supply different internal blocks inside the chip, they creates the internal power mesh inside the chip to power the whole chip and actually MMCAU is powered by internal 1.2v, generated by internal regulator through 3.3v VDD from external. to be exact, VDD1, VDD2 and VDD3 power the internal regulator, and the internal regulator power the mmcau. | Ctm H/W defect_D | Demo/Reference | General | FAE (He Ciang)
WW28 | william
WW28 | william | Jia Ding | 1 | 1 | Industry | oplink | Kinetis K | MK20DX256ZVMC10 | DI |  |  |  |  | ADC |  | FAE reported customer's 4 of the 20 prototype products have issue with the ADC results. | Analyzed the issues and provide some suggestions on community. Asked the FAE to provide more information. Still waiting for the feedback. |  |  | General | FAE(He Ciang) | https://community.nxp.com/message/808434
WW28 | William
WW28 | William | YangXi | 0.5 | 0.5 | Consumer/Communication | ScanWorld | Kinetis K | K81 | Early Evaluation | [6 empty] | Early evualation of QR decoder | Introduce our QR decoder demo to customer, customers interested in our solution and want to do evaluation. 1. Give customer QR adapter board schematic. 2. Customer will use their own camera module(Hi704) and modify adapter schematic to fit their system. |  |  | General | FAE(May Li) | https://community.nxp.com/message/810346
WW28 | William
WW28 | William
WW28 | William
WW28 | Eric | Shi Changhao, Terry Lv | 4 | 29 | WirelessConnectivity/IoT | LG/VW | Kinetis W | KW41 | Early Evaluation |  | Car BLE/WIFI Dual Anteana System | 12M |  | Radio | IAR | Customer request to have a technical data sheet on BLE power consumption of KW41 | test the RF_ACTIVE signal output in the RF ADV period and found that there is timing issue for this signal which will impact the RF coexistence use case. the RF coexistence use case is the must feature for LGE. At the same time, report the issue to design team, and they feedback that this bug is fixed by K3S. | Design issue | Fix - Erata/JIRA | General | FAE(Thomas Kang) | https://community.nxp.com/message/665311
WW28 | Eric
WW28 | Eric
WW28 | Eric
WW28 | Eric
WW28 | Eric
WW28 | Eric
WW28 | Richy | Zhong Ji | 1 | 223.5 | Motor Control | Deye | DSC | MC56F84789 | DI |  | VF Air-conditioner | 10 | 1-1S40I05 |  | CW10.6 | 3in1 soluiton of outdoor A/C unit | Deye 3in1 transfer have been completed by the end of last week, including compressor control 3 libraries and related code and report. Sutter and Howard reviewed the projects and give some revising suggestions. The revision version will be completed next week. |  | Customization | Key | FAE (Zhuang Chao-B50031)
WW28 | Richy | Richy Ye, Wang Lingling | 0.5 | 52 | Digital Power | Artesyn Philippines | DSC | MC56F82748 | Early Evaluation |  | Digital power development platform |  |  |  |  | Tool box for automatic code generation from MATLAB | Started to write the documentation about automatically code generation. | New Requirement | Customization | Key | FAE(Andrey Eng - B43125)
WW28 | Richy | Richy Ye, Jiang Dengyu, Mao Huan | 3.5 | 64.5 | Wireless Charger | LGIT | WCT | MWCT1111CLH | DW |  | 15W 1COIL TX | $1.70 | 1-FFWPV2 |  | CW10.6 | Customer want a solution of WPC+PMA based on WCT1111 | 1. As LGIT’s requirements, comparison tests are done on LGIT-Belkin board with different step-down ICs(MP2315 vs MP1498). According to the test results, MP1498 produced lower ripple voltage on V3.3 and leaded to better DDM performance. However MP1498 had no AAM mode and consumed higher standby current. The test results are summarized in a document and sent to LGIT for reference. 2. Checked LGIT calibration issue: Sent NXP elf file , which can work well to customer for check, it worked well on customer's side; found that the issue is caused by their modification of application code and now has been fixed, the calibration could be done normally. | New Requirement | Customization | Key | FAE (Kate Lee - B45752)
WW28 | Richy | Jiang Dengyu, Wang Li, Wang Dechang | 1 | 45.5 | Wireless Charger | PLDS | WCT | WCT1001A | Early Evaluation |  | 15W_TXAUTO |  |  |  | CW10.6 | Support customer debug. | 1,Debugged PLDS 15W AUTO TX board under half-bridge topology. After optimizing, PLDS board can load 3A gradually with MP RX BUCK board and 2A gradually with MP RX LDO board. | New Requirement | Customization | General | FAE (Beta Chen - B44998)
WW28 | Richy | Zhao Ping | 5 | 38.5 | Wireless Charger | Delphi China | WCT | WCT1001A | MP | 2016.3 | 5W Automotive Power Transmitter |  | 1-UXG1IX |  |  | CAN debug issue | 1, Merge RS FOD code to GA3.3, 1jiao coin and 1yuan coin can be detected, 5jiao coin can be detected at the overlap area. Sent the code to customer for test; 2, Customer requested to merge RS FOD code to her project. Merged and sent it.; 3, Customer reported that RS FOD was triggered when some RX placed on the surface of TX. I checked it and found the detection numbers were not enough, so RS FOD was triggered before RX sending the SS packet. I increased the detection numbers and sent it to customer for test. | New Requirement | Customization | General | FAE (Yu Ningning - B45276)
WW28 | Richy | Ding Wenshuang, Zhou Xuwei | 2 |  | Motor Control | Little Swan | DSC | MC56F82723 | Early Evaluation |  | BPM Wash machine |  |  |  | CW10.6 | Load test for BPM wash machine | Modified the motor parameters and tested the project with load in Suzhou lab based on the customer's BPM motor. 1, Heavy unbalance load test: Motor can startup sucessfully every time with heavy unbalance load.The lowest speed can be up to 250rpm. Found one issue that in low speed range (250rpm) the motor stalls one time beacuse the load is stuck, but no fault issue reported. 2, Motor runs well in 14000rpm with empty drum. increase d axis reference current will improve the low-speed Dynamic performance. | New Requirement | Customization | General
WW28 | Richy | Ding Wenshuang | 1 | 3 | Motor Control | Little Swan | DSC | MC56F82723 | MP |  | ACIM wash machine | 0.8 | 1-1Y288OT |  | CW10.6 | Help to solve the issue in MP state | Customer report one issue that the current surge occurred in the startup state, by researching the startup waveform,it might caused by startup when the rotor is still rotating. FAE will onsite support the customer this week. | New Requirement | Customization | General | FAE larry yang
WW28 | Richy | Ethan Cheng | 2 | 2 | Security | iBase | Kinetis K | K81F150M | DI |  | NFC card reader | $ 0.108 M | 1-23HE2Y9 |  | KSDK | Provide NFC and contact reader solution with Kinetis K81F150M for iBase | Visited Acer who is the end customer of iBase to discuss design requirements and cooperation model. NXP will provide NFC (PN5180) and contact reader (TDA8029) solution for Kinetis K81F150M, iBase is responsible for hardware manufacture, and Acer will take care the payment application. Supported NFC software porting into KSDK2.0 for K81F150M so far. | New Requirement | Customization | General | FAE (David Chen - B36932)
WW28 | Richy | Richy Ye, Wang Lingling | 1.5 | 7 | Digital Power | Huawei | DSC | MC56F82733 | DI |  | Board Mounted Power | 3.11 | 1-LR7IQU |  |  | Example code and design guidance | 1, It turns to design in. Customer has at least one board can work with CW smoothly now, the ADC and PWM also works on the board as well, will complete all components assembly for system debugging later. 2, Completed the example code and design guidance about input voltage zero-crossing detection, and phase error detection for software PLL, and sent it to customer for reference. | New Requirement | Customization | Key | FAE (Roger Fan - R30375)
WW28 | Richy | Gao Xiang, Richy Ye | 1.5 | 2 | Wireless Charger | HTC | WPR | WPR1516 | Early Evaluation |  | 15W power receiver for mobile |  |  |  |  | Prototype development | Reviewed the customer schematic for dual-mode (Qi and A4WP) 10W RX, and provided comments about Qi system design, MWPR1516 pin assignment, and relative pin signals interface design for revise. Finally, GPIO simulated IIC is recommended for another two weeks effort because IIC pins are occupied by single wire mode UART. | New Requirement | Customization | General | FAE (Beta Chen - B44998)
WW28 | Richy | Richy Ye, Zhou Xuwei, Ding Wenshuang | 0.5 | 0.5 | Motor Control | Changhong | DSC | MC56F827xx | Early Evaluation |  | Washing machine |  |  |  |  | Solution introduction and technical discussion | Customer setup one team to develop washing machine solution. Had conf. call with customer R&D to introduce NXP VF washing machine motor control solutions and answer customer concerns/questions. Seems customer hasn't too much experience on washing machine development, will follow up if there is opportunity to cooperate in near future. | New Requirement | Customization | General | Sales (Zhang Yuan)
WW28 | Richy | Kevin Cheng | 0.5 | 1 | Digital Power | GE Energy | DSC | MC56F82748 | Early Evaluation |  | Interleaved Full bridge converter |  |  |  |  | PCCM evaluation | Customer accept we use half bridge driver to minimize DSC pinout, But the control of two full-bridge converter with SR is still challenge to AngSilver. The limitation is peak current control of two full-bridge converters need two DAC peripherals. the only availabe options are AngSilver and KV3x. |  | Customization | BD Activity | FAE (Cherrish liao-R65774)
WW28 | Richy | Kevin Cheng | 3 | 10.5 | Digital Power | Huntkey Shenzhen | DSC | MC56F84786 | DI |  | 15KW LLC converter |  | 1-22EBZJW |  |  | abnormal pwm behavior | Supported customer debugging HB shorted PWMs, there're two root causes generate the abnormal pwm behavior. 1) When the dithered Valn content same with Val1, it generates abnormal output when Val1 less than Valn. 2) External synchonized pwm module's Valn breakdown when it equals Val1. | Design issue | Workaround | General | FAE (Roger Fan - R30375)
WW28 | Richy | Gao Xiang, Wang Peng | 1.5 | 2 | Digital Power | Delta Shanghai | DSC | MC56F84543 | DW |  | Telecom Power |  |  |  |  | Latch up issue when ESD test or power on at short time after power off | Visit Delta together with TC for the MC56F84543 ESD/HOT PLUG latch up issue, detail analysis the voltage power up sequence, chip programming process, the connection of unused GPIO and other DSC external connection circuits. Provide up to 11 suggestions for customer to optimize their design, but customer's attitude is not very positive and not willing to attempt all these suggestions. |  | Workaround | General | FAE(Moris Hsu)
WW28 | Richy
WW28 | Richy
WW28 | XD | Liu weiping | 1 | 1 | Security | 联迪 |  | K81 | DW | [6 empty] | 1. Fixed the issue of RSA encrpyt/decrypt failure. (RSA operation would be failed when it used keys by the key-generator function)
WW28 | XD | Liu weiping | 2.5 | 2.5 | Smart-POS | 寰果 |  | K81 | DW | [6 empty] | Customer report an issue that some times the evml1 driver will lost one byte in receiving. But if it not use the mutil-task then this issue will not be occurred. At last, we changed the emvl1 task to top levle prior and fixed this issue.
WW28 | XD | Chu Hongdong | 4 | 34 | ePOS/Security | Landi | i.MX | i.MX6UL |  |  | ePOS | 500K | #1-1PPBZ7A | HAB,CAAM,SNVS,Dryice,BEE | Yocto | Implement security features. | Reworked i.MX6UL EVK board and reproduced the issue that SNVS LP module is reset during system power down/up under some conditions. The issue reported by Landi that system halts during stress testing is caused by RTIC watchdog error , have updated the RTIC timeout value to Landi. |  | Customization | Key
WW28 | XD
WW28 | XD
WW28 | XD
WW28 | XD
WW28 | XD
WW28 | XD
WW28 | XD

## Reference Design
Week | Team | Apps Engineer | Open Date | Close Date | Effort (man- days) | Total Effort | Family | Segment | Project | Reference Phase | Milestone Date | Progress record
WW28 | Sherry
WW28 | Sherry
WW28 | Sherry
WW28 | William | Zhong Juying | 2016-06-06 |  | 2.5 | 2.5 | Kinetis L | Security | RSA & ECC with DPA countermeasure | Development |  | 1.improve blinding method on RSA countermeasure as below: 1.1 did some try on an improved blinding method. blinding message and spliting exponent(E1, E2, .... En), then calculated mod_exp for E1 to En. ----- Done 1.2 implemented a policy for randomly inserted dummy exponent. ---- Done 1.3 implemented a policy for recoverying the real result of mod_exp. ---- Done 1.4 will continue to do debug and testing ---- on-going
WW28 | William
WW28 | William
WW28 | William | YangXi | 2016-04-07 | 2016-06-07 | 2 | 113 | Kinetis K | Industry | QR decoder | Lib Release |  | 1. LanDi begin to evaluate QR decoder solution and they need to use SDRAM. Update the qr_decoder_sdram project to support latest decoder library and camera.(Hi708). Complete and send to FAE. 2. Draft an QR decoder induction PPT for sales & customers.
WW28 | William
WW28 | William
WW28 | William
WW28 | William
WW28 | William
WW28 | William
WW28 | William
WW28 | Eric | Shi Changhao,Terry Lv | 2015-11-16 |  | 4 | 129 | Kinetis W | WirelessConnectivity/IoT | Smart Home With KW41 | Development |  | 1,Continue to code on our sensor tag application. 2, Evaluate application on mobile side. 3, Inivestigate the BLE smart lock applciation.
WW28 | Eric
WW28 | Eric
WW28 | Eric
WW28 | Eric
WW28 | Eric
WW28 | Richy | Richy Ye, Wang Dechang, Jiang Dengyu, Kevin Cheng, Gao Xiang, Wang Lingling | 2015-03-23 |  | 4 | 204 | DSC | Digital Power | Golden Server Power | Design |  | 1,Fixed the difference between two boards and tested the new designed parameters in them, the effect is similar. 2,Analyzed the difference between discrete and integrated transformer LLC, found the defects of the main circuit parameter design. In the first version, using the wrong gain function makes the choosed Qe value too small, in the second version, the nominal condition is not designed to work in resonant frequency and the design margin is too small. 3, Submit the DRM on DOC tracker for document team to edit.
WW28 | Richy | Gao Xiang | 2015-02-01 |  | 1 | 189 | WCR | Wireless Charger | WPR1500 LDO/BUCK MPRX | Development |  | Continue to build FreeMASTER GUI of receiver side, complete the current and voltage calibration in GUI.
WW28 | Richy | Wang Dechang, Zhang Yangjie, Richy Ye, Gao Xiang, Wang Lingling | 2015-08-06 |  | 6 | 437 | DSC | Digital Power | Golden Server Power-Totem Pole BLPFC | Design |  | 1， continued the new SW structure design, the basic function is OK under 90Vac input and 250V output, performance is OK, but found one issue, that hte PWM duty will be 100% at some time, this will cause the over current, and this problem is under debugging. 2,Continued to calculation sheet edit, completed the out voltage loop calculation, ahte result is almost same with the testing.
WW28 | Richy | Jiang Dengyu, Mao Huan, Richy Ye | 2014-10-04 |  | 3 | 481 | WCT | Wireless Charger | WCT-15W1COLTX | Development |  | Realized ADC limit protection but it couldn't work real time; then used comparator to realize maximum voltage protection instead, the testing is ongoing.
WW28 | Richy | Liu Zhen, Ding Wenshuang, Zhou Xuwei | 2016-03-10 |  | 4 | 43 | S08 | Motor Control | SU16-Edrone | Development |  | 1,Continue to debug the startup fault issue, finally we selected the method that shift to closed loop state after one openloop startup vector, and also added restart mechanism if can't detect BEMF zero-crossing point in 120°, now the ESC can sucessfully startup every time,But sometimes the fan blades shaked several times because of the restart mechanism. 2,Found one issue that we must add about 800pF capacitance on the BEMF signal or it can't work,but there is no capacitance in the SD8 EVB board, root cause is under debugging.
WW28 | Richy | Wang Dechang, Jiang Dengyu, Wang Li | 2015-11-25 |  | 1.5 | 57 | WCT | Wireless Charger | WCT-15WTXAUTO | Design |  | 1. Checked the PCB EQ documents and gave comments to PCB manufacturer, now PCB board production is ongoing; 2. Checked the alternative parts list and gave comments。
WW28 | Richy | Wang Dechang, Jiang Dengyu, Wang Li, Richy Ye | 2015-03-02 |  | 5 | 208 | WCT | Wireless Charger | WCT-15WTXMULTI | Design |  | 1, NXP 15W consumer multi-coil power transmitter solution is accepted as MP-A8 by WPC. Completed the v1.2.2 specs addendum for MP-A8, now it's on WPC SWG review for final release review, target to release on WPC web at the end of July. 2, Tested and repaired all the WCT1111 boards, prepare for the new release and QI compliance test. 3, Debugged the DDM performance issue. Tx can't decode well when charging Rx with DCR mode, it is believed to be caused by the ripple from buck IC. By changing the IC chip, the VCC is more stable than before, and the DDM performance is much better. 4, Prepare for the 2.0 release. Debugged the Q factor measurement issue. With the new library, the Q factor can't be measured correctly, it is found to be caused by some logic errors, and the incorrect calibration parameters, after these updates, the Q factor measurement can work well; Debugged the RX quick removal function, since the control logic is quite different from A13, the function need to be otimized, now it is still under debug.
WW28 | Richy | Howard Liu, Richy Ye | 2014-09-20 |  | 1 | 53.5 | DSC | Motor Control | Sensorless FOC e-Sooter -MC56F82728 | Development |  | PM, h/w and application s/w status: 1) The Xiaoniu M1 eScooter arrived in the Warsaw customs. The Europe agent needs some documents for custom clearance and called Roznov team but no answer since Roznov team was in holiday last week. Contacted the agent and asked them to wait their back office. 2) Asked IDH to expedite the new board manufacturing. MC software status of development and test (From Roznov team): No update due to holiday in Roznov.
WW28 | Richy
WW28 | Richy
WW28 | Richy
WW28 | XD
WW28 | XD
WW28 | XD
WW28 | XD
WW28 | XD
WW28 | XD
WW28 | XD
WW28 | XD

## Apps Lead
Week | Team | Apps Engineer | Open Date | Close Date | Effort (man- days) | Total Effort | Family | Project | NPI Phase | Next Apps Milestone | TO Date | Enablement Task | Highlight/Lowlight/Issues/Risks | Progress record
WW28 | Sherry
WW28 | Sherry
WW28 | Sherry
WW28 | William | Jia Ding | 2016-06-29 |  | 1 | 2.5 | Kinetis L | L5K | Launching |  |  | System Engineering |  | Measured current adder of RTC and LPTMR, and added code that used to wake up the device from VSS1 to make sure the IP running normal in the low power mode. The results seem normal and much smaller than baces team's results. Aligned within team and asked for baces team to measured again.
WW28 | William | GuoJia | 2016-07-04 |  | 0.5 | 0.5 | Kinetis L | KL28 | Execution |  |  | Certification - USB |  | 1.Prepare the FRDM-KL46 board for eye-diagram test. The test are planned to be finished in 7/11. 2.As the Allion engineer was in PTO last week, the test is delayed. They promised to give us the test report on 7/15.
WW28 | William | Guo Jia | 2016-07-04 |  | 4.5 | 4.5 | Kinetis L | L5K | Launching |  |  | System Engineering |  | Make LPSPI use case for multi-IO mode. Found one issue that in continuous mode, the dummy signal given out by LPSPI is not correct. Now I am waiting for design to clarify on it. Another issue I found is, when connecting to flash, and read a page in multi-IO mode, the output from SPI flash is not correct. I have contacted the engineer from the SPI flash company for help.
WW28 | william | Wang Hao | 2016-05-30 |  | 1 | 20.5 | Kinetis K | K4TV | Plan | Execution | Aug 11st |  |  | K4TV tapeout date delayed due to other project tapeout delay, new tapeout date being 8/11.
WW28 | william
WW28 | william
WW28 | william
WW28 | william
WW28 | Eric | Chen Xinyu, Lv Terry | 2016-05-08 |  | 0.5 | 0.5 | Kinetis K | KS22F256N | Launching |  |  | Documentation - RM |  | Reviewed the revised RM Part2 from 3rd Party based on our comments. There's still some comments not updated into this version, asked Vicky to check again.
WW28 | Eric
WW28 | Eric | Ben Wang | 2016-11-23 |  | 2 | 81 | Kinetis E | MT512P | Execution | Documentation -- TWR user guide and AN | Q1'16 | Board - FAT Coding & test |  | 1.Finish OOBE/FAT coding and FSW document. 2.Reviewed and provided comments on TWR and HVP board QSG.Preparing writing the TWR user guide and AN of "Kinetis migration guide from KE0x to KE1x" next. 3.PE did the 100LQFP LU test with only stress the same pins/pads as LQFP64, the result is the same as LQFP64, it will still fail w/o de-cap between VDD and VSS.Michi suggest to do further tests to add back the power supply pins to see the difference.
WW28 | Eric | Ben Wang | 2016-06-24 |  | 3 | 8 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | 1.Finish coding and testing FlexIO UART KPET use case.
WW28 | Eric | Chen Yonggang | 2016-06-29 |  | 2 | 4 | Kinetis E | KE15Z | Execution | KPET ready on 7/15 | Q4'15 | Board - OOBE |  | 1. Finished FRDM-KE15Z OOBE code. 2. Finished 43pcs FRDM-KE15Z board manual resoldering with 1.1 KE15Z samples. Provided FSW/FAT files and DAP-LINK firmware for board factory test, and found DAP-LINK drag/drop issue on 20pcs boards while the other 20pcs board without this issue. The root cause is under debugging.
WW28 | Eric | Chen Yonggang | 2016-06-24 |  | 1 | 3 | Kinetis E | KE15Z | Execution | KPET ready on 7/15 | Q4'15 | System Cases-KPET |  | Finished LPTMR KPET code development, and developing TSI and LPIT.
WW28 | Eric | Chen Yonggang | 2016-07-08 | 2016-07-08 | 1 | 1 | Kinetis E | KE15Z | Execution | KPET ready on 7/15 | Q4'15 | System Engineering |  | 1. Submitted a ticket (TKT307951) in DesignPDM to improve ADC block guide on calibration chapter. 2. All chip level PESD testing on 1.1 sample are completed, the test result shows that the positive PESD damage level is +8KV and the negative PESD damage level is around -6KV.The 1.1 sample test result is much better than the previous 1.0 sample.
WW28 | Eric
WW28 | Richy | Howard Liu | 2015-07-16 |  | 3 | 102.5 | Kinetis E | MT512P | Execution |  | Q3'16 | System Cases |  | MT512P NPI: 1) Created the new workspace with new folder structure to remove the independence on the KSDK release. All references to the macros defined in the xxx_extension.h files were removed since this head file will not be provided in the SDK any more. Finished the code porting to use the KSDK2.0 head files.
WW28 | Richy
WW28 | Richy
WW28 | XD
WW28 | XD
WW28 | XD
WW28 | XD
WW28 | XD

## Others
Week | Team | Apps Engineer | Open Date | Close Date | Effort (man- days) | Total Effort | Item | Segment | Family | Part | Module | Tools | Request brief | Overal Progress | Input Source
WW28 | Sherry
WW28 | Sherry
WW28 | Sherry
WW28 | Sherry
WW28 | William | Zhong Juying | 2016-07-05 | 2016-07-07 | 2 | 2 | Donnie Garcia wanted to got a document that explains how he did the DPA hardening for the software algorithm like as "mmcau_des_sw_dpa_overview.pdf", because a customer met problems on passing DPA testing | Security | Kinetis K | MK21F |  |  | Donnie Garcia wanted to got a document that explains how he did the DPA hardening for the software algorithm like as "mmcau_des_sw_dpa_overview.pdf", because a customer met problems on passing DPA testing | 1. analyzed and pointed out those problems of mmcau library with DPA based on "mmcau_des_sw_dpa_overview.pdf". 2. re-wrote a overview document named "pure_sw_des_countermeasure_overview.doc" for Donnie Garcia's requirement. 3. prepared and delivered a porting guide code for PCI SCA testing to Donnie Garcia. | Donnie Garcia
WW28 | William
WW28 | William
WW28 | William
WW28 | William
WW28 | William
WW28 | William
WW28 | William
WW28 | William
WW28 | William
WW28 | Eric | Chen Xinyu | 2016-07-07 | 2016-07-08 | 0.5 | 0.5 | Reviewed the KE1x Web training slides of LPIT/LPSPI/LPUART comments from marketing. All the comments are good and accepted. |  | Kinetis E |  | LPIT |  |  | All the training slides for KE1x assigned to me are done.
WW28 | Eric
WW28 | Eric
WW28 | Eric
WW28 | Richy | Li Shunan | 2016-06-02 |  | 3 | 7 | Prepare for KV reference design and KV customer support |  | Kinetis V | MKV42F128VLH16 |  | IAR | Learn TWR-KV10 and TWR-KV46 | Demo some example codes on TWR-KV10 and TWR-KV46 based on IAR IDE environment. Flash an universal firmware into the K20 of TWR-KV46 on my hand.
WW28 | Richy | Liu Zhen, Ding Wenshuang, Zhou Xuwei, Richy Ye | 2016-07-05 | 2016-07-05 | 1 | 1 | Review ESC drone schematic |  | Kinetis V | MKV30F64VFM10 |  |  | Review ESC drone schematic for ZLG | Supported customer to review the two versions drone FOC ESC solutions schematics on KV30, provided comments for schematics optimization and customer questions.
WW28 | Richy | Wang Li | 2016-07-07 |  | 0.5 | 0.5 | Visa application | [5 empty] | Applicate the Visa | Prepare the application douments for Visa to Korea.
WW28 | Richy | Richy Ye, Kevin Cheng, Ethan Cheng, Gao Xiang | 2016-01-01 |  | 0.5 | 4.5 | Digital power customer issues review | Digital Power |  |  |  |  | Bi-weekly review digital power customer issues with FAEs | Review digital power customer issues with FAEs, provide action/answer/advice for all open issues.
WW28 | Richy
WW28 | Richy
WW28 | Richy
WW28 | Richy
WW28 | Richy
WW28 | XD | Liu weiping | 2016-06-13 |  | 1.5 | 11.5 | POS solution |  | i.MX |  |  |  |  | 1. Start coding an EMV contact card application on imx6ul.
WW28 | XD

## List_Def
Team | Segment | Family | Part | Customer Phase | Reference Phase | NPI Phase | Module | Tools | Root cause | Solution | Support Type | Source | Enablement Task
KM | Automotive | S08 | i.MX53 | Early Evaluation | Design | Concept | USB | KSDK | Ctm S/W defect | Fix - Erata/JIRA | General | FAE | Documentation - Data Sheet
Sherry | Consumer/Communication | CF | KM34Z64 | DI | Development | Feasibility | ADC | PEx | Ctm H/W defect_D | Workaround | Key | BD_MKT | Documentation - Errata
Manish | Industry | DSC | KM34Z256 | DW | Integration | Plan | I2C | MQX | EMC | Customization | Professional Service | NPI_MKT | Documentation - RM
Lily | eReader | Kinetis L | KM34Z128 | Pilot | Reference Release | Execution | SPI | Linux | Design issue | Demo/Reference | Leverage | Sales | Documentation - Application Notes
Robin | Security | Kinetis E | KL17 | MP | SoW | Launching | TSI | Android | Design limitation | Benchmark | BD Activity | Unknown | Documentation - Others
Richy | Wireless Charger | Kinetis M | KM14Z64 | DL | Lib Release |  | AFE | WinCE | RM defect |  |  | CQI | System Cases
William | Motor Control | Kinetis V | ​MK60DN512 |  | Documentation |  | GPIO | CW10.6 | DS defect |  |  |  | System Engineering
Eric | Digital Power | Kinetis K | MC56F82313 |  | Testing |  | ENET | IAR | System improvement |  |  |  | Board - Design
XD | WirelessConnectivity/IoT | Kinetis X | MC9S08PT16AVLD |  |  |  | QTimer |  | Driver issue |  |  |  | Board - FAT Coding & test
| Smart Grid | Kinetis W | MK64FN1M |  |  |  | JTAG |  | Ref board issue |  |  |  | Board - Document
| Industry-Touch | i.MX | MWCT1012CFM |  |  |  | FLASH |  | New Requirement |  |  |  | Certification - USB
| Industry-HomeAppliance | WCT | MKE02Z32 |  |  |  | UART |  | SW issue |  |  |  | Certification - Others
| Power | WCR | MC56F82723 |  |  |  | I2S | [5 empty] | Training
| Smart-POS |  | MC9S08SD8 |  |  |  | DAC | [5 empty] | Alpha Customer Support
|  |  | KL16Z128 |  |  |  | FlexIO | [5 empty] | Tools Support
|  |  | KE18Z |  |  |  | LPIT | [5 empty] | Bug analysis support
|  |  | MKV10Z32VFM7 |  |  |  | LPTimer | [5 empty] | SDK Driver
|  |  | KE18F512VLL15 |  |  |  | LPTPM | [5 empty] | System EMC
|  |  | MC56F84789 |  |  |  | Flextimer | [5 empty] | System Cases-KPET
|  |  | MC9S08PA16AVWJ |  |  |  | PWT | [5 empty] | System Cases-BLDC demo
|  |  | MT512P |  |  |  | PDB | [5 empty] | System Cases-Peripheral adder
|  |  | KE15Z |  |  |  | PIT | [5 empty] | Board - OOBE
|  |  | KL17Z32VFM4 |  |  |  | eFlexPWM
|  |  | MC9S08SU16 |  |  |  | DMA
|  |  | i.MX6RT |  |  |  | WDOG
|  |  | KW41 |  |  |  | EWM
|  |  | K81/i.MX6UL |  |  |  | SIM
|  |  | KE06 |  |  |  | MCG
|  |  | KL02 |  |  |  | SCG
|  |  | KS22F256N |  |  |  | OSC
|  |  | K81 |  |  |  | ICS
LLWU
RCM
PMC
SMC
SAI
RTC
CRC
CAN
ESDHC
ACMP
VREF
DryICE
RNGA/TRNG
CMT
QDecoder
AMP
DDR
LCD
KBI
FlexNVM
IRQ
FlexBus
CM0+
CM4
CACHE
OPAMP
bootROM
Radio
Note on L2: Author: General Customer Support
Note on L3: Author: Key Customer Support
Note on L4: Author: Professional Service
Note on E5: Author: pre mass production
Note on L5: Author: Leverage to general base from customer support
Note on N8: support enablement tools such as register header files validation, debugger svd file validation and etc
Note on N9: support PE/design to do bench test on bugs