## Customer Support
Week | Team | Apps Engineer | Effort (man- days) | Total Effort | Segment | Customer | Family | Part | Customer Phase | MP Date | Product | LTR ($M) | GIBC | Module | Tools | Request brief | Progress record | Root cause | Solution | Support Type | Support Region | Input Source | Community Link (Mandatory)
WW30 | Sherry | T.C. Lun | 3 | 3 |  | Internal SE | Kinetis | KE18 and KV31 | DI |  | KE18 and KV31 HVP Boards |  |  |  |  | FCC failure issues |  Per internal system engineer (Ben Wang, ben.wang@nxp.com) request, we help him to review this board and want to solve the FCC issues and fix it.  Received the schematic, PCB layout and spectrum plot information. Found that one frequency component around 400MHz is over the FCC limit. It causes fail the FCC test. First around of review had been completed and shared my finding with Shanghai local SE (Wang Peng) for further support.  Discussed with local SE and shared how to use the near field probe to locate the noise source and then fix it. Two RF adaptors had been sent to him for near field probe noise measurement. Noise source was located near the on-chip DC-DC module. Its harmonic 192MHz and 394MHz had been found. Some suggestion passed to him to eliminate the noise and particular frequency components.  Our Shanghai SE team performed some measurement and found lot of noise (particular in 196MHz and 390MHz ) by use of the near field probe. And they also found some improvement after followed by my suggestion (add ferrite bead and move bypass capacitor near the U6). At the same time, I do some measurement in Shenzhen EMC lab. and found similar frequency components near the U6 and 396MHz is found in USB cable. After studied the isolated DC-DC converter chip (U6) datasheet, it not only to point out the edge and input-to-output dipole emissions will cause FCC test fail but also introduces the solution by application note (AN-0971). I had passed my finding to our Shanghai SE team. And suggest to follow the AN to solve the FCC problem. |  | hardware design review, evaluation report with recommendations | Professional Service | Great China | System Engineer (Ben Wang, ben.wang@nxp.com)
WW30 | Sherry
WW30 | Sherry
WW30 | Sherry
WW30 | Sherry
WW30 | William
WW30 | william | Wang Hao | 2 | 4 | Consumer/Communication | HuaXin | Kinetis K | K22FN256VLH12 | MP |  | IR touch panel | 0.85 | 1-22LIZTT | USB | KSDK | Customer reported HID device enumeration failure with multiple tries and requested help to find root cause. | Got dump result for USB registers and BDT table content when enumeration failed, found USB controller has DMA error bit set. Need design help on conditions which could lead to DMA error bit set. Customer reported flash programming issue when switched from HSRUN to RUN mode, flash module set access error bit. Double checked customer code, found this is related to a software bug with AN4985 accompanying code which caused incomplete mode change from HSRUN to RUN mode, flash erase command was still issued under HSRUN mode. Contact application owner to fix associated code. |  |  | General | Great China | FAE(Xiong Chunliu) | https://community.nxp.com/thread/430297
WW30 | William | Wang Hao | 1 | 1 | Consumer/Communication | Microsoft | Kinetis K | SC667334DC12 (K22F) | DI |  | Surface accessory | 0.636 | 1-1ZXJDQJ |  |  | Customer experienced ESD issue and request help. | Customer experienced ESD issue with K22F, MCU saw watchdog timeout, after adding 2.2nF cap close to MCU GPIO and 200ohm series resistor, they can solve the ESD issue. But they had concern if the instant high current(about 158mA) induced by 2.2nF will damage GPIO or not. Explained to customer maximum injection current for GPIO is 25mA so there is risk connection big caps close to MCU. Suggest them to use lower value caps and connect series resistor in between MCU GPIO and the cap and put the cap close to connectors. |  |  | Key | Great China | FAE(Xiong Yu)
WW30 | william | Wang Hao | 0.5 | 1 | Consumer/Communication | Microsoft | Kinetis K | MK60 | MP | [6 empty] | Customer reported big failure rate for oscillator output waveform level and request us investigate. | Aligned with Alistair and analog design that the seen OSC amplitude should be in valid range and measurement OSC amplitude on assmebly line is rare and depends on how the measurement is made. Request Pegatron to provide measurement scheme used, got no reply from them yet. |  |  | Key | Great China | FQE (YiMeng Zou)
WW30 | william | Jia Ding | 1 | 1 | Consumer/Communication | Microsoft | Kinetis K | SC667353DC5(MK22DX256VMC5) | DI |  | Gaming HID | 2.388 | 1-1NAXYD3 |  |  | Customer reported when entering VLPS after waking up from VSS0, abnormal current (3.7mA) would be watched. | Requested some information from customer, and speculated the issue might be resulted from customer's code. As we could not access customers code, it was difficult for us to analyzer the issue. So made a simple example which has similar work flow structure with customer's project, and sent to customer. Still waiting for the feedback. |  |  | Key | Great China | FAE(Xiong Yu) | https://community.nxp.com/thread/430542
WW30 | william | Wang Hao | 0.5 | 0.5 | Consumer/Communication | Shenyang RMS medical | Kinetis K | K22FN512 | DW |  | Ventilator | 0.5 | 1-1NZT4XV |  | MQX | Customer reported MQX4.1 MFS issue and request help. | Customer reported MQX4.1 MFS issue that whenever file write with 512 bytes, after one cluster of data was written, file open will fail. With other file write sizes, there is no such problem. Confirmed this on K64 tower board by writing to SD card, later confirmed this issue has already been fixed on MQX4.2. Provided instructions to FAE on how to port MQX4.2 MFS package back to MQX4.1. | SW issue | Workaround | General | Great China | FAE(Ji Cheng) | https://community.nxp.com/thread/430534
WW30 | William | Wang Hao | 2 | 3.5 | Consumer/Communication | Kona | Kinetis K | MK22 |  |  | Bio Smart Card | 5 |  | USB | KSDK | FAE requested to provide CCID demo which works with UART ISO7816 module. | Finished porting and testing CCID demo onto K64 tower board by directly connecting smart card without external PHY. Replied FAE in community ticket on general steps to follow to port CCID demo with UART ISO7816 support. |  | Customization | General | Korea | FAE(Thomas Kang) | https://community.nxp.com/message/814546
WW30 | William
WW30 | William | YangXi | 1 | 3 | Consumer/Communication | Artesyn | DSC | MC56F84766 |  |  | i.Hp | 1M | 1NIHKSM | CAN | CW10.6 | Online meeting with FAE and customer to discuss FlexCAN lost frame issue | Customer want to use Rx FIFO instead of Rx queue to avoid frame lost, but they have less knowledge about it, intrude Rx FIFO to them and share them with a FlexCAN RX FIFO demo. Ask customer’s questions about when to clear Rx FIFO warning flag/ read massage content and clear flags. |  | Customization | General | NA | FAE(Audrey Eng ) | https://community.nxp.com/message/813003?et=watches.email.thread#comment-813003 | Support Region is Malaysia
WW30 | William | Zhong Juying | 0.5 | 0.5 | Security | BBPOS | Kinetis K | MK21F | MP | [6 empty] | Customer reported that they got a DPA testing fail from PCI lab | 1
WW30 | William
WW30 | Eric | Chen Xinyu | 1 | 5 | Consumer/Communication | SONY | Kinetis L | KL17Z32VDA4 | DI |  | Walkman | $1.1M | 1-1WC0CVE | FlexIO | KSDK | 1. FlexIO I2S Rx sample lost issue 2. 44.1Khz 32bits can run under VLPx or not | 1. FAE found there's sample lost issue when using the SDK v1.3 FlexIO I2S Rx HAL driver working with a K64 I2S Tx. They provide a workaround to fix in the Rx driver by changing the BCLK clock polarity. Debug and found the issue is caused by Tx/Rx BCLK polarity is not consistent. Raise JIRA ticket for SW team to provide a BCLK polarity when doing FlexIO I2S init, but not hard code to HIGH Active (KPSDK-11611). 2. FAE is asking if SONY's code can run under VLPx mode when receiving I2S data with 44.1/48Khz sample rate, 32bits I2S format. Checked FlexIO I2S timing SPEC, VLPx mode can not provide such high clock source for 44.1/48Khz. Customer can only use STOP/PSTOP mode. | SW issue | Fix - Erata/JIRA | General | Japan | FAE (Hiroshi Hiraga) | https://community.nxp.com/message/811392?et=notification.mention#comment-811392
WW30 | Eric | Chen Xinyu | 0.5 | 1 | Consumer/Communication | MicroTip | Kinetis K | KS22F256N | DI |  | AudioBox | $106K/y | 1-2067HOF | USB | KSDK | Customer using KS22 as a USB audio class 2.0 device. And met issue on 1) Failed to enable high sample rate (44.1Khz) with 24bits format on Mac OSX 2) Failed to work on Windows with thesycon USB audio PC drivers | 1. Issue fixed by customer itself. But they're asking adding two mic in-endpoint into descriptor, we provided example for them to refer. 2. The connection between SDK USB device demo (audio class 2.0) with Thesycon PC driver issue has been fixed. The issue is identified by SW team, that one of the parameter in our demo's descriptor is not compatible with 2.0. Tried the fix on customer's code, it can work. Now the customer still has the opportunity from his end-customer. | New Requirement | Customization | General | Great China | FAE (Lin Kent) | https://community.nxp.com/message/811532?et=watches.email.thread#comment-811532
WW30 | Eric | Shi Changhao, Terry Lv | 2 | 2 | Smart Grid | Waison | Kinetis M | KM34Z256 | Early Evaluation |  | Breaker |  |  | AFE | IAR | Customer want to know the AFE sampling time on KM34Z256 to see if AFE is qulified for their electronic breaker. | Customer want to know the AFE sampling time on KM34Z256. We tested AFE sampling data with OSR=1K and send the data to customer. | New Requirement | Customization | General | Great China
WW30 | Eric | Shi Changhao, Terry Lv | 2 | 2 | Smart Grid | Waison | Kinetis M | KM34Z256 | Early Evaluation |  | High-end export meter |  | 1-1TMBY86 | AFE | IAR | Customer is evaluating MMCAU on KM34Z256. They want to know the feature and performance of MMCAU. | Customer is evaluating MMCAU on KM34Z256. They want to know the feature and performance of MMCAU. Customer wants to use MMCAU for AES-128, AES-256, ECDSA P-256/P-284 and EEC CDH. MMCAU don't support ECDSA and customer needs to use software for it. Also, we send performance disgram of MMCAU to customer. | New Requirement | Customization | General | Great China
WW30 | Eric
WW30 | Eric
WW30 | Eric
WW30 | Richy | Wang Li, Jiang Dengyu, Wang Dechang, Zhao Ping | 6 | 7 | Wireless Charger | Seoyou | WCT | WCT1111 | Early Evaluation |  | 15W_TXMULTI |  |  |  | CW10.6 | Board bringup . | 1.Reworked the board power circuits, and found the AUX power design fault and revidsed it. 2, Changed the SW with this boards design coil selection logic and ADC pin assignment, the boards can charging 15W with NXP's MPRX, and the basic function is good. | New Requirement | Customization | General | Korea | FAE (Kate Lee - B45752)
WW29 | Richy | Richy Ye, Wang Lingling | 2.5 | 59 | Digital Power | Artesyn Philippines | DSC | MC56F82748 | Early Evaluation |  | Digital power development platform |  |  |  |  | Tool box for automatic code generation from MATLAB | Finished the documentation about automatically code generation, and reorgnized the matlab files for well understanding. | New Requirement | Customization | Key | Globe Transition | FAE(Andrey Eng - B43125)
WW30 | Richy | Richy Ye, Jiang Dengyu, Mao Huan | 3 | 70 | Wireless Charger | LG IT | WCT | MWCT1111CLH | MP |  | 15W 1COIL TX | $1.70 | 1-FFWPV2 |  | CW10.6 | Customer want a solution of WPC+PMA based on WCT1111 | 1. The low power mode can work well on LGIT board; the reason of the unstable working status is that there is no pull-up resistor on RXD port and the noise on board can wake up TX; it could be resolved by enabling internal pull-up resistors, 2. Got some signal of LGIT_Belkin board during compliance test; the reason of failed power control items might be that the Z-gap is 1.5mm other than 3mm; have suggested customer try to increase the Z-gap or decrease minimum phase percent; 3. Prepared debugging firmware for LGIT to do research on Q factor measurement, especially on Q factor of phones with friendly mental. | New Requirement | Customization | Key | Korea | FAE (Kate Lee - B45752)
WW30 | Richy | Liu Zhen | 0.5 | 1 | Motor Control | Positec | Kinetis E | MKE02Z32 | Early Evaluation |  | Drill |  |  |  | IAR | BLDC solution for KE02 | Sent the source code to FAE to promote customer, FAE demonstrate it to customer on site, fund that start torque is not enough when rotor is blocked. Will debug it next week. | New Requirement | Customization | General | Great China | FAE(Cherrish Liao - R65774)
WW30 | Richy | DingWenshuang Zhou xuwei | 1 | 5 | Motor Control | Little Swan(BPM) | DSC | MC56F82723 | Early Evaluation |  | BPM washing machine |  |  |  | CW10.6 | Test and optimize the BPM washing machine performance | 1,Optimized of the observer parameters and now the motor runs well with 150rpm target speed and unblanced load. | New Requirement | Customization | General | Great China | FAE(Larry Yang)
WW30 | Richy | DingWenshuang Howard Liu | 1 | 5 | Motor Control | Little Swan(ACIM) | DSC | MC56F82723 | MP |  | ACIM washing machine | 0.8 | 1-1Y288OT |  | CW10.6 | Help customer to solve the issure during the MP state | 1,Throutgh FAE's on site support last week, found the ADC ISR and PWM reload ISR timing is wrong during the current distortion issure occurred. Root cause is that customer added class B code for IEC60730 standard in main loop and this will bring a risk to the isr timing. Suggested the customer to integrate the two ISR to one,and it worked well through test. | New Requirement | Customization | General | Great China | FAE(Larry Yang)
WW30 | Richy | Zhao Ping | 0.5 | 1 | Wireless Charger | Beijing InvisPower | WCT | WCT100xA | DI |  | 5W Automotive Power Transmitter |  |  |  |  | First packet timeout | Customer board printed "Timeout on Start" when charging a RX. This message means the first packet timeout. Suggested customer to check their board noise with FreeMASTER GUI tool. Told FAE the meaning of basic print messages. | New Requirement | Customization | General | Great China | FAE (Ji Cheng - B46604)
WW30 | Richy | Zhao Ping | 0.5 | 40.5 | Wireless Charger | Delphi China | WCT | WCT1001A | MP | 2016.3 | 5W Automotive Power Transmitter |  | 1-UXG1IX |  |  | Flash security | Customer requested flash security state. Added it to customer project and sent the code for customer test. | New Requirement | Customization | General | Great China | FAE (Yu Ningning - B45276)
WW30 | Richy | Zhao Ping | 0 | 23.5 | Wireless Charger | Omron Japan | WCT | WCT1001A | DW | 2018 | 5W Automotive Dual-Mode Power Transmitter |  |  |  |  | Release V4.0.3 code | Released V4.0.3 code per customer request and detailed changes between V4.0.3 and V4.0.2. | New Requirement | Customization | Professional Service | Japan | FAE (Noriaki Masuda-B01926)
WW30 | Richy | Zhou Xuwei | 2 | 4 | Automotive | ZFTRW | DSC | s56F8013 | DW |  | Electrical Power Steering |  |  |  |  | The malfunctioned part has been sent back to TJ site for FA. Now we have a code that reproduces the issue, and the problem may relate to RAM controller or data bus switch. TRW requested to screen out this kind of chips during tests. PE decided to add this screening code in burn-in process. Pinjiao Chen(PE) asked for my help on working out the test codes. | The test results need to be written into the flash. Worked out and tested the flash driver for 8013. Helped P.J Chen to modify the linker file and taught her how to use the driver functions in her own platform through skype.
WW30 | Richy | Kevin Cheng | 4 | 6.5 | Digital Power | GE Energy | DSC | MC56F82748 | Early Evaluation |  | Interleaved Full bridge converter |  |  |  |  | PCCM evaluation | send out the PCCM peripheral planning to FAE. An anguilla silver controls one fullbirdge converter only. Two interleaved fullbridge converter can control by two DSC. |  | Customization | BD Activity | Globe Transition | FAE (Cherrish liao-R65774)
WW30 | Richy | Gao Xiang, Richy Ye | 0.5 | 3.5 | Wireless Charger | HTC | WPR | WPR1516 | Early Evaluation |  | 15W power receiver for mobile |  |  |  |  | Prototype development | Analysis the mode detection method, which can be completed by polling FEDT (from FDU and FDL registers) of NX1MP15, since the function is simple, suggested third-party to continue A4WP coding on the current firmware pack, just consider it a single A4WP receiver. And we will verify the switching logic when debugging the QI function. | New Requirement | Customization | General | Great China | FAE (Beta Chen - B44998)
WW30 | Richy | Gao Xiang, Mao Huan | 0.5 | 11.5 | Wireless Charger | Magic-Link | WPR | WPR1516 | DW |  | Wireless charger Rx |  | 1-1OU7KWR |  | IAR | Customer board debugging | Reviewed the WPR1500-HV schematic and PCB from customer, customer use TYPE-C USB port to support QC function and other two ports need to be shut down by SW before VOUT change to 9V or 12V. Suggest customer to use internal VOUT sample circuit to save one GPIO for output control. |  | Customization | Key | FAE(Yu Ningning-B45276)
WW30 | Richy
WW30 | Richy
WW30 | Richy
WW30 | Richy
WW30 | Richy
WW30 | Richy
WW30 | Richy
WW30 | Richy
WW30 | Richy
WW30 | Richy
WW30 | Richy
WW30 | Richy
WW30 | Richy
WW30 | XD | Chu Hongdong | 3 | 37 | ePOS/Security | Landi | i.MX | i.MX6UL |  |  | ePOS | 500K | #1-1PPBZ7A | HAB,CAAM,SNVS,Dryice,BEE | Yocto | Implement security features. | Discuss with Shanghai team and help to reproduce the power sequence issue reported by Landi on i.MX6UL EVK board. Landi reported that the hwrng device is not registered on their platform, need check their kernel config file to find the cause. |  | Customization | Key | Great China
WW30 | XD
WW30 | XD
WW30 | XD
WW30 | XD
WW30 | XD
WW30 | XD
WW30 | XD
WW30 | XD
WW30 | XD

## Apps Lead
Week | Team | Apps Engineer | Open Date | Close Date | Effort (man- days) | Total Effort | Family | Project | NPI Phase | Next Apps Milestone | TO Date | Enablement Task | Highlight/Lowlight/Issues/Risks | Progress record
WW30 | Sherry
WW30 | Sherry
WW30 | Sherry
WW30 | William
WW30 | william | Guo Jia | 2016-07-11 | 2016-07-22 | 3 | 9 | Kinetis L | L5K | Launching |  |  | Certification - USB | Both HOST and DEVICE certification passed. | Shot all the hardware issues on the boards. And will make a check list and it will be applied in future USB certification.
WW30 | william | Guo Jia | 2016-07-11 | 2016-07-22 | 1.5 | 9.5 | Kinetis L | L5K | Launching |  |  | Documentation - Application Notes |  | 1.For the LPSPI use case, got the feed back from design that after set TXMSK, need to clear it by SW, or LPSPI would keep sending dummy bytes. In application, it would bring some trouble. I am doubting this is a design flaw, need to be confirmed by design. 2. For the TRIGMUX use case, some concept is not expressed well in our RM. Especially the connection with DMA MUX. Need to make an AN for it.
WW30 | william | wang Peng | 2016-03-25 |  | 2.5 | 6.5 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | Finish the coding of CRC adder, and finish the draft data collection of CRC,CMP and PDB, share the test data and related doc to BACEs team.
WW30 | william
WW30 | william
WW30 | william
WW30 | Eric | Chen Xinyu | 2016-03-25 |  | 1 | 13 | Kinetis E | MT512P | Execution |  | Q1'16 | Documentation - Data Sheet |  | 1. Updating the DS with comments from different team. 2. Co-work with BACES for the LPI2C peripheral adder data collection. 3. Discuss with PE/TE/BACES on the current TBD data in both MT256/512P. Ask owner to provide data. Now TE/PE is commit to develop the RAMP ATE program for ADC linearity test, and we will have Min/Max data weeks later. Other TBD is still under testing.
WW30 | Eric | Chen Xinyu, Song Juanjuan | 2016-07-18 | 2016-07-22 | 2.5 | 2.5 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Engineering |  | Tested the LPSPI performance and timing on FRDM-KE15Z board. The LPSPI SCK can up to 24/36Mhz, both master and slave work correctly. Also the timing (SCK rising/falling, data hold time, etc) is matched with the SPEC. Will check with IP owner and system on this result.
WW30 | Eric | Ben Wang, Chen Xinyu, Cao Nan, Chen Yonggang | 2016-06-24 |  | 7.5 | 47.5 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | 1. Learning the KPET backend database XML format. 2. Adding the 11 IDD cases we need for KPET into the BACES idd test code with coremark support. 3. Porting adder program to BACES board with configuration support. Providing each peripheral's configuration in doc. 4.Finish FlexIO I2C KPET use case.Found one SDK2.0 driver issue of FlexIO, the JIRA ticket number is KPSDK-11678.
WW30 | Eric | Ben Wang | 2015-11-23 |  | 2 | 85 | Kinetis E | MT512P | Execution | Documentation - TWR UG ready 7/31 | Q1'16 | Documentation - Others |  | 1.Finished signoff QMS workflow to stage 5.0. 2.Reviewed the updated PB and CN version of DS, provided comments and feedback to marketing. 3.HVP-KE18F daplink firmware released by SW team, verified ok and intergrated into FSW. 4.Writing the UG of TWR-KE18F.
WW30 | Eric | Chen Yonggang | 2016-07-18 | 2016-07-20 | 4 | 6 | Kinetis E | KE15Z | Execution | TSI EVB software/appnotes ready 8/15 | Q4'15 | System Cases-KPET |  | 1. Developing demo software on TSI reference board, 30% done, and verifying TSI features like sensitivity boost, proximity features. Found the shield feature can't work, checking with TSI IP owner. 2. Sent 2pcs FRDM-TOUCH boards to customer Electrolux to support KE15Z evaluation. 3. Improved SCG FIRC data in MT256 Datasheet, only the 48MHz has 1% deviation with trimmed value, the other 52/56/60MHz hasn't been trimmed thus can't guarantee the 1% deviation. 4. Checked and released the final FSW files for FRDM-KE15Z production board testing.
WW30 | Eric | Fang Yizhou | 2016-07-18 | 2016-07-21 | 4 | 4 | i.MX | i.MX6ULL | Execution | Documentation-HUG,QSG,HDG,Power Consumption ready 8/16 | Q4'15 | System Engineering |  | 1. Request new parts in Agile. 2. Based on i.MX 6UL EVK Schematic, revise CPU, DDR and QSPI-Flash circuits of i.MX 6ULL EVK. Also revise schematic number, comments and other related things.
WW30 | Eric | Fang Yizhou | 2016-07-22 | 2016-07-22 | 1 | 1 | i.MX | i.MX6ULL | Execution | Documentation-HUG,QSG,HDG,Power Consumption ready 8/16 | Q4'15 | System Engineering |  | FCC PART15 ClassA test passed of i.MX 6ULL EVK board, including 30M-6G test and power supply test.
WW30 | Richy | Howard Liu | 2015-07-16 |  | 3 | 106.5 | Kinetis E | MT512P | Execution |  | Q3'16 | System Cases |  | MT512P NPI: 1) During check on the issue of PFC resetting system, found two PFC inductors were soldered with incorrect pin-mapping. The different specification of new inductors causes the manufacturer soldering wrong pins, so the inductances were bypassed on the board. Asked board manufacturer shipping another board with fix. The root cause of system reset by enabling PFC was the RESET pin without pull-up on the DSC daughter card. The bad electromagnetic interference caused the false reset signal. 2) Studied the changes list between PTV and Rev 1.0. Some low-level peripheral initialization codes need modification for Rev1.0 chip. Alpha customer support: Japan FAE reported that the initialization trigger of FTM had different behavior between PTV and Rev1.0 in the FTM->PDB->ADC trigger path. After checking the information from Mitsubishi, there's no clue for the issue. Ask FAE to get the details of initialization code used by Mitsubishi.
WW30 | Richy
WW30 | Richy
WW30 | XD
WW30 | XD
WW30 | XD
WW30 | XD
WW30 | XD

## Reference Design
Week | Team | Apps Engineer | Open Date | Close Date | Effort (man- days) | Total Effort | Family | Segment | Project | Reference Phase | Milestone Date | Progress record
WW30 | Sherry
WW30 | Sherry
WW30 | Sherry
WW30 | William | Jia Ding | 2016-07-12 |  | 3 | 6.5 | Kinetics |  | KEED | Development |  | 1. Finished K20256R's KEED project. 2. Finished part of the LPC54102's KEED project.
WW30 | William
WW30 | William
WW30 | William | YangXi | 18/7/2016 | 22/7/2016 | 3 | 116 | Kinetis K | Industry | QR decoder | Lib Release |  | 1. Measure QR decoder demo decoder execution time and MIPS. 2. Update QR decoder introduction PPT.
WW30 | William | wang peng | 2016-05-16 |  | 1.5 | 12.5 | Kinetis L | Industry | iPOS | Design - evaluation |  | Fix one bug on using DMA to transfer data of ADC sampling, and the further performance improvement is on-going.
WW30 | William | Zhong Juying | 2016-06-06 |  |  |  | Kinetis L | Security | RSA & ECC with DPA countermeasure | Development |  | 1.improve blinding method on RSA countermeasure as below: 1.1 did some try on an improved blinding method. blinding message and spliting exponent(E1, E2, .... En), then calculated mod_exp for E1 to En. ----- Done 1.2 implemented a policy for randomly inserted dummy exponent. ---- Done 1.3 implemented a policy for recoverying the real result of mod_exp. ---- Done 1.4 will continue to do debug and testing ---- met some problem on obtaining a correct result, will adjust policies designation ---- on-going
WW30 | William
WW30 | William
WW30 | William
WW30 | William
WW30 | William
WW30 | Eric | Terry Lv, Shi Changhao | 2015-11-16 |  | 4 | 137 | Kinetis W | WirelessConnectivity/IoT | Smart Home | Development |  | 1. Developing android APP based on BLE ToolBox. 2. Create a smart_home_ble_android_app repository for Android APP.
WW30 | Eric
WW30 | Eric
WW30 | Eric
WW30 | Eric
WW30 | Eric
WW30 | Richy | Wang Dechang, Zhang Yangjie, Richy Ye, Gao Xiang, Wang Lingling | 2015-08-06 |  | 7 | 450 | DSC | Digital Power | Golden Server Power-Totem Pole BLPFC | Design |  | 1.Tested the basic performance with the new structure SW, the PF, THDi are improved. 2.Debugged the system under input voltage 85V-265V. 85V can work well, however, when input voltage is 240-260V, duty became smaller than 10% at the peak input voltage and current sample can be disturbed, then will cuase the input current not stable. Changed sample instant to falling middle of inductor current to solve the problem when the duty < 15%, this will solve the problem. 3.Started writing Totem PFC DRM, 25% completed.
WW30 | Richy | Li Shunan | 2014-08-07 |  | 4 | 31 | DSC | Motor Control | Stepper Motor Driver | Development |  | Complete the draft version of the application note which title is dual hybrid stepper motor microstepping control on MC56F84766, and reviewing is ongoing.
WW30 | Richy | Wang Dechang, Jiang Dengyu, Wang Li, Richy Ye | 2015-03-02 |  | 2 | 213 | WCT | Wireless Charger | WCT-15WTXMULTI | Design |  | 1. Prepared 4 WCT1111 boards for Qi testing in the LG Lab. 2. Followed the release testing, and send another prototypes to verigy the testing issues, now onle the FOD simulator DDM issue is not solved.
WW30 | Richy | Jiang Dengyu, Mao Huan, Richy Ye | 2014-10-04 |  | 2 | 486 | WCT | Wireless Charger | WCT-15W1COLTX | Development |  | 1. The test item Maximum Voltage couldn't pass in compliance tests ; had a discussion with team and will do more research; 2. Prepared two boards and latest firmware for compliance tests in LGIT lab;
WW30 | Richy | Liu Zhen, Ding Wenshuang | 2016-03-10 |  | 4 | 52 | S08 | Motor Control | Drone ESC | Development |  | 1, Optimizing startup algorithm, the effect is not obvious. The debug is ongoing. 2, Added PWT speed control function into source code, it works well after test. 3, Sent the schematic of this reference design to marketing to promote customer per their request.
WW30 | Richy | Howard Liu, Richy Ye | 2014-09-20 |  | 1 | 55.5 | DSC | Motor Control | Sensorless FOC e-Sooter -MC56F82728 | Development |  | PM, h/w and application s/w status: 1) The eScooter Xiaoniu M1 arrived in Roznov, and additional control board for evaluation was shipped together. 2) Called IDH and discussed the MOSFET transistors on new board. If using other replacement for the original suggested MOSFET that's expensive, the resistors in the drive circuit needs low resistances to enlarge the current to reduce the time of charge to capacitors, as a result of increase the MOSFET turn-on time. After considering the pros and cons, IDH still wants to use original suggested MOSFET transistors. The purchasing is in the process. MC software status of development and test (From Roznov team): - Multiple test rides performed, comparing the performance of the new M1 scooter and our current solution. Our solution seems to be more aggressive (gives more acceleration). - The control of the scooter on required power (set from throttle) was improved, the precession of calculation of required Iq current was improved based on power measurement done last week. - Denis Cabrol (Global Leader of Solutions Team) visited Roznov for one day, eScooter project status, challenges and futures plans were presented and discussed.
WW30 | Richy | Gao Xiang | 2015-02-01 |  | 1 | 191 | WCR | Wireless Charger | WPR1500 LDO/BUCK MPRX | Development |  | 1, Review the updated WPR1500-BUCK FOD Calibration Guide, use total power loss Ploss_rx instead of Ploss_buck for calibration, thus make it easy and simple for customer to understand. 2, Provide 2 WPR1500-Buck boards for NXP NFC team of compatibility testing
WW30 | Richy | Richy Ye, Wang Dechang, Jiang Dengyu, Kevin Cheng, Gao Xiang, Wang Lingling | 2015-03-23 |  | 2 | 209 | DSC | Digital Power | Golden Server Power | Design |  | 1, Complete the review of LLC design reference manual, update the HW design part to compatible with experiment, provide the comments to back to doc team. 2, Continue to research the 2P2Z PI control method, analysis the pole and zero point influence to system amplitude and phase.
WW30 | Richy
WW30 | Richy
WW30 | XD | Hu Teng | 2016-06-20 |  | 5 | 21 | Kinetis W | WirelessConnectivity/IoT |  |  |  | Finished developing a simple BLE and Thread hybrid demo on KW41. This demo mainly controls LEDs in a Thread network by an iPhone App, which connects to one KW41 in the network through BLE. This demo is simple but demonstrates BLE and Thread co-existence on our KW41.
WW30 | XD
WW30 | XD
WW30 | XD
WW30 | XD
WW30 | XD
WW30 | XD

## Others
Week | Team | Apps Engineer | Open Date | Close Date | Effort (man- days) | Total Effort | Item | Segment | Family | Part | Module | Tools | Request brief | Overal Progress | Input Source
WW30 | Sherry
WW30 | Sherry
WW30 | Sherry
WW30 | Sherry
WW30 | William
WW30 | William | Wang Peng | 2016-02-24 |  | 1 | 3 | translation review |  | Kinetis S | KS22 | USB |  | review the translation of KS22 reference manual | USB chapter review is on-going, and 20 comments is added.
WW30 | William
WW30 | William
WW30 | William
WW30 | William
WW30 | William
WW30 | William
WW30 | William
WW30 | William
WW30 | Eric | Ben Wang | 2016-07-20 | 2016-07-22 |  |  | Revised the KE web trainning slides. | [6 empty] | Got review feedback from marketing, and revised all the training slides of FTM,PWT,PDB and ADC module.
WW30 | Eric | Nan Cao | 2016-07-18 | 2016-07-19 | 1.5 | 1.5 | Fotile induction cooker trainning about Control System | [6 empty] | Focused on MT256 peripheral, such as :UART TSI LPTMR and LPIT module.
WW30 | Eric | Nan Cao | 2016-07-18 | 2016-07-18 | 0.5 | 0.5 | Suzhou New Hire Orientation Training | [6 empty] | iCAP,Fiance,EC,TSO,IT&Awareness,Logistics,Rewards & HR useful links
WW30 | Eric | Shi Changhao, Lv Terry | 2016-07-20 | 2016-07-21 | 2 | 4 | Develop firmware for 1PH 4CH Meter which will be used for 1PH 4CH Meter AN. |  | Kinetis M | KM34Z256 | AFE | IAR |  | Develop firmware for 1PH 4CH Meter which will be used for 1PH 4CH Meter AN.
WW30 | Richy | Ding Wenshuang Liu Zhen | 2016-07-22 | 2016-07-22 | 0.5 | 0.5 | Code and document preparation for Taiwan FAE |  | Kinetis E | MKE02Z32 |  | IAR |  | packaged the critical function into lib and sent the code with AN to FAE(Stanley Huang)
WW30 | Richy | Zhao Ping | 2016-07-22 | 2016-07-22 | 0.5 | 0.5 | Study Q factor detection of MP platform |  | WCT | WCT1111 |  | CW10.6 |  | Study Q factor detection theory and related code.
WW30 | Richy | Zhou Xuwei | 2016-07-18 | 2016-07-19 | 2 | 2 | Take over the compressor control code for 3-in-1 |  | DSC | 56F84789 |  |  |  | Went through the library codes to understand the definitions of the macros.
WW30 | Richy | Ethan Cheng | 2016-07-18 | 2016-07-19 | 2 | 2 | Study software stack of PoS peripheral |  | Kinetis K | K81F150M |  |  |  | Traced the source code of smart card reader (TDA8029) and pinpad software stack. Also studied the related material of TWR-K81F150M KSDK2.0 for customer support.
WW30 | Richy
WW30 | Richy
WW30 | Richy
WW30 | Richy
WW30 | XD | Liu weiping | 2016-06-13 |  | 4.5 | 21 | POS solution |  | i.MX |  |  |  |  | 1. Pick up an open source code of QR code scan and porting to imx6ul linux project. 2. Worte a camera QR code scan linux application for first release.
WW30 | XD | Yang Zhao | 2016-07-18 |  | 5 | 5 | Secruity |  | Kinetis K |  |  |  | Test the ECC code of KSDK2.0 | 1 .Fixed the memory leak problem now the demo do not stop.2 .Test the code and find the ecdsa verify process may fail sometimes . Next step :Debug and try to fix it.
WW30 | XD | Chu Hongdong | 1/4/2016 |  | 2 | 26 | Side channel test |  | i.MX |  |  |  |  | Check DES software algorithm with antiDPA, add DES encryption/decryption code in side channel test firmware.

## List_Def
Team | Segment | Family | Part | Customer Phase | Reference Phase | NPI Phase | Module | Tools | Root cause | Solution | Support Type | Source | Enablement Task | Support Region
KM | Automotive | S08 | i.MX53 | Early Evaluation | Design | Concept | USB | KSDK | Ctm S/W defect | Fix - Erata/JIRA | General | FAE | Documentation - Data Sheet | Japan
Sherry | Consumer/Communication | CF | KM34Z64 | DI | Development | Feasibility | ADC | PEx | Ctm H/W defect_D | Workaround | Key | BD_MKT | Documentation - Errata | Korea
Manish | Industry | DSC | KM34Z256 | DW | Integration | Plan | I2C | MQX | EMC | Customization | Professional Service | NPI_MKT | Documentation - RM | Great China
Lily | eReader | Kinetis L | KM34Z128 | Pilot | Reference Release | Execution | SPI | Linux | Design issue | Demo/Reference | Leverage | Sales | Documentation - Application Notes | Globe Transition
Robin | Security | Kinetis E | KL17 | MP | SoW | Launching | TSI | Android | Design limitation | Benchmark | BD Activity | Unknown | Documentation - Others | Community
Richy | Wireless Charger | Kinetis M | KM14Z64 | DL | Lib Release |  | AFE | WinCE | RM defect |  |  | CQI | System Cases | NA
William | Motor Control | Kinetis V | ​MK60DN512 |  | Documentation |  | GPIO | CW10.6 | DS defect |  |  |  | System Engineering
Eric | Digital Power | Kinetis K | MC56F82313 |  | Testing |  | ENET | IAR | System improvement |  |  |  | Board - Design
XD | WirelessConnectivity/IoT | Kinetis X | MC9S08PT16AVLD |  |  |  | QTimer |  | Driver issue |  |  |  | Board - FAT Coding & test
| Smart Grid | Kinetis W | MK64FN1M |  |  |  | JTAG |  | Ref board issue |  |  |  | Board - Document
| Industry-Touch | i.MX | MWCT1012CFM |  |  |  | FLASH |  | New Requirement |  |  |  | Certification - USB
| Industry-HomeAppliance | WCT | MKE02Z32 |  |  |  | UART |  | SW issue |  |  |  | Certification - Others
| Power | WCR | MC56F82723 |  |  |  | I2S | [5 empty] | Training
|  |  | MC9S08SD8 |  |  |  | DAC | [5 empty] | Alpha Customer Support
|  |  | KL16Z128 |  |  |  | FlexIO | [5 empty] | Tools Support
|  |  | KE18Z |  |  |  | LPIT | [5 empty] | Bug analysis support
|  |  | MKV10Z32VFM7 |  |  |  | LPTimer | [5 empty] | SDK Driver
|  |  | KE18F512VLL15 |  |  |  | LPTPM | [5 empty] | System EMC
|  |  | MC56F84789 |  |  |  | Flextimer | [5 empty] | System Cases-KPET
|  |  | MC9S08PA16AVWJ |  |  |  | PWT | [5 empty] | System Cases-BLDC demo
|  |  | MT512P |  |  |  | PDB | [5 empty] | System Cases-Peripheral adder
|  |  | KE15Z |  |  |  | PIT | [5 empty] | Board - OOBE
|  |  | KL17Z32VFM4 |  |  |  | eFlexPWM
|  |  | MC9S08SU16 |  |  |  | DMA
|  |  | i.MX6RT |  |  |  | WDOG
|  |  | KW41 |  |  |  | EWM
|  |  | K81/i.MX6UL |  |  |  | SIM
|  |  | KE06 |  |  |  | MCG
|  |  | KL02 |  |  |  | SCG
|  |  | KS22F256N |  |  |  | OSC
|  |  | K81 |  |  |  | ICS
|  |  | KL17Z32VDA4 |  |  |  | LLWU
RCM
PMC
SMC
SAI
RTC
CRC
CAN
ESDHC
ACMP
VREF
DryICE
RNGA/TRNG
CMT
QDecoder
AMP
DDR
LCD
KBI
FlexNVM
IRQ
FlexBus
CM0+
CM4
CACHE
OPAMP
bootROM
Radio
Note on L2: Author: General Customer Support
Note on L3: Author: Key Customer Support
Note on L4: Author: Professional Service
Note on E5: Author: pre mass production
Note on L5: Author: Leverage to general base from customer support
Note on N8: support enablement tools such as register header files validation, debugger svd file validation and etc
Note on N9: support PE/design to do bench test on bugs