## Customer Support
Week | Team | Apps Engineer | Effort (man- days) | Total Effort | Segment | Customer | Family | Part | Customer Phase | MP Date | Product | LTR ($M) | GIBC | Module | Tools | Request brief | Progress record | Root cause | Solution | Support Type | Support Region | Input Source | Community Link (Mandatory)
WW31 | Sherry
WW31 | Sherry
WW31 | Sherry
WW31 | Sherry
WW31 | Sherry
WW31 | William
WW31 | william | Wang Hao | 2 | 6 | Consumer/Communication | HuaXin | Kinetis K | K22FN256VLH12 | MP |  | IR touch panel | 0.85 | 1-22LIZTT | USB | KSDK | Customer reported HID device enumeration failure with multiple tries and requested help to find root cause. | Had meeting with customer to explain root cause for flash programming failure after HSRUN to RUN mode switch. Customer request us to provide estimation of maximum switch time over their operating temperature range for risk assessment of not updating firmware of 30k units already in field. Involved design team for the estimation. Worked with USB IP owner for enumeration failure root cause analysis. Found suspicious BDT content when USB device receiving USB host set config setup request. Need FAE to rerun the test to capture if by any chance BDT table is changed by customer code. |  |  | General | Great China | FAE(Xiong Chunliu) | https://community.nxp.com/thread/430297
WW31 | William | Wang Hao | 0.5 | 1.5 | Consumer/Communication | Microsoft | Kinetis K | MK60 | [7 empty] | Customer reported big failure rate for oscillator output waveform level and request us investigate. | Had call with Pegatron engineer and explained why checking OSC amplitude in mass production not recommended and the seen OSC amplitude is in valid range. Suggest them involve Nestlabs for discussion and check why they want to add OSC amplitude checking as one of the mass production steps. Also asked Pegatron to provide how they measure OSC amplitude in field. |  |  | Key | Great China | FQE (YiMeng Zou)
WW31 | william
WW31 | william | Jia Ding | 1.5 |  | Consumer/Communication | Microsoft | Kinetics K | SC667353DC5(MK22DX256VMC5) | DI |  | Gaming HID | 2.388 | 1-1NAXYD3 |  |  | Customer reported data copying costs ~23ms if acknowledge isolation after the data copying operation after waking up by LLWU from VLLS0 in their code. But it would cost ~50ms if acknowledge isolation before the data copying operation. | Made a simple demo which has similar work flow structure with customer's project, trying reproducing customer's issue on FRDM-K22F. However, it works well. The issue was reproduced. Thus, sent the demo to customer for their reference. |  |  | Key | Great China | FAE(Xiong Yu)
WW31 | william | Zhong Juying | 1.5 | 1.5 | Security | BBPOS | Kinetis K | MK21F | MP |  | mPOS |  |  |  |  | Customer reported that they got a DPA testing fail from PCI lab | 1. obtained and analyzed the report from lab. after carefully analyzing the report description, found that this issue maybe be caused by a mistake on our countermeasure implementation, so supplied a more detailed description on cryptDESDPA_ecb. 2. answered some questions of the detailed description from customer engineer. | Ctm S/W defect | Customization | Key | Great China | FAE (Yang YU)
WW31 | William
WW31 | William
WW31 | William
WW31 | William
WW31 | William
WW31 | Eric | Wang Ben | 0.5 |  | Industry | DELTA | S08 | MC908AB32CFUE | [5 empty] | GPIO |  | Delta Wujiang factory found MC908AB32CFUE issue in factory line, which already make line down. They produced 27pcs MC908AB32CFUE, and found 20 pcs failed.FAE did on site check, found the issue is PTE3/TACH1 and PTE7/SPCLK.When chip VDD is powered 5V, PTE3/TACH1 only output 4.09V high voltage and PTE7 output 7.6V high voltage.FAE want to know if 4.09V and 7.6V is normal in AB32? | Checked the AB32 datasheet, thought the output voltage is abnormal and not reasonable.A 5V part device can not be possible to output high voltage over 7.6V.Suggest FAE/PE to use a new part on another evalution board(not use customer board) to try again.The parts need to be checked by PE to see if they are counterfeit or misbonded. |  |  | General | Community | Community | https://community.nxp.com/message/816548?et=notification.mention#comment-816548
WW31 | Eric | Chen Xinyu | 0.5 | 1.5 | Consumer/Communication | MicroTip | Kinetis K | KS22F256N | DI |  | AudioBox | $106K/y | 1-2067HOF | USB | KSDK | Customer failed to add two MIC IN channel and endpoint into the USB Audio applications. | Meeting with customers, looks like they do not have ability to develop the USB audio applications, and request NXP to support enabling their product application. Sales, Marketing has rejected Microtips request, and talking with them to go through SW service. | New Requirement | Customization | General | Great China | FAE (Lin Kent) | https://community.nxp.com/message/811532?et=watches.email.thread#comment-811532
WW31 | Eric | Shi Changhao, Terry Lv | 5 | 40 | WirelessConnectivity/IoT | LG/VW | Kinetis W | KW41 | Early Evaluation |  | Car BLE/WIFI Dual Anteana System | 12M |  | Radio | IAR | Got patch from Connectivity Software Team to enable STOP mode in ADV and SCAN and do a full test. | Got patch from Connectivity Software Team to enable STOP mode in ADV and SCAN and do a full test. The new patch can bring about 3% - 18% improvement to power consumption. But it's still not enough. There's still a gap between KW41 and CC2650. Compared with CC2650 504uA in ADV and 1445uA in SCAN, our data is 867uA and 2812uA. HuTeng from Xiaodong team did an experiment and narraw down the ADV time from 8.9ms to 6ms. But after testing, the patch may not work on all KW41 boards. After some investigation, there're two points in optimizations: 1. Peak current. From our data sheet, both TX/RX current are 6.5 mA. Now we have reduced the current to TX 8.1mA, RX 9.1mA and Scan 12 mA. There're still spaces. 2. ADV and Scan time. Now one ADV time for KW41 is about 8.9 ms, but for CC2650, it is 5 ms. From Hu Teng's experiment, we can narrow down the duration from 8.9 ms to 6 ms. There might be chances to investigate the RF parameters. | New Requirement | Customization | General | Great China | FAE(Thomas Kang) | https://community.nxp.com/message/665311
WW31 | Eric
WW31 | Eric
WW31 | Eric
WW31 | Eric
WW31 | Richy | Liu Zhen, Ding Wenshuang | 1 | 1 | Motor Control | HongRi | S08 | SU16 | Early Evaluation |  | Electric tool with HALL sensor |  |  |  | CW10.6 | Review the schematic for the customer | Finished reviewing the draft schematic customer provided and gave some comments to them. | New Requirement | Customization | Key | Great China | Marketing(Felix Wang)
WW31 | Richy | Richy Ye, Jiang Dengyu, Mao Huan, Wang Li | 9 | 79 | Wireless Charger | LG IT | WCT | MWCT1111CLH | MP |  | 15W 1COIL TX | $1.70 | 1-FFWPV2 |  | CW10.6 | Customer want a solution of WPC+PMA based on WCT1111 | 1. Supported LGIT Qi compliance tests; run full compliance tests and , all test items can pass except maximum voltage in SGS lab after debugging; will get more test data for this test items. 2. Released one version code to LGIT based on their request to open FOD protection time based on their mechanism; fixed bug that two SCI can't work together; 3. Customer wants to use external crystal instead of internal crystal, have modified code for them; need debug on their latest board. | New Requirement | Customization | Key | Korea | FAE (Kate Lee - B45752)
WW31 | Richy | Ethan Cheng | 3 | 14 | WirelessConnectivity/IoT | Senao | Kinetis W | MKW41Z512VHT4 | DI |  | IoT gateway | $1.2M | 1-218W7NO |  |  | Senao required a sample code for Linux platform to communicate with KW40/KW41 BLE via FSCI interface. | Senao required a sample code for Linux platform to communicate with KW40/KW41 BLE via FSCI interface. The latest KW41 software release provided a Python wrapper for Linux Host SDK. FSCI demo setup and provided the related information for customer. | New Requirement | Customization | General | Great China | FAE (Chiang Jason-R44828)
WW31 | Richy | Ding Wenshuang, Zhou Xuwei | 2 | 7 | Motor Control | Little Swan | DSC | MC56F82723 | Early Evaluation |  | BPM washing machine |  |  |  | CW10.6 | Test the performance under unblanced load | 1,Increased the unblanced load and tested the performance under this condition. Now the peak torque current can be up to 3A, finished the test report under different control parameters. | New Requirement | Customization | General | Great China | FAE(Larry Yang)
WW31 | Richy | Wang Dechang, Jiang Dengyu, Zhaoping | 5 | 5 | Wireless Charger | Mobis | WCT | WCT1001A | DI |  | 15W Auto TX |  |  |  | CW10.6 | Board bebug support. | 1. Received the customer's board, and start to debug it. Optimized some parameters on the board. 2. By adjusting the resonant parameters, now the board can basically charge LP RX and NXP MP RX(BUCK) with full load. 3. Release the change lists and initial version F/W for customer test. | New Requirement | Customization | General | Korea | FAE (Kate Lee - B45752)
WW31 | Richy | Zhao Ping | 1 | 41.5 | Wireless Charger | Delphi China | WCT | WCT1001A | MP | 2016.3 | 5W Automotive Power Transmitter |  | 1-UXG1IX |  |  | Exit FOD retry phase when RX is still on TX surface | Customer reported that FOD protection only occurred 5s then PING started with TI dual mode RX. This issue was caused by TI dual mode switch. S6 workaround contains the solution for this issue. Merged the relevant code and sent to customer. Customer said this issue was solved. | New Requirement | Customization | General | Great China | FAE (Yu Ningning - B45276)
WW31 | Richy | Wang Li, Jiang Dengyu, Wang Dechang, Mao Huan | 0.5 | 2.5 | Wireless Charger | Omron Korea | WCT | WCT1111 | Early Evaluation |  | 15W_TXMULTI |  |  |  | CW10.6 | Board bringup and full function debug. | 1. Released one version code with Samsung fast wireless charging support; now it can work in fast charging mode basically. | New Requirement | Customization | General | Korea | FAE (Kate Lee - B45752)
WW31 | Richy | Zhao Ping | 0 | 23.5 | Wireless Charger | Omron Japan | WCT | WCT1001A | DW | 2018 | 5W Automotive Dual-Mode Power Transmitter |  |  |  |  | Release V4.0.4 code | Customer reported a bug that there was no coil selection after FOD retry time out. SW team fixed it. I released V4.0.4 code to customer for test. | New Requirement | Customization | Professional Service | Japan | FAE (Noriaki Masuda-B01926)
WW31 | Richy | Kevin Cheng | 0.5 | 0.5 | Digital Power | Chicony Wugu | DSC | MC56Fxxxxx | Early Evaluation |  | Digital Power supply |  |  |  |  | pwm feature request | Customer seeks pwm examples for peak controlled half bridge converter, provided the pwm configuration developed for GE engergy team. and provided detailed behavior illusatration. Customer is now willing to use it on their design. |  | Workaround | BD Activity | Great China | FAE (Jiunn Yang - B45153)
WW31 | Richy | Zhou Xuwei | 1 | 1 | Digital Power | Chengetech | DSC | MC56F84769 | Early Evaluation | [7 empty] | 1). Customer asked for support of E2PROM usage on 56F84769. Sent him AN5074 and related driver codes. Explained the memory structure and addressing mechanism of flash and related IFR to customer. 2). AN5074 provides a way of updating firmware without erasing EEPROM by "Target Tasks", which can't enter debug mode when downloading is finished, so customer would like an alternative method. I had thought unchecking "Always mass erase on download" in Debug Configurations would solve this problem, but it doesn't work on Multilink. It works on USBTAP, but the read out words are reversed after reprogramming. 3). Customer asked for random number generation function, I suggested to use functions in MSL since there's no such hardware module in the chip. |  | Customization | Key | Great China
WW31 | Richy | Zhou Xuwei | 2 | 44 | Motor Control | Delta HA | DSC | MC56F82746 | Early Evaluation |  | BPM washing machine |  |  |  | CW10.6 |  | 1). Changed the startup to a method that customer required. Now motor mergers into closed loop at 150RPM. Next step is to eliminate alignment stage. 2). Tried several ways to increase the loading performance at low speed. It turned out that a little positive Id and larger bandwidth of the observer would help. |  |  | General | Great China
WW31 | Richy | Gao Xiang, Richy Ye | 0.5 | 4 | Wireless Charger | HTC | WPR | WPR1516 | Early Evaluation |  | 15W power receiver for mobile |  |  |  |  | Prototype development | Align with A4WP expert Yang yin for the SW structure, WPR1516 flash memory is limited, thus difficult to support separated flash area for each protocol support and bootloader. Provide reference materials to him to get familiar with WPR1516 code. | New Requirement | Customization | General | Great China | FAE (Beta Chen - B44998)
WW31 | Richy | Gao Xiang | 0.5 | 12 | Wireless Charger | Magic-Link | WPR | WPR1516 | DW |  | Wireless charger Rx |  | 1-1OU7KWR |  | IAR | Customer board debugging | Complete the draft code for customer based on application structure. TYPE-C USB port support QC function and other two ports to be shut down by SW before VOUT change to 9V or 12V. Use internal VOUT sample circuit to save one GPIO for output control. |  | Customization | Key | Great China | FAE (Yu Ningning-B45276)
WW31 | Richy | Richy Ye | 0.5 | 0.5 | Digital Power | GE Healthcare | DSC | MC56F827xx | Early Evaluation |  | Digital power supply for MRI RF module |  |  |  |  | Demo evaluation | Customer is looking for digital LLC converter solution for his next generation MRI RF module. Had conf. call with customer R&D to understand the basic requirements, and provided our reference slides for evaluation first. Will ship one demo next week to customer for evaluation test. |  |  | General | Great China | FAE (Ryan Li)
WW31 | Richy | Richy Ye | 0 | 0 | Wireless Charger | Phihong | WCT | MWCT1000CFM | DW |  | Wireless TX for Philips toothbrush | $2.4M | 1-1UQP3XD |  |  |  | 1kU MWCT1000 was shipped to Philong in July, it turns to design win. | New Requirement | Customization | General | Great China | FAE (Beta Chen - B44998)
WW31 | Richy
WW31 | Richy
WW31 | Richy
WW31 | XD | haidong | 2 | 7 | WirelessConnectivity/IoT | Honeywell | Kinetis W | KW41 | Early Evaluation |  | Home Automation |  |  |  | IAR |  | 1: Help them upgrading Thread Stack to Shanghai internal 1.0.1.12, that resolved their Thread node routing outside issue. 2: Answer their question about Thread DTLS handshake J-PAKE. |  |  |  | Great China
WW31 | XD | HuTeng | 3 | 3 | WirelessConnectivity/IoT | LGE | Kinetis W | KW41 | Early Evaluation | [7 empty] | 1. Test BLE power consumption using newest software version provided by RD team; 2. Try to make some optimizations and till now, I think we have done the best we can, and RD team should step further to refine our both hardware and software
WW31 | XD | haidong | 1 | 1 | WirelessConnectivity/IoT | AVNET | Kinetis W | KW40 | Early Evaluation | [7 empty] | Look into the AVNET ticket about KW40 FEM module FAD feature, try to understand this issue and repeat it at my side, had sent ticket to FAD owner Keith, waitting for response. |  |  |  | Great China
WW31 | XD | Chu Hongdong | 3 | 40 | ePOS/Security | Landi | i.MX | i.MX6UL |  |  | ePOS | 500K | #1-1PPBZ7A | HAB,CAAM,SNVS,Dryice,BEE | Yocto | Implement security features. | Porting RSA key generation to i.MX6UL security library, setup android environment and build security library for android platform, send updated pkha example code to Landi. |  | Customization | Key | Great China
WW31 | XD | Yang Zhao | 5 | 5 | Security | 深圳大趋科技 | Kinetis K | kl81 | [7 empty] | SM2 on kl81 | 1.Fix the bug of our sdk which will lead to the memory lead problem 2.Change the API of our SDK so that customer can use their our malloc&free function. |  | Customization | Key | Great China
WW31 | XD | Liu Weiping | 0.5 | 0.5 | Security | BBPOS | Kinetis K | K21 | [7 empty] | Random generator test | 1. The DRBG code of BBPos can't pass the random test with STS tool . 2. Corrected some wrong settings and give some suggestions after check their DRBG code. |  | Customization | Key | Great China
WW31 | XD
WW31 | XD
WW31 | XD
WW31 | XD

## Reference Design
Week | Team | Apps Engineer | Open Date | Close Date | Effort (man- days) | Total Effort | Family | Segment | Project | Reference Phase | Milestone Date | Progress record
WW31 | Sherry
WW31 | Sherry
WW31 | Sherry
WW31 | William
WW31 | William | wang peng | 2016-05-16 |  | 2 | 14.5 | Kinetis L | Industry | iPOS | Design - evaluation |  | Capture ADC data and use Matlab help to analysis it, some failed case is recorded that it has the lower amplitude when slowly swipe cards or cards is weak magnetic, and signals amplitude is vary during some swiping, which can't trigger the threshold and lead to reading card fail, workaround is on-going.
WW31 | William | Jia Ding | 2016-07-12 |  | 2 | 8.5 | Kinetics |  | KEED | Development |  | Finished LPC54102's KEED project. For now, all of the assigned parts' ULPBench and KEED projects have been completed.
WW31 | William
WW31 | William
WW31 | William
WW31 | William | YangXi | 25/7/2016 | 27/7/2016 | 2 | 118 | Kinetis K | Industry | QR decoder | promotion support |  | 1. assembly 2 x TWR QR decoder hardware for marketing to customer promotion. customer name is: XGD and WHTY. 2. Discuss with SOC team about QR decoder use case on K4TV. summarized a report about QR decoder demo workflow and also provide key timing specification at different CoreClock and different camera output frame rate.
WW31 | William | Zhong Juying | 2015-06-06 |  | 3.5 | 3.5 | Kinetis K | Security | RSA & ECC with DPA countermeasure | Development |  | "1.improve blinding method on RSA countermeasure as below: 1.1 did some try on an improved blinding method. blinding message and spliting exponent(E1, E2, .... En), then calculated mod_exp for E1 to En. ----- Done 1.2 implemented a policy for randomly inserted dummy exponent. ---- Done 1.3 implemented a policy for recoverying the real result of mod_exp. ---- Done 1.4 will continue to do debug and testing ---- met some problem on obtaining a correct result, finished to adjust policies designation, finished to solve memory problems and sucessfully verified spliting exponent countermeasure in normal values mode; had a problem in Montgomery values mode and found that blinding message don't be supported by LTC ---- on-going to debug the known problems"
WW31 | William
WW31 | William
WW31 | William
WW31 | Eric | Shi Changhao, Terry Lv | 2015-11-16 |  | 1 | 134 | Kinetis W |  |  | Development |  | 1. Continue to code on smart home application. 10% finished.
WW31 | Eric
WW31 | Eric
WW31 | Eric
WW31 | Eric
WW31 | Eric
WW31 | Richy | Liu Zhen, Ding Wenshuang | 2016-03-10 |  | 5 | 58 | S08 | Motor Control | SU16-edrone | Development |  | 1,Added 150 degrees algorithm to decrease running noise, it's effective. 2,Added openloop state and acceleration parameter,now it can startup sucessfully every time though the startup time is a bit longer.
WW31 | Richy | Wang Dechang, Jiang Dengyu, Wang Li, Zhao ping | 2015-11-25 |  | 4.5 | 61.5 | WCT | Wireless Charger | WCT-15WTXAUTO | Design |  | 1. Received 22 sets of 15W AUTO TX boards; 2. Debugging the small DCDC boards(Non-sync & Sync SEPIC converter, Non-sync & Sync buck-boost converter) and the boards are ok now; 3. Estimated the efficiencies of different DCDC converters, at about 10.5V/2.5A load the sync buck-boost efficiency is about 93%, which is about 10% higher than that of non-sync SEPIC & 8% higher than that of sync SEPIC; 4. Modified peripheral and GPIO configuration, and debugged on the boards, the control logic and basic charging function worked, and can charing the LP RX with full load.
WW31 | Richy | Wang Dechang, Zhang Yangjie, Richy Ye, Gao Xiang, Wang Lingling | 2015-08-06 |  | 3 | 453 | DSC | Digital Power | Golden Server Power-Totem Pole BLPFC | Design |  | 1.Tested 3 prototypes, and verificated the performance difference between the differnce boards, and hte reuslt is OK. 2.Continued to write Totem PFC DRM, 35% completed. 3.Get familiar with latest code and set up the system working environment (SHA Team).
WW31 | Richy | Li Shunan | 2016-02-18 |  | 4.5 | 26 | DSC | Motor Control | Close-loop step-servo drvier | Development |  | 1. Move the field weakening algorithm from slow loop into fast loop, and set the cut-off frequency of error filter as 1-2kHZ, and then the vibration at high speed (more than 1500RPM) is reduced a little. 2. Connect the MOONS step-servo motor to the driver board, and it run well under 1500 RPM. But it can not speed up to 3000 RPM. This problem is being deal with now.
WW31 | Richy | Howard Liu, Richy Ye | 2014-09-20 |  | 1 | 56.5 | DSC | Motor Control | Sensorless FOC e-Sooter -MC56F82728 | Development |  | PM, h/w and application s/w status: 1) The provider of the selected MOSFET transistors purchasing was found and the purchasing is in process. The new board will be available soon. IDH told that the new boards would be tested for power only. China NXP team will help with testing the new board functions. 2) Asked Bosch for performance report of the motor shipped last time. Sent the performance report and the nominal power data to Roznov team. MC software status of development and test (From Roznov team): The M1 scooter features regenerative braking. This feature was also added to our solution. When the brake lever is pulled, the scooter starts to break (negative Id current is applied) and the energy is stored back to battery. The maximum allowable battery voltage and charging current is considered. Since the Pb gel batteries on original old scooter can be charged by 6 A only, the braking torque is not significant. The function works very well when the Hall sensors are used in entire speed range. When Back-EMF observer is used for position detection, the operation is instable in speed below 50% of nominal speed. Further investigation reveals that Back-EMF observer is loosing the precision of calculated position, when significantly higher negative Id current is demanded. Together with Jaroslav we performed deep dive into the Back-EMF observer algorithm structure in order to find-out the reason of the issue (improper motor parameters identification or bug in algorithm implementation). The investigation is in progress.
WW31 | Richy | Jiang Dengyu, Mao Huan, Richy Ye | 2014-10-04 |  | 2.5 | 488 | WCT | Wireless Charger | WCT-15W1COLTX | Development |  | 1, Tried to use dynamic limit to realize maximum voltage protection; record some data to use step curve to set limit, need more tests. 2, Gave answers to customer's question document about 15w 1 coil project. 3, Completed the draft version datasheet for new added WCT1011 part.
WW31 | Richy | Richy Ye, Wang Dechang, Jiang Dengyu, Kevin Cheng, Gao Xiang, Wang Lingling | 2015-03-23 |  | 5 | 214 | DSC | Digital Power | Golden Server Power | Design |  | 1, Got the bode plot of period to resonant current and period to output voltage by Psim, and designed the 2P2Z controller according to the bode plot. Modified the software with the new controller and tested it, it turns out that the controller designed by this method is well fit for our system, stable with good dynamic performance. However, there are still some little problem need to be debugged. 2, Complete final review of LLC design reference manual, provide the comments to back to doc team.
WW31 | Richy | Gao Xiang | 2015-02-01 |  | 1 | 192 | WCR | Wireless Charger | WPR1500 LDO/BUCK MPRX | Development |  | 1, Complete FreeMASTER GUI for MPRX, include current calibration, FOD calibration and system control. 2, The timing constraint required in v0.9 spec is conflict when working with 110kHz A13, which will cause the wrong count value and was removed in V1.2.2 spec, fix the bug in WPR1500 V2.0 code, verified success.
WW31 | Richy
WW31 | Richy
WW31 | XD | Hu Teng | 2016-06-20 |  | 2 | 23 | Kinetis W | WirelessConnectivity/IoT |  |  |  | 1. Refine current BLE and Thread hybrid demo on KW41 2. Study MDNS, about its packet format, protocol and usage; Check our own MDNS and TMDNS code in current Thread project
WW31 | XD | Haidong | 2016-01-04 |  | 2 | 84 | Kinetis W | WirelessConnectivity/IoT |  |  |  | Complete upgrading our internal Thread network stack from 1.0.0.35 to 1.0.1.12.
WW31 | XD
WW31 | XD
WW31 | XD
WW31 | XD
WW31 | XD
WW31 | XD

## Apps Lead
Week | Team | Apps Engineer | Open Date | Close Date | Effort (man- days) | Total Effort | Family | Project | NPI Phase | Next Apps Milestone | TO Date | Enablement Task | Highlight/Lowlight/Issues/Risks | Progress record
WW31 | Sherry
WW31 | Sherry
WW31 | Sherry
WW31 | William
WW31 | william | Wang Hao | 2016-05-30 |  | 1 | 21.5 | Kinetis K | K4TV | Plan | Execution | Aug 11st | System Cases |  | Plan to develop FlexSPI driver based on existing QuadSPI driver in KSDK, associated header file need to be created by SE team as header file delivered by BACES team is in different style than KSDK.
WW31 | william
WW31 | william | Guo Jia | 2016-07-11 |  | 4 | 9 | Kinetis L | L5K | Launching |  |  | Documentation - Application Notes |  | 1. Finished draft of AN - Using LPSPI on KL28 and sent out for review. Updated the workaround for the limitation that continuous mode is not available for multi-IO mode. 2. AN - Using TRIGGER MUX on KL28 is going on.
WW31 | william | Guo Jia | 2016-07-25 |  | 0.5 | 1 | Kinetis L | L5K | Launching |  |  | Documentation - RM |  | Found some issue in the RM, and work with document team to correct it.
WW31 | william
WW31 | william
WW31 | Eric | Wang Ben | 2015-11-23 |  | 2 | 87 | Kinetis E | MT512P | Execution | Documentation - AN ready 8/20 | Q1'16 | System Engineering |  | 1.HVP-KE18F production factory test is done.Reviewed the test report is ok.Worked out single board FCC test code for HVP-KE18F,team will use the rework board to run FCC at Shanghai Murata FCC lab. 2.Finish writing the TWR-KE18F UG, under review by internal team. 3.Answerd FAE several questions about KE18F headfile.
WW31 | Eric | Ben Wang, Chen Xinyu, Cao Nan, Song Juanjuan | 2016-06-24 |  | 10 | 57.5 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | 1. Tested and recorded the KPET raw data of some modules: FTM,FlexIO Uart\I2C\SPI. 2. Learning the KPET backend database XML format. 3. Finished creating the chip files and some IP equation files. Successfully loading the chip information in the offline tool. 4. Learning the KPET uiLayout. 5. Refined the BASELINE IDD test program, and uploaded into the git repo. 6. Found the communication peripheral adder results are highly impacted by the external loading, like connected slave or not, have lacquered wire connected on the pin or not. Sent email to US Apps to know what exact test method they did on K22/KL27.
WW31 | Eric | Wang Ben | 2016-02-01 |  | 0.5 | 9 | S08 | MC9S08SU16 | Execution | Marketing launch Q4'16 | Q1'16 | Tools Support |  | 1.Per marketing request, did some tests on S08 production with IAR. We may need IAR to support SU16 to replace CW. 2.Answered several questions from DELTA RD about the SD8 GDU AMP usage and configuration.
WW31 | Eric | Fang Yizhou | 2016-07-18 | 2016-07-29 | 5 | 9 | i.MX | i.MX6ULL | Execution | Documentation-HUG,HDG,QSG,Power Consumption 8/16 | Q4'15 | System Engineering |  | 1. Revise the DQS Capacitors,eMMC, NAND, 24M crystal and company logo. 2. Give comments on the 6UL C4 version. Its DDR circuit and two capacitors need to be revised. 3. Compare every part, circuit and details of 6ULL A version and 6UL C4 version. Make sure both schematic work and align. 4. Give tips to layout guys about the difference of 6ULL A version and the 6UL C3 version. 5. Finish the 6ULL schematic A version.
WW31 | Eric
WW31 | Eric | Chen Xinyu | 2016-03-25 |  | 0.5 | 13.5 | Kinetis E | MT512P | Execution |  | Q1'16 | Documentation - Data Sheet |  | 1. Updated the LPI2C performance and timing test results into DS. All I2C modes are supported. 2. Refined the LPI2C and LPSPI peripheral adder test program, and co-work with BACES to get data. Now the all of the peripheral adder under 25degree have been tested, except the RTC and LPTMR, which will be finished in WW32. 3. The ADC linearity testing is on going in PE side.
WW31 | Eric | Chen Yonggang | 2016-07-25 | 2016-07-29 | 6 | 12 | Kinetis E | KE15Z | Execution | TSI EVB software/appnotes ready 8/15 | Q4'15 | System Cases-KPET |  | 1. Developing demo software on TSI reference board, 50% done. Tested the proximity feature and found the best distance is 1cm, much worse than competitor 10cm. 2. Communicated with ADC IP owner and made the ADC calibration checking method clear, so the calibration related code won't block SDK GA release. ADC calibration appnotes AN5314 is available on nxp.com now http://www.nxp.com/doc/AN5314. 3. Updated datasheet CMP chapter, filled the correct typical/max data tested by PE/ATE. 4. Updated Clocking and CMP KE web training slides by adding keynotes. 5. Reviewed the schematic of the touch demo board that customer Electrolux developed based on KE15Z256, gave comments on TSI mutual channel arrangement, and mutual mode can work under 3.3V, so the 3.3V/5V level shift devices can be removed. 6. Answered Jap FAE questions on TSI for Toshiba refrigerator project. Toshiba is using Cypress CY8C4125 as touch sensor MCU for the door open feature, and customer want to know whether KE15Z supports 10cm thick overlay and 3cm distance proximity. 7. Answered Jap FAE question on KE1xF cache control that does cache need to be disabled from RAM. Provided FAE cache example code to show that KE1xF doesn't need to disable cache from RAM, but need to push any modified contents before disable cache, and invalidate before enable.
WW31 | Eric
WW31 | Eric
WW31 | Richy | Howard Liu | 2015-07-16 |  | 3 | 109.5 | Kinetis E | MT512P | Execution |  | Q3'16 | System Cases |  | MT512P NPI: 1) Modified the low-level peripherals initialization codes for Rev1.0 chip and SDK2.0 release. The PWMs and their synchronization worked as correctly as the design expectation. Two PWMs with 180 degree phase shit were implemented also for interleave PFC. 2) During the system timing test, found that the MCU failed start on POR reset. If downloading image through JTAG and run, MCU worked well. But system couldn't work after power up and must be reset more than twice by reset button. The issue check was still in process. 3) Found Channel(n+1) had no output in combine mode if setting COMP=0 that's same as channel(n) according to the RM document. Asked design team check it.
WW31 | Richy
WW31 | Richy
WW31 | XD
WW31 | XD
WW31 | XD
WW31 | XD
WW31 | XD

## Others
Week | Team | Apps Engineer | Open Date | Close Date | Effort (man- days) | Total Effort | Item | Segment | Family | Part | Module | Tools | Request brief | Overal Progress | Input Source
WW31 | Sherry
WW31 | Sherry
WW31 | Sherry
WW31 | Sherry
WW31 | William
WW31 | William | Wang Peng | 2016-02-24 | 2016-07-29 | 2.5 | 5.5 | translation review |  | Kinetis S | KS22 | USB |  | review the translation of KS22 reference manual | Finish the translation revview of USB and SAI chapter of KS22, totally 125 comments are added.
WW31 | William
WW31 | William | YangXi |  |  | 1 | 1 | FlexIO usecase |  | Kinetis L | KL28 | FlexIO |  | KL28 use case pool maintain and update: | KL28 use case pool maintain and update: 1. Collect information and code for FlexIO design contest demo. Will add valuable demo into KL28 use case pool. Selected 3 most valuable demo for design contest and will porting to KL28: a. Using FlexIO drive LCD/camera(Done) b. Using FlexIO drive servo motor c. Using FlexIO drive 1-wire bus device(DS18B20 temperature sensor) 2. Begin coding for FRDM-K64 as device programmer host to program code to a target offline
WW31 | William
WW31 | William
WW31 | William
WW31 | William
WW31 | William
WW31 | William
WW31 | Eric | Cao Nan | 2016-07-28 | 2016-07-29 | 2 | 2 | Create a simple PPT about IAR and CW for marketing |  | S08 | MC9S08PT60 |  |  | Evaluated the IAR performance to support S08 and compared with CodeWarrior. | Create a simple PPT,include: 1.User experience: easy use, features etc. 2.Binary code size after compiling versus CodeWarrior . 3.Execution speed versus CodeWarrior . 4.Debugging / tracking features and convenience.
WW31 | Eric
WW31 | Eric
WW31 | Eric
WW31 | Richy | Liu Zhen | 2016-07-28 | 2016-07-28 | 0.5 | 0.5 | Marketing support/other |  | S08 | SU16 |  |  | Marketing support/other | Sent one reference board to FAE to promote customer per marketing request, and answered some questiones they raised
WW31 | Richy | Zhou Xuwei | 2016-07-25 | 2016-07-27 | 1 | 1 | WT Support |  | DSC | 56F82748 |  |  | WT had a customer who needs to replace all their brushed DC motor with BLDC in three years. FOC is required due to noise. | Bryan is working on their motor using DSC, but found the speed was limited to half the nominal speed. I helped him to check the code and locate the root cause. There's something wrong with ADC channel settings and the PWM period constant is half the real value, which led to this problem.
WW31 | Richy | Richy Ye | 2016-07-28 | 2016-07-28 | 0.5 | 0.5 | FAE support | Motor Control |  |  |  |  | Motor control on UAV | FAE is collecting NXP solutions information for UAV promotion program. Supported the NXP motor control solutions on UAV for integration.
WW31 | Richy
WW31 | Richy
WW31 | Richy
WW31 | Richy
WW31 | Richy
WW31 | Richy
WW31 | XD | Chu Hongdong | 1/4/2017 |  | 2 | 28 | Side channel test |  | i.MX |  |  |  |  | Prepare DES softDPA image and user guide for side channel test, need check the trigger signal on i.MX6UL EVK board.
WW31 | XD | Liu weiping | 2016-06-13 |  | 4.5 | 25.5 | POS solution |  | i.MX |  |  |  |  | 1. Read the code of NFC linux module. 2. Start coding the NFC card reading Application.
WW31 | XD

## List_Def
Team | Segment | Family | Part | Customer Phase | Reference Phase | NPI Phase | Module | Tools | Root cause | Solution | Support Type | Source | Enablement Task | Support Region
KM | Automotive | S08 | i.MX53 | Early Evaluation | Design | Concept | USB | KSDK | Ctm S/W defect | Fix - Erata/JIRA | General | FAE | Documentation - Data Sheet | Japan
Sherry | Consumer/Communication | CF | KM34Z64 | DI | Development | Feasibility | ADC | PEx | Ctm H/W defect_D | Workaround | Key | BD_MKT | Documentation - Errata | Korea
Manish | Industry | DSC | KM34Z256 | DW | Integration | Plan | I2C | MQX | EMC | Customization | Professional Service | NPI_MKT | Documentation - RM | Great China
Lily | eReader | Kinetis L | KM34Z128 | Pilot | Reference Release | Execution | SPI | Linux | Design issue | Demo/Reference | Leverage | Sales | Documentation - Application Notes | Globe Transition
Robin | Security | Kinetis E | KL17 | MP | SoW | Launching | TSI | Android | Design limitation | Benchmark | BD Activity | Unknown | Documentation - Others | Community
Richy | Wireless Charger | Kinetis M | KM14Z64 | DL | Lib Release |  | AFE | WinCE | RM defect |  |  | CQI | System Cases | NA
William | Motor Control | Kinetis V | ​MK60DN512 |  | Documentation |  | GPIO | CW10.6 | DS defect |  |  |  | System Engineering
Eric | Digital Power | Kinetis K | MC56F82313 |  | Testing |  | ENET | IAR | System improvement |  |  |  | Board - Design
XD | WirelessConnectivity/IoT | Kinetis X | MC9S08PT16AVLD |  |  |  | QTimer |  | Driver issue |  |  |  | Board - FAT Coding & test
| Smart Grid | Kinetis W | MK64FN1M |  |  |  | JTAG |  | Ref board issue |  |  |  | Board - Document
| Industry-Touch | i.MX | MWCT1012CFM |  |  |  | FLASH |  | New Requirement |  |  |  | Certification - USB
| Industry-HomeAppliance | WCT | MKE02Z32 |  |  |  | UART |  | SW issue |  |  |  | Certification - Others
| Power | WCR | MC56F82723 |  |  |  | I2S | [5 empty] | Training
|  |  | MC9S08SD8 |  |  |  | DAC | [5 empty] | Alpha Customer Support
|  |  | KL16Z128 |  |  |  | FlexIO | [5 empty] | Tools Support
|  |  | KE18Z |  |  |  | LPIT | [5 empty] | Bug analysis support
|  |  | MKV10Z32VFM7 |  |  |  | LPTimer | [5 empty] | SDK Driver
|  |  | KE18F512VLL15 |  |  |  | LPTPM | [5 empty] | System EMC
|  |  | MC56F84789 |  |  |  | Flextimer | [5 empty] | System Cases-KPET
|  |  | MC9S08PA16AVWJ |  |  |  | PWT | [5 empty] | System Cases-BLDC demo
|  |  | MT512P |  |  |  | PDB | [5 empty] | System Cases-Peripheral adder
|  |  | KE15Z |  |  |  | PIT | [5 empty] | Board - OOBE
|  |  | KL17Z32VFM4 |  |  |  | eFlexPWM
|  |  | MC9S08SU16 |  |  |  | DMA
|  |  | i.MX6RT |  |  |  | WDOG
|  |  | KW41 |  |  |  | EWM
|  |  | K81/i.MX6UL |  |  |  | SIM
|  |  | KE06 |  |  |  | MCG
|  |  | KL02 |  |  |  | SCG
|  |  | KS22F256N |  |  |  | OSC
|  |  | K21 |  |  |  | ICS
|  |  | MC908AB32CFUE |  |  |  | LLWU
|  |  | MC9S08PT60 |  |  |  | RCM
|  |  | MWCT1001A |  |  |  | PMC
SMC
SAI
RTC
CRC
CAN
ESDHC
ACMP
VREF
DryICE
RNGA/TRNG
CMT
QDecoder
AMP
DDR
LCD
KBI
FlexNVM
IRQ
FlexBus
CM0+
CM4
CACHE
OPAMP
bootROM
Radio
Note on L2: Author: General Customer Support
Note on L3: Author: Key Customer Support
Note on L4: Author: Professional Service
Note on E5: Author: pre mass production
Note on L5: Author: Leverage to general base from customer support
Note on N8: support enablement tools such as register header files validation, debugger svd file validation and etc
Note on N9: support PE/design to do bench test on bugs