## Customer Support
Week | Team | Apps Engineer | Effort (man- days) | Total Effort | Segment | Customer | Family | Part | Customer Phase | MP Date | Product | LTR ($M) | GIBC | Module | Tools | Request brief | Progress record | Root cause | Solution | Support Type | Support Region | Input Source | Community Link (Mandatory)
WW39 | Sherry
WW39 | Sherry
WW39 | Sherry
WW39 | Sherry
WW39 | Sherry
WW39 | William
WW39 | william | Wang Hao | 1 | 1 | Security | Wuhan Tianyu | Kinetis K | MK81FN256V | DI |  | mPOS | 1 |  | DryICE |  | Customer reported problem for tamper trigger when only VBAT is powered. | Customer reported tamper does not get triggered when only VBAT is powered and MCU VDD not powered. After MCU VDD powers up, no tamper event triggered. Reviewed customer code, found there is explicit tamper clear code inside dryice init routine which clears tamper event. After fixing this software issue, tamper can be triggered. | Ctm S/W defect | Workaround | General | Great China | FAE (Hanson He)
WW39 | william | Wang Peng | 1 | 4 | Consumer/Communication | wuhan tianyu | Kinetis K | k81 | DI |  | smart pos |  |  | QSPI |  | Support to solve the issue about QSPI application | Debug QSPI base on customer board, modify code and fix the issue, and it can support QSPI flash working with quad mode now, and this project go smoothly. |  | Customization | General | China | FAE | https://community.nxp.com/message/826303
WW39 | william
WW39 | william
WW39 | william
WW39 | William
WW39 | William
WW39 | William
WW39 | William
WW39 | William
WW39 | Eric | Wang Ben | 0.5 |  | Industry | Media | S08 | MC9S08LL16 | MP |  | Remote Controller |  |  | OSC |  | Customer found some MCU's crystal cannot start up successfully，FAE doubts it caused by the unmatched characteristic between MCU and crystal.Customer is using one of the OSC circuits recommended in Datasheet(low range，low power mode，without any resistor or capacitance).But the internal incorporated R and C value are not listed on datasheet. | Consulted with OSC IP owner about the component value.The RF is around 100M, and the value of C1=C2 are around 16~18pF. Feedback to FAE and will go on investigating why the startup is failed. |  |  | General | Great China | Community | https://community.nxp.com/message/833281?commentID=833281&et=notification.mention#comment-833281
WW39 | Eric
WW39 | Eric
WW39 | Eric
WW39 | Eric
WW39 | Eric
WW39 | Eric
WW39 | Richy | Li Shunan | 3.5 | 18 | Motor Control | Supcon Hangzhou | DSC | MC56F84786 | DI |  | Stepper Servo Driver for Solar Panel |  |  | System | CW10.6 |  | Customer and the distributor ZLG visited our Suzhou lab last Wednesday: 1) Explained all the problems on the 1st hardware to customer. Customer admitted these problems and would make 2rd hardware. 2) Showed our stepper servo reference to customer. Customer are very satisfied with it and say that our reference design has an advantage over their previous solution provided by TI which is a kind of open-loop stepper driver. 3) Due to the 2rd hardware is a 2in1 stepper servo driver in customer's plan, choose DSC MC56F84786 as the core MCU replace with KV4X. Designed and sent the pinout of 2in1 stepper servo to customer. 4) Customer say that they have 3 orders, 90k in total, from their customer by now, and the MP date is the second half of 2017. | New Requirement | Customization | General | Great China | FAE - Zhuang Chao
WW39 | Richy | Ethan Cheng | 3 | 3 | Consumer/Communication | Foxlink | Kinetis L | KL27 | DI |  | USB mouse | 0.15 | 1-21RRXAG | USB |  | Problem about KL27 USB certification | Supported FAE to clarify customer’s problem on KL27 USB certification, and then full-speed peripheral test was passed. Looking into remote wake function of KL27 HID mouse so far. | New Requirement | Customization | General | Great China | FAE (Stanley Huang-B42861)
WW39 | Richy | Liu Zhen | 1 | 2 | Motor Control | Gree | Kinetis E | MKE02Z32 | Early Evaluation |  | Indoor Fan |  |  |  | IAR | PMSM solution for indoor fan | Debug the program based on our HVP platform and customer's fan. Solved the issue that dynamic performance is poor when speed is higher than 650rpm. Root cause is that the current sample time is not enough in high speed range. Tried SVMU0n function, the electromagnetic noise is obvious. finally I chose 8K PWM frequency, 10M ADC clock and SVMStd function, now the indoor fan can run up to full speed 1400rpm. | System improvement | Customization | General | Great China | FAE(Yu Yang)
WW39 | Richy | Zhao Ping, Richy Ye | 2 | 6.5 | Wireless Charger | Leggett & Platt | WCT | WCT1003A | Early Evaluation |  | 5W Automotive Power Transmitter |  |  |  |  | Training about CodeWarrior and QuickStart | 1, Prepared training materials about CodeWarrior and QuickStart. 2, Did the training to Leggett engineer. | New Requirement | Customization | General | Globe Transition | Charlie Wu
WW39 | Richy | Liu Zhen | 1 | 3 | Motor Control | HongRi | S08 | MC9S08SU16 | DI |  | Power Tools |  |  |  | CW10.6 | BLDC solution for power tools | Answered some questions they raised. Hongri's engineer report that debugging is completed, and the motor can run basically now. | New Requirement | Customization | General | Great China | FAE(Liu Huabo)
WW39 | Richy | Jiang Dengyu | 1 | 1 | Wireless Charger | Leggett & Platt | WCT | WCT1013A | Early Evaluation |  | WCT-15WTXAUTO |  |  |  |  | Schematic review | 1. Checked L & P 15W automotive TX schematic and gave comments; | New Requirement | Customization | General | Globe Transition | Charlie Wu
WW39 | Richy | Kevin Cheng | 0.5 | 5 | Digital Power | Delta Chungli Telcom | Kinetis V | MKV5x | Early Evaluation |  | Telcom power supply |  |  |  |  | next generation platform survey | 1) Customer asks references for VSC(valley switching control), slua644 describes details for VSC or ZVS. Explain to FAE that is an advanced contorl technique, and customer can implemented it easily on their platform. 2) provide performance measurement based on core rate and no wait memory size between STM32F334 and MKV44F128. |  |  | General | Great China | FAE(Moris Hsu) | http://www.ti.com/lit/an/slua644/slua644.pdf
WW39 | Richy | Kevin Cheng | 3 | 3 | Digital Power | Liteon | DSC | MC56F82748 | Early Evaluation |  | Digital Power supply |  |  |  |  | NXP power solution survey | Received totem-pole PFC referece design, combined PFC and LLC board and test result is same with internal. Writing Slides for customer engagement. |  | Demo/Reference | Key | Great China | FAE(Jiunn Yang)
WW39 | Richy
WW39 | Richy
WW39 | Richy
WW39 | Richy
WW39 | Richy
WW39 | Richy
WW39 | Richy
WW39 | Richy
WW39 | Richy
WW39 | Richy
WW39 | Richy
WW39 | Richy
WW39 | Richy
WW39 | Richy
WW39 | Richy
WW39 | Richy
WW39 | Richy
WW39 | XD
WW39 | XD
WW39 | XD
WW39 | XD
WW39 | XD
WW39 | XD
WW39 | XD
WW39 | XD
WW39 | XD
WW39 | XD

## Apps Lead
Week | Team | Apps Engineer | Open Date | Close Date | Effort (man- days) | Total Effort | Family | Project | NPI Phase | Next Apps Milestone | TO Date | Enablement Task | Highlight/Lowlight/Issues/Risks | Progress record
WW39 | Sherry
WW39 | Sherry
WW39 | Sherry
WW39 | William
WW39 | william | Wang Peng | 2016-08-10 |  | 2 | 14 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases |  | BACEs find the TSI_adder code has big adder current when trigger TSI, and also confirm it can up to 8mA in my side, however, TSI low power demo don't have bigger currents(just more 500uA), maybe the different configuration result it, and try to find the root cause.
WW39 | william | Jia Ding | 2016-08-01 |  | 4.5 | 13 | Kinetis K | K4TV | Plan | Execution |  | System Cases |  | Studied the FlexSPI module and the oct-flash device. Finished part of the FlexSPI driver based on the KSDK2.0 framework.
WW39 | william | Wang Hao | 2016-05-30 |  | 2 | 14 | Kinetis K | K4TV | Plan | Execution |  | System Cases |  | Start precoding for CAUv3 module based on KSDK2.0 based code framework.
WW39 | william
WW39 | william
WW39 | william
WW39 | Eric | Wang Ben | 2016-11-23 |  | 3.5 | 106.5 | Kinetis E | MT512P | Execution | Launching | Q1'16 | System Engineering |  | 1.Support launch marketing to do production launch stuff before FTF.All the KE1xF documents have been posted on NXP web page, including DS, RM, Errata, TWR UG and Application Notes. 2.System has officially raised CR to to change the test freq from current 25MHz to 26.67MHz. PE/TE and NVM team is evaluating the effort needed. 3.DAPlink issue on TWR-KE18F is still not resloved by Michal.He will deliver one "workaround" version of masking UID read.
WW39 | Eric | Wang Ben | 2016-06-24 |  | 1 | 16.5 | Kinetis E | KE15Z | Execution | Launching | Q4'15 | System Cases-KPET |  | 1.Revised ftm, flexio_uart,flexio_i2c, flexio_spi adder code to support 8Mhz/4Mhz/2Mhz/1Mhz functional clock source.
WW39 | Eric | Cao Nan | 2016-06-24 |  | 3 | 107.5 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | 1.Dynamic association the result with different clock source and power mode. Maybe we have to test some new case with clock source(SOSC 8M SIRC 8M) and power mode(VLP mode). 2.Update UIlayout. 3.Revised LPI2C ,LPSPI, LPTMR , LPIT ,LPUART adder code to support 8Mhz/4Mhz/2Mhz/1Mhz functional clock source.
WW39 | Eric | Chen Yonggang | 2016-09-18 | 2016-09-23 | 6 | 54 | Kinetis E | KE15Z | Execution | Touch demo for FTF on 9/28 | Q4'15 | System Cases-KPET |  | 1. Finished touch demo tuning for FTF based on NT2.0 library. Fixed the bug of slider detector of the library and shared the solution to library developer to improve the NT2.0 touch library. 2. Updated KE15Z datasheet by adding STOP/VLPS current consumption with BIAS enabled/disabled options, and removing all ECC info per Marketing request. Now the DS is ready for KE15Z launch. 3. Supported BACES team finish the TSI KPET test. Under 5V power supply and triggered by 5ms LPTMR, the current consumption is around 180uA for TSI self mode and 2300uA for TSI mutual mode.
WW39 | Eric
WW39 | Eric
WW39 | Eric
WW39 | Richy
WW39 | Richy
WW39 | Richy
WW39 | XD
WW39 | XD
WW39 | XD
WW39 | XD
WW39 | XD

## Reference Design
Week | Team | Apps Engineer | Open Date | Close Date | Effort (man- days) | Total Effort | Family | Segment | Project | Reference Phase | Milestone Date | Progress record
WW39 | Sherry
WW39 | Sherry
WW39 | Sherry
WW39 | William
WW39 | William | wang peng | 2016-05-16 |  | 2 | 23.5 | Kinetis L | Industry | iPOS | Design - evaluation |  | Refine the MSR decode code, and improve the 3-track decoding rate up to about 80%,and update code to share point and share to team.
WW39 | William
WW39 | William
WW39 | William
WW39 | William
WW39 | William
WW39 | William
WW39 | William
WW39 | William
WW39 | William
WW39 | Eric | Shi Changhao, Terry Lv | 2015-11-16 |  | 5 | 167 | Kinetis W | WirelessConnectivity/IoT | Smart Home | Development |  | 1. Finish smart lock reference design first version. RSSI Auto and Mannual Lock/Unlock are supported. 2. Prepare the smart lock reference design demo and sent to Shenzhen FTF for demo.
WW39 | Eric
WW39 | Eric
WW39 | Eric
WW39 | Eric
WW39 | Eric
WW39 | Richy | Wang Dechang, Zhang Yangjie, Richy Ye, Gao Xiang, Wang Lingling | 2015-08-06 |  | 10 | 516 | DSC | Digital Power | Golden Server Power-Totem Pole BLPFC | Design |  | 1,Optimized the hardware filter and software control loop parameter, now there is a version for both AC source and E-power, which PF and THDi can meet the design demand, 600W THDi < 5%. 2, Solved the light mode issue, now the system can enter and exit the light mode stably. 3, DRM modification is completed according to all comments, SCH, PCB and BOM doc are ready for release.
WW39 | Richy | Wang Dechang, Jiang Dengyu, Wang Li, Richy Ye | 2015-03-02 |  | 7 | 233 | WCT | Wireless Charger | WCT-15WTXMULTI | Design |  | 1. Prepared the test code for Qi compliance test. Enabled the free resonance Q factor measurement, fixed the bug of inaccurate PWM pluse. But the test result in Intertek lab is not so good, the meausred Q factor is unstable. Need more debug. Enabled the MVL function on MultiCoil platform; 2. Supported Emma for the Qi compliance test in Intertek. Found some issues in the test, like Q factor measurement and so on. Will do more optimization for the issues found in furture.
WW39 | Richy | Ding Wenshuang Liu Zhen | 2015-08-26 |  | 1.5 | 95 | Kinetis E | Motor Control | Low Cost PMSM sensorless solution-MKE02Z64 | Reference Release |  | 1,Finished cleaning code and test the reliability of HVP PMSM FAN project for solution release, have sent the code out for open source conflict check.
WW39 | Richy | Wang Dechang, Jiang Dengyu, Wang Li, Zhao Ping, Richy Ye | 2015-11-25 |  | 7 | 118 | WCT | Wireless Charger | WCT-15WTXAUTO | Design |  | 1, Updated the schematic and layout design documents according to NFC team’s comments, and got the positive feedback from NFC team in the further check, and we’ll freeze the layout design and export the manufacturing documents; 2, Received 10 pcs coil samples from TDK, and assembled WCT-15WTXAUTO samples with WCT1011A & WCT1013A, also sent one WCT-15WTXAUTO prototype to NFC team for debug ; 3, Reworked WCT-15WTXAUTO prototypes for Q factor detection. 4, Modified Q factor detection code and Q factor is right now. 5, Tested quick start service pack for WCT1011A and WCT1013A. The service pack can work normally. 6, Porting NFC stack. Modified the low-level configuration for NFC.
WW39 | Richy | Liu Zhen, Ding Wenshuang | 2016-03-10 |  | 2 | 93 | S08 | Motor Control | Drone_ESC | Integration |  | 1, Modify the application note according to review result, 50% complete. 2, Solved two issues in test process for FTF demo show.
WW39 | Richy | Jiang Dengyu, Mao Huan, Richy Ye | 2014-10-04 |  | 5 | 514 | WCT | Wireless Charger | WCT-15W1COLTX | Development |  | 1. Walk-in at Intertek for pre-compliance test of MPA4 and MPA8; after debugging, one MPA4 board can pass all compliance tests; left another four MPA4 boards for further compliance tests and IOP; Checked some issue and got some detailed information of MPA8 for further improvement; 2. Fixed some issues of MPA4 during walk-in: the Power Control test item failed before since the MAX/MIN voltage exceeded the limit, which could be fixed by decreasing Z-gap to 2mm and adjusting PID parameters of phase control; one Guaranteed Power test item with TPR#MP3 could terminate charging when RX switches load from full to tiny and RX rail voltage jumps, which can be fixed by adding an workaround to limit RX rail voltage jump when load decrease a lot; after debugging it could work normally and this item can pass; Q FOD and power loss FOD could work well after calibration and normalization; Maximum voltage limit test item could pass after setting appropriate parameters. 3. Checked some issues of MPA8: the external driver Q factor measurement worked unstably because the driver voltage is too high for TPR#MP3, tried to decrease the driver voltage and it could work well if the RX rail voltage don't exceed 830mv during measurement; there are still some problems of free resonance Q measurement, will do more research based on some signals; some power control test items still couldn't pass, need more research.
WW39 | Richy
WW39 | Richy
WW39 | XD | Hu Teng | 2016-01-09 |  | 1 | 9 | Kinetis W | WirelessConnectivity/IoT | FTF Demo |  |  | Last test before our boards shipped to FTF, fixed little bugs
WW39 | XD
WW39 | XD
WW39 | XD
WW39 | XD
WW39 | XD
WW39 | XD
WW39 | XD

## Others
Week | Team | Apps Engineer | Open Date | Close Date | Effort (man- days) | Total Effort | Item | Segment | Family | Part | Module | Tools | Request brief | Overal Progress | Input Source
WW39 | Sherry
WW39 | Sherry
WW39 | Sherry
WW39 | Sherry
WW39 | William | Guojia | 2016-09-19 |  | 5 | 5 |  |  | Kinetis L | L5K |  |  | Set up the dual core use case. | 1.Disccussed with sensor team colleagues about the dual core application. And got the feedback that the dual core is not a key feature necessary here. The key feature needed here is to support floating point computation. But on L5K, the dual core is based on CM0+ and CM0+, which lead to a quite big flaw in applications which need intensive computation. 2.Had an internal discussion with Wanghao and we think the main work that we should get done for dual core application is to provide user-friendly demo for customer, in which the synchronization and data communication between the dual core should be covered. 3.Look into the XRDC module and found our RM does not make a clear and easy description about how to use this module.
WW39 | William
WW39 | William
WW39 | William
WW39 | William
WW39 | William
WW39 | William
WW39 | William | YangXi |  |  | 3 | 3 | SWD timing ayalysis and optimzation and offline programmer discuss. |  | Kinetis K | K20 | SPI | KSDK | SWD timing ayalysis and optimzation and offline programmer discuss. | 1. Discuss with BD(Liang Ping) the possible way of increase offline-programmer performance. Come to following conclusion: a. Main bottleneck come from two points: 1. HID USB which max speed only 64KB/s b. SWD implementation is too slow. A packet can take up to 20us. 2. Study ARM’s SWD protocol and change SWD implementation from GPIO to SPI. Performance increased about 34% and is still possible to do further optimization. 3. Draft a summary PPT to introduce SWD protocol and show SPI optimization technical detail.
WW39 | William
WW39 | William
WW39 | Eric | Wang Ben | 2016-09-23 |  | 1 | 1 |  |  | i.MX | i.MX6RT |  |  | Develop a test suite for real time performance benchmark for i.MX6RT.Plan first to develop this on KE+ platform in this Q4, then later porting to i.MX6RT next year. | Learned and reviewed the I.MX6RT ADD. | Xinyu Chen
WW39 | Eric | Can Nan | 2016-09-20 | 2016-09-21 | 2 | 2 | [6 empty] | New Hire Boot-Camp on September | 1.Marketing Training 1 - S&C 2.Marketing Training 2-RF Power 3.Marketing Training 3- Digital Networking 4.Marketing Training 4- Automotive MCU 5.Legal 6.Reimbursement policy and process 7.IT, Attendance Record system , HR Rewards
WW39 | Eric | Shi Changhao | 2016-09-21 | 2016-09-22 | 1 | 1 | KW41 CAS training | [6 empty] | Gave the KW41 training per CAS team's request, it cost several day for preparing the slides and the lesson is about 3 hours, basically focus on hardware design and system design level.
WW39 | Eric | Terry Lv | 2016-09-22 | 2016-09-22 | 1 | 1 | KW41 CAS training | [6 empty] | Attend BLE/Thread training. Got feedback from CAS that a blackbox BLE/Thread library is requirement for China market.
WW39 | Richy
WW39 | Richy
WW39 | Richy
WW39 | Richy
WW39 | Richy
WW39 | Richy
WW39 | Richy
WW39 | Richy
WW39 | Richy
WW39 | XD | Hu Teng | 14/9/2016 |  | 3 | 5 | Kinetis W |  | WirelessConnectivity/IoT |  |  |  | CAS Training | Prepare CAS Training, and test latest KW41 Software release meanwhile
WW39 | XD | Hu Teng | 21/9/2016 |  | 2 | 2 | Kinetis W |  | WirelessConnectivity/IoT |  |  |  | CAS Training | CAS Training
WW39 | XD

## List_Def
Team | Segment | Family | Part | Customer Phase | Reference Phase | NPI Phase | Module | Tools | Root cause | Solution | Support Type | Source | Enablement Task | Support Region
KM | Automotive | S08 | i.MX53 | Early Evaluation | Design | Concept | USB | KSDK | Ctm S/W defect | Fix - Erata/JIRA | General | FAE | Documentation - Data Sheet | Japan
Sherry | Consumer/Communication | CF | KM34Z64 | DI | Development | Feasibility | ADC | PEx | Ctm H/W defect_D | Workaround | Key | BD_MKT | Documentation - Errata | Korea
Manish | Industry | DSC | KM34Z256 | DW | Integration | Plan | I2C | MQX | EMC | Customization | Professional Service | NPI_MKT | Documentation - RM | Great China
Lily | eReader | Kinetis L | KM34Z128 | Pilot | Reference Release | Execution | SPI | Linux | Design issue | Demo/Reference | Leverage | Sales | Documentation - Application Notes | Globe Transition
Robin | Security | Kinetis E | KL17 | MP | SoW | Launching | TSI | Android | Design limitation | Benchmark | BD Activity | Unknown | Documentation - Others | Community
Richy | Wireless Charger | Kinetis M | KM14Z64 | DL | Lib Release |  | AFE | WinCE | RM defect |  |  | CQI | System Cases | NA
William | Motor Control | Kinetis V | ​MK60DN512 |  | Documentation |  | GPIO | CW10.6 | DS defect |  |  |  | System Engineering
Eric | Digital Power | Kinetis K | MC56F82313 |  | Testing |  | ENET | IAR | System improvement |  |  |  | Board - Design
XD | WirelessConnectivity/IoT | Kinetis X | MC9S08PT16AVLD |  |  |  | QTimer |  | Driver issue |  |  |  | Board - FAT Coding & test
| Smart Grid | Kinetis W | MK64FN1M |  |  |  | JTAG |  | Ref board issue |  |  |  | Board - Document
| Industry-Touch | i.MX | MWCT1012CFM |  |  |  | FLASH |  | New Requirement |  |  |  | Certification - USB
| Industry-HomeAppliance | WCT | MKE02Z32 |  |  |  | UART |  | SW issue |  |  |  | Certification - Others
| Power | WCR | MC56F82723 |  |  |  | I2S | [5 empty] | Training
|  |  | MC9S08SD8 |  |  |  | DAC | [5 empty] | Alpha Customer Support
|  |  | KL16Z128 |  |  |  | FlexIO | [5 empty] | Tools Support
|  |  | KE18Z |  |  |  | LPIT | [5 empty] | Bug analysis support
|  |  | MKV10Z32VFM7 |  |  |  | LPTimer | [5 empty] | SDK Driver
|  |  | KE18F512VLL15 |  |  |  | LPTPM | [5 empty] | System EMC
|  |  | MC56F84789 |  |  |  | Flextimer | [5 empty] | System Cases-KPET
|  |  | MC9S08PA16AVWJ |  |  |  | PWT | [5 empty] | System Cases-BLDC demo
|  |  | MT512P |  |  |  | PDB | [5 empty] | System Cases-Peripheral adder
|  |  | KE15Z |  |  |  | PIT | [5 empty] | Board - OOBE
|  |  | KL17Z32VFM4 |  |  |  | eFlexPWM
|  |  | MC9S08SU16 |  |  |  | DMA
|  |  | i.MX6RT |  |  |  | WDOG
|  |  | KW41 |  |  |  | EWM
|  |  | K81/i.MX6UL |  |  |  | SIM
|  |  | KE06 |  |  |  | MCG
|  |  | KL02 |  |  |  | SCG
|  |  | KS22F256N |  |  |  | OSC
|  |  | K81 |  |  |  | ICS
|  |  | MC9S08LL16 |  |  |  | LLWU
RCM
PMC
SMC
SAI
RTC
CRC
CAN
ESDHC
ACMP
VREF
DryICE
RNGA/TRNG
CMT
QDecoder
AMP
DDR
LCD
KBI
FlexNVM
IRQ
FlexBus
CM0+
CM4
CACHE
OPAMP
bootROM
Radio
Note on L2: Author: General Customer Support
Note on L3: Author: Key Customer Support
Note on L4: Author: Professional Service
Note on E5: Author: pre mass production
Note on L5: Author: Leverage to general base from customer support
Note on N8: support enablement tools such as register header files validation, debugger svd file validation and etc
Note on N9: support PE/design to do bench test on bugs