## Customer Support
Week | Team | Apps Engineer | Effort (man- days) | Total Effort | Segment | Customer | Family | Part | Customer Phase | MP Date | Product | LTR ($M) | GIBC | Module | Tools | Request brief | Progress record | Root cause | Solution | Support Type | Support Region | Input Source | Community Link (Mandatory)
WW40 | Sherry | T.C. Lun | 3.5 | 14.5 | Industry-HomeAppliance | Galanz | Kinetis | KE02 | DI |  | Mircowave Oven |  |  |  |  | EMC problem solving |  Found one old high frequency probe for further analysis. Checked the high frequency probe function and it seems OK but there are some sensitive problem when we calibrate it in spectrum analyzer. Since we have not network analyzer for further test and check. We may need to send it back to the manufacturer to check later. On the other hand, we used it to check the difference between the VDD pin in two KE02 boards with two difference SMPS (LNK364 and LC1206A). We found that there are some difference spectrum components between two boards. In KE02 with LNK364 board, frequency components are located below 50MHz with higher noise power (e.g. 13MHz @-42dBm). In KE02 with LC1206A board, frequency components are located below 100MHz with related lower noise power (e.g. 17MHz @-59dBm, 33.6MHz @-60dBm and 68MHz @-56dBm). Further study and analysis are needed to find the difference such as noise ripple and PSRR figure later. |  | hardware design review, evaluation report with recommendations | Professional Service | Great China | Marketer (Alex Zhang, alex.zhang@nxp.com)
WW40 | Sherry
WW40 | Sherry
WW40 | Sherry
WW40 | Sherry
WW40 | William
WW40 | william | Wang Hao | 0.5 | 0.5 |  | Juniper networks | Kinetis K | MK22FN512CAP12R | Early Evaluation |  |  |  |  | I2C | KSDK | Customer wants to know I2C capablity to run 400kbps with 1.8V I/O. | Customer requested to know I2C module's capability to run 400kbps with 1.8V I/O. Our DS added some notes that to run with 1.8V I/O, high drive pins are needed, which caused customer's concern. Also they wanted to know for their cap loading of 80pF, which pullup resistor value is appropriate. Provided explanation on how to calculate the min and max Rpu based on cap loading on I2C bus and pad driving capability. Found the note about high drive pins are needed for 1.8V case may not be right. Still checking with design team on this. Confirmed from design team that HDRS bit inside I2C module to enable high drive pin does not work, instead user should choose port register control bit. This requires RM update for Kinetis devices. Also raised JIRA request KPSDK-12701 for software team to update I2C driver code. |  |  | General | Community | Sales (Michael Goudey) | https://community.nxp.com/thread/435467
WW40 | William | Wang Hao | 0.5 | 0.5 |  | Foxlink | Kinetis L | KL27Z128 | DI |  | USB HID Mouse | 0.15 | 1-21RRXAG | USB | KSDK | Customer needed demo to show remote wakeup feature of HID mouse. | Work on porting remote wakeup demo from TWR-K65 to FRDM-KL43 board. |  |  | General | Community | SE (Ethan Cheng) | https://community.nxp.com/message/836548
WW40 | william | william | 0.5 | 0.5 | Industry-HomeAppliance | MIDEA | S08 | S08LL16 | MP |  | Remote Controller |  |  | OSC |  | 32KHz crystal startup issue reported by customer/FAE, need root cause | As follow-up of crystal startup issue, supported analog design to measure the capacitance of the crystal path on board (borrowed one high precision LCR meter from TSO), and provided data to design. It looks like too much load on crystal, and pending IP owner’s comments. | Design limitation | Customization | Key | Great China | FAE (Sam Wang/Qin K.H) | https://community.nxp.com/message/833281?commentID=833281&et=notification.mention#comment-833281
WW40 | william | YangXi | 3 | 3 | Industry | SANTROL | Kinetis E | KE02 | Pilot |  | E-Bike | 2 |  | ICS | KSDK | Offline programmer for KE02 which support internal clock trim function | Customer need a cheap solution for production programming which need support KE02 ICS trim function. Update FRDM-K64 based offline-programmer software and also flash algorithm to support KE0x series. Done. Current issue: 1. Flash algorithm cannot support KE02’s EEPORM yet. 2. The trim method use a SWD_CLK pin to configure as RTCO for measure ICS internal reference clock frequency, which means the SWC_CLK pin is multiplexing to SWD and RTCO. It could cause some issue if write KE02 register directly via SWD. The RTCO cannot output clock signal . if download a program to flash, all works OK. Still investigating the root cause. |  | Customization | General | Great China | FAE (JiCheng) | https://community.nxp.com/message/837835?commentID=837835&et=watches.email.thread#comment-837835
WW40 | william
WW40 | William
WW40 | William
WW40 | William
WW40 | William
WW40 | William
WW40 | Eric | Shi Changhao, Terry Lv | 2 | 49.5 | WirelessConnectivity/IoT | LG/VW | Kinetis W | KW41 | Early Evaluation |  | Car BLE/WIFI Dual Anteana System | 12M |  | Radio | IAR | Got patch from Connectivity Software Team to enable STOP mode in ADV and SCAN and do a full test. | LGE required the comunication distance should reach 50 meter, though communication with USA team, we started to do some baseline test using external dipole antenna.1) buy the external diple 2.4G antenna from internet.2)test in real environment to calculate PER using different data length.3) sent the test report to Khuram for feedback. | New Requirement | Customization | General | Great China | FAE(Thomas Kang) | https://community.nxp.com/message/665311
WW40 | Eric
WW40 | Eric
WW40 | Eric
WW40 | Eric
WW40 | Eric
WW40 | Eric
WW40 | Richy | Kevin Cheng | 2 | 5 | Digital Power | Liteon | DSC | MC56F82748 | Early Evaluation |  | Digital Power supply |  |  |  |  | NXP power solution survey | Studing PFC side firmware details for reference design promotion |  | Demo/Reference | Key | Great China | FAE(Jiunn Yang)
WW40 | Richy | Kevin Cheng | 0.5 | 0.5 | Digital Power | Liteon | Kinetis L | MKL16 | DI |  | DP housekeeping |  |  |  |  | I2C time out period estimation | Customer asked how to estimate the SCL high time out period, their kinetis L is now facing problem on frequently interrrupt request which takes lot of cpu time. Provide estimation result to FAE, need confirm it on FRDM-KL25Z. |  |  |  | Great China | FAE(Jiunn Yang)
WW40 | Richy | Ethan Cheng | 2 | 5 | Consumer/Communication | Foxlink | Kinetis L | KL27Z128 | DI |  | USB HID Mouse | 0.15 | 1-21RRXAG | USB | KSDK | Problem on KL27 USB Remore Wakeup function | Got the sample code of TWR-K65 HID Mouse Suspend Resume Demo from Shanghai AE team. This remote wakeup example for USB HID device will be added into the future USB stack release. Investigated this remote wakeup function enablement and Wang Hao is supporting to port this demo to FRDM-KL43 board. | New Requirement | Demo/Reference | General | Great China | FAE (Stanley Huang-B42861)
WW40 | Richy | Li Shunan | 0.5 | 6 | Motor Control | Fromot-elec Jiangyin | DSC | MC56F84442 | DI |  | Stepper Motor Driver |  |  | System | CW10.6 |  | Reviewed the version 2 schematic designed by customer. | Ctm H/W defect_D | Customization | General | Great China | FAE - Cherrish Liao
WW40 | Richy | Richy Ye, Jiang Dengyu, Mao Huan, Wang Li | 1 | 100 | Wireless Charger | LG IT | WCT | MWCT1111CLH | MP |  | 15W 1COIL TX | $1.70 | 1-FFWPV2 |  | CW10.6 | Customer want a solution of WPC+PMA based on WCT1111 | 1.LGIT reported an LED issue. In long time test of 1000 hours. 2 of 10 samples are found the issue that charging continues while the LED turns to red status. Considering the possiability of fault statuses reason, simulated all the error codes in charging state, but can't replicate the fault LED status. Since the issue is quite hard to be replicated, we have required customer provie more details in their test. The debug work is ongoing; 2. (Highlight) The Belkin's module has got the 1.2.2 QI certification. This is the first MP Tx product meeting the 1.2.2 spec. |  | Customization | Key | Korea | FAE (Kate Lee - B45752)
WW40 | Richy | Wang Dechang, Jiang Dengyu, Zhao Ping, Wang Li | 1 | 9 | Wireless Charger | Mobis | WCT | WCT1011A WCT1013A | DI |  | 15W Auto TX |  |  |  | CW10.6 | Board bebug support. | 1. Customer reported the effeciency is lower than before when using the new released F/W. By debugging this issue, found the root cause is the setting of the I/O port for controlling the discharing resistance of Vrail. The configuration should be right according to the schematic, however, customer reworked the board, making another pin to control the discharging circuit, which makes the resistance always be connected, so the effeciency is decreased. The new configuration file is updated for customer test now; 2. Tested the reset issue when charging, but can't replicate it with WPR1500 Rxs. Since customer momitored the issue with IDT MP Rx, have required them to send the Rx for test; 3. Communicated with FAE for cusomter's schedule, prepare to release the next full function version code before 10/21. | New Requirement | Customization | General | Korea | FAE (Kate Lee - B45752)
WW40 | Richy | Wang Li, Jiang Dengyu, Wang Dechang, Zhao Ping | 1.5 | 8.5 | Wireless Charger | Seoyon | WCT | WCT1111 | Early Evaluation |  | 15W_TXMULTI |  |  |  | CW10.6 | Board bringup . | 1.As customer required, merged the fast charging function for Samsung phone, and opened the API for DDM packet modification. The new F/W is released for test now. | New Requirement | Customization | General | Korea | FAE (Kate Lee - B45752)
WW40 | Richy | Ding Wenshuang | 2 | 14 | Motor Control | zhanyu | Kinetis E | MKE02Z32 | DI |  | PMSM FAN |  |  |  | IAR | Debug PMSM FOC solution based on customer's board. | 1,FAE report one issue that the motor rotor shakes during the align state. Reduced the align current and increased the align period. Updated the code with latest version. Have sent the code to FAE to demonstrate to customer. | New Requirement | Customization | General | Great China | FAE(Cherrish liao-R65774)
WW40 | Richy | Gao Xiang | 2 | 14 | Wireless Charger | Magic-Link | WPR | WPR1516 | DW |  | Wireless charger Rx |  | 1-1OU7KWR |  | IAR | Customer board debugging | Debug customer's new completed high voltage output board, verified 5V, 9V and 12V can output successfully with 15W loading and 3 output port switch function working correctly. |  | Customization | Key | Great China | FAE (Yu Ningning-B45276)
WW40 | Richy
WW40 | Richy
WW40 | Richy
WW40 | Richy
WW40 | Richy
WW40 | Richy
WW40 | Richy
WW40 | Richy
WW40 | Richy
WW40 | Richy
WW40 | Richy
WW40 | Richy
WW40 | Richy
WW40 | Richy
WW40 | Richy
WW40 | Richy
WW40 | XD | Chu Hongdong | 2 | 56 | ePOS/Security | Landi | i.MX | i.MX6UL |  |  | ePOS | 500K | #1-1PPBZ7A | HAB,CAAM,SNVS,Dryice,BEE | Yocto | Implement security features. | Landi reported that hash result is not correct in some cases on HAB board, the issue is fixed and the patch has been sent to Landi. |  | Customization | Key | Great China
WW40 | XD | Chu Hongdong | 3 | 4 | ePOS/Security | PAX | i.MX | i.MX6UL | Early Evaluation |  | ePOS |  |  | HAB | Yocto | CST tools. | Write a simple tool to sign the u-boot image, and test the signature generated by the tool on HAB board. PAX can use it as a reference to develop their own code signing tool. |  | Customization | Key | Great China
WW40 | XD | Yang Zhao | 3 | 3 | Security | Landi | Kinetis K | k81 | [7 empty] | Issue of GCM&CCM algorithm in ksdk2.0 | 1. Since the engineer of landi doubt that the AES_GCM algorithm has problem,I test the algorithm and compare the result with the successful one(the successful result is from freedom k64 ). At last found that the result are the same. So I think our algorithm is ok. 2.landi engineer send the tls package to us and help him to find the root cause. They also want to get the performace of the secruity hardware accelerate of KSDK. Next step is to test the KSDK and send to Landi. |  | Customization | Key
WW40 | XD | Yang Zhao | 2 | 2 | Security | 武汉天喻 | Kinetis K | k81 | [7 empty] | Memory leak of SM2 | 1. Customer feedback that the code of SM2 will have the hardfault issue if test more than 50 times. 2. Reproduce the issue and build a new lib and sent to FAE |  | Customization | Key
WW40 | XD
WW40 | XD
WW40 | XD
WW40 | XD
WW40 | XD
WW40 | XD

## Apps Lead
Week | Team | Apps Engineer | Open Date | Close Date | Effort (man- days) | Total Effort | Family | Project | NPI Phase | Next Apps Milestone | TO Date | Enablement Task | Highlight/Lowlight/Issues/Risks | Progress record
WW40 | Sherry
WW40 | Sherry
WW40 | Sherry
WW40 | william | Wang Peng | 2016-08-10 |  | 1.5 | 15.5 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases |  | Find the root cause of big current on TSI adder, which configure one TSI channel as GPIO and output high, and when trigger TSI, also see the similar waveform on this pad and get the big current(about 8mA), feedback to IP design to confirm it.
WW40 | william | wang Peng | 2016-03-25 |  | 1 | 7.5 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | Finish the adder code modification of ADC,CMP,PDB and CRC, support clock select so that get the adder with different function clock.
WW40 | william | Wang Hao | 2016-05-30 |  | 2 | 34 | Kinetis K | K4TV | Execution |  | 2016-08-12 | System Cases |  | Prepare slides for comparison between MMCAU and CAUv3 module. Spent time to study performance monitor inside Cortex A7 core for checking any similarity with K4TV PM module.
WW40 | william | Jia Ding | 2016-08-01 |  | 4 | 17 | Kinetis K | K4TV | Execution |  |  | System Cases |  | Continued the pre-coding of the FlexSPI drivers and demos. About 40% has been finished.
WW40 | william
WW40 | william
WW40 | william
WW40 | Eric | Cao Nan | 2016-06-24 |  | 5 | 112.5 | Kinetis E | KE15Z | Execution |  | Q4'15 | System Cases-KPET |  | 1.Finished the dynamic association the result with different clock source and power mode .We can write the new func clocks data to the database once the BACES team finished test. 2.TSI test result form BACES team had been wrote to the KPET database(5V). 3.Starting test the LPIT ,LPTMR adder value in 8M,4M,2M,1M. 4.Verifiying some cases on BACES board and FRDM board to co-work with BACES team and ATE test.
WW40 | Eric | Yizhou Fang/Changhao Shi | 2016-08-19 |  | 4 | 24 | i.MX | i.MX6RT | Feasibility |  | Q1'17 | System Engineering |  | 1. Planning summit. Deliver application plan and confirm questions to other teams. 2. i.MX6 RT agile part set up and review. 3. Start i.MX 6RT FPGA board design.
WW40 | Eric | Chen Yonggang | 2016-09-26 | 2016-09-30 | 6 | 60 | Kinetis E | KE15Z | Execution | TSI AN on 10/28 | Q4'15 | System Cases-KPET |  | 1. Attended Shenzhen FTF for touch demo. Many customer engineers came and watched the touch demo, including Haier, Glanz, etc. The customer requirements of touch MCU are low price and small package/flash size. 2. Debugged the big current consumption problem for the TSI mutual mode together with Design team, and found out the root cause is TSI IP pull down all Tx channels in mutual mode, which caused big current consumption when the related pin is configured as GPIO output high. Created the ticket TKT316157 in designPDM and TSI designer will fix this problem at the next IP version, but for now MT256 won't fix this problem immediately.
WW40 | Eric
WW40 | Eric
WW40 | Eric
WW40 | Eric
WW40 | Richy | Richy Ye, Li Shunan | 2016-04-27 |  | 1 | 6 | i.MX | i.MX6RT | Planning |  | Q1'17 | System Cases |  | Aligned with NPI marketer about motor control reference for 6RT, 3D printer with robot arm is proposed with 4 motors control on single chip. Completed the CCB slides to add the additional 6kUS$ for the proposed reference.
WW40 | Richy
WW40 | Richy
WW40 | XD
WW40 | XD
WW40 | XD
WW40 | XD
WW40 | XD

## Reference Design
Week | Team | Apps Engineer | Open Date | Close Date | Effort (man- days) | Total Effort | Family | Segment | Project | Reference Phase | Milestone Date | Progress record
WW40 | Sherry
WW40 | Sherry
WW40 | Sherry
WW40 | William
WW40 | William
WW40 | William
WW40 | William
WW40 | William
WW40 | William
WW40 | William
WW40 | William
WW40 | William
WW40 | William
WW40 | William
WW40 | Eric | Shi Changhao, Terry Lv | 2015-11-16 |  | 1 | 172 | Kinetis W | WirelessConnectivity/IoT | Smart Home | Development |  | 1. Sent the smart lock reference demo to Shenzhen FTF and online support the question and feedback.
WW40 | Eric
WW40 | Eric
WW40 | Eric
WW40 | Eric
WW40 | Eric
WW40 | Richy | Wang Dechang, Jiang Dengyu, Wang Li, Zhao Ping, Richy Ye | 2015-11-25 |  | 8 | 126 | WCT | Wireless Charger | WCT-15WTXAUTO | Design |  | 1, 15W automotive transmitter silicon MWCT101xA was launched during FTF. http://www.nxp.com/products/power-management/wireless-charging-ics/15-watt-wireless-charging-transmitter-ics-for-automotive-applications:MWCT1x1xA?lang_cd=en. 2, Porting NFC stack. Project was compiled successfully. But the I2C driver was for touch feature, will modify the driver code. 3, Tested WCT101xA service pack. WCT101A had no issue, but the mem file for WCT1013A was not right. 4, Froze the WCT-15WTXAUTO Rev B design documents, and released the design documents into agile system( layout documents(A080), schematic documents(A085)); 5, During the debug it’s found the secondary OVP is easy to false trigger on the center coil with smallest Z-gap with WPR1500 BUCK, this issue is caused by good coil coupling between TX coil and RX coil and can be solved by increasing Z-gap a little. In the future if NFC antenna board is implemented, the Z-GAP will be enough. And more research will be done in the following. 6, Prepared boards with basic charging for customer promotion: (1) Prepared one WCT-15WTXAUTO board with WCT1011A to Vaclav;(2) Prepared one WCT-15WTXAUTO board with WCT1013A to Delphi US;(3) Prepared one WCT-15WTXAUTO board with WCT1013A to Fouyou;
WW40 | Richy | Richy Ye, Wang Dechang, Jiang Dengyu, Kevin Cheng, Gao Xiang, Wang Lingling | 2015-03-23 |  | 2 | 220.5 | DSC | Digital Power | Golden Server Power | Design |  | 1,The hardware burst mode simulation completed, the system can enter and exist the burst mode as expected. 2，Study the the DSC reference manual and data sheet for the implementation of hardware burst mode for power saving.
WW40 | Richy | Liu Zhen Ding Wenshuang | 2015-08-25 |  | 3 | 97 | S08 | Motor Control | SU16 E-Drone | Development |  | 1, FTF engineer report one bug that sometimes motor can't startup during test. Repeat testing in Suzhou lab for many times and there is no repetition, will continue to debug it later. 2,Marketing want to make another 200 pcs boards for SU16 global release.Have sent the latest schematic and bom out for quotation. 3, FAE report one issue that the SU16 chip damaged during the demonstration to customer in high speed, Doubt about the GDU's drive ability. Will do high speed and big current test to verify this issue next week.
WW40 | Richy | Wang Dechang, Zhang Yangjie, Richy Ye, Gao Xiang, Wang Lingling | 2015-08-06 |  | 8 | 524 | DSC | Digital Power | Golden Server Power-Totem Pole BLPFC | Design |  | 1.Removed the software current filter, now the new version is able to run under AC source and E-load.(SH) Test under new version with maximum power 600W(Efficiency up to 98.1%)and update power factor and THDi can both meet the requirements. 2.Final revision DRM has been provided to the documnet team for review. 3. Have a meeting to discuss of the transferring of light load and normal load logic, and make this feature stable to meet the design requirement.
WW40 | Richy
WW40 | Richy
WW40 | Richy
WW40 | Richy
WW40 | Richy
WW40 | Richy
WW40 | XD
WW40 | XD
WW40 | XD
WW40 | XD
WW40 | XD
WW40 | XD
WW40 | XD
WW40 | XD

## Others
Week | Team | Apps Engineer | Open Date | Close Date | Effort (man- days) | Total Effort | Item | Segment | Family | Part | Module | Tools | Request brief | Overal Progress | Input Source
WW40 | Sherry | T.C. Lun | 2015-01-12 |  | 1.5 | 16 | EMC Tools Maintenance (Tools repair, software renewal, ESD gun replacement) | [5 empty] | EMC maintenance |  Setup and install software in the i7 DELL NB is in progress.  Over 20 common use TVS parts are selected and placed the simple order from our standard part group for use of EMC support. Received portion of those parts and will received all in coming few weeks.
WW40 | Sherry
WW40 | Sherry
WW40 | Sherry
WW40 | William | Guo Jia | 2016-09-19 |  | 5 | 10 |  |  | Kinetis L | L5K |  |  | Accumulate the knowledge for dual core application as the preparation for the L5K dual core NPI. 1. Look into the KL28T RM and SDKA2.0 code related with dual core application. 2. Related concepts include: MU, SEMA42, XRDC, ERPC, RPMSG.
WW40 | William | Wang Hao | 2016-09-26 | 2016-09-27 | 1 | 1 |  | Motor Control | Kinetis E | KE02 |  |  | Applied blackduck to scan three motor control projects for any license issues. |  | SE (Ding wenshuang)
WW40 | William | Jia Ding | 2016-09-29 | 2016-09-29 | 0.5 | 0.5 | NXP Design | Industry-HomeAppliance | Kinetis L | KL28Z | FlexIO |  | Drew system block diagrams for the previous FTF demos FlexIO-8080-LCD and FlexIO-Camera for the NXP design web pages show. |  | Web team
WW40 | William | Zhong Juying | 2016-10-26 |  | 3 | 3 | technical sharing - Differential power analysis | [5 empty] | wrote 90% of technical sharing PPT - Differential power analysis
WW40 | William | Zhong Juying | 2016-10-26 |  | 2 | 2 | technical sharing - Security architecture introduction | [5 empty] | wrote 80% of technical sharing PPT - Security architecture introduction
WW40 | William
WW40 | William
WW40 | William
WW40 | William
WW40 | William
WW40 | Eric
WW40 | Eric
WW40 | Eric
WW40 | Eric
WW40 | Richy | Richy Ye, Zhou Xuwei, Howard Liu | 2016-09-13 | 2016-09-29 | 7 | 12 | FTF China 2016 | [5 empty] | Attend FTF | 1, Presented two sessions about KV5x and digital energy conversion solutions, 3 audience for each session. 2, Demo worker for wireless charging and digital power supply demos, had interview with Taiwan media to introduce NXP 15W wireless charging solution as this is announced by Geoff during FTF. 3, Demo workers for motor control demos including SU16 ESC, KMS, DSC dual servo motors and 3in1 on KE1x. 4, Joined 3 customer meeting for wireless charging and digital power projects.
WW40 | Richy | Li Shunan | 2016-09-28 |  | 2.5 | 2.5 | Support designer for ENC module update |  | DSC |  |  | CW10.6 | Make suggestions for ENC module | Make a slides about suggestions for ENC module based on our patent “improved speed measurement method with low-cost incremental encoder”
WW40 | Richy
WW40 | Richy
WW40 | Richy
WW40 | Richy
WW40 | Richy
WW40 | Richy
WW40 | Richy
WW40 | XD | Yang Zhao | 2016-09-12 |  | 2 | 2 | Secruity |  | Kinetis K |  | IAR |  | Optimize the mbedtls code of KSDK 2.0 | Test the ecdsa and ecdh function of the KSDK 2.0 . There are 11 elliptic curves turns out to be OK.
WW40 | XD | Liu Weiping | 2016-06-13 |  | 4 | 51.5 | POS solution |  | i.MX |  |  |  |  | 1.Wrote some demo applications for CAAM AES & DES. 2. Read the sec boot doc about i.mx6ul.
WW40 | XD

## List_Def
Team | Segment | Family | Part | Customer Phase | Reference Phase | NPI Phase | Module | Tools | Root cause | Solution | Support Type | Source | Enablement Task | Support Region
KM | Automotive | S08 | i.MX53 | Early Evaluation | Design | Concept | USB | KSDK | Ctm S/W defect | Fix - Erata/JIRA | General | FAE | Documentation - Data Sheet | Japan
Sherry | Consumer/Communication | CF | KM34Z64 | DI | Development | Feasibility | ADC | PEx | Ctm H/W defect_D | Workaround | Key | BD_MKT | Documentation - Errata | Korea
Manish | Industry | DSC | KM34Z256 | DW | Integration | Plan | I2C | MQX | EMC | Customization | Professional Service | NPI_MKT | Documentation - RM | Great China
Lily | eReader | Kinetis L | KM34Z128 | Pilot | Reference Release | Execution | SPI | Linux | Design issue | Demo/Reference | Leverage | Sales | Documentation - Application Notes | Globe Transition
Robin | Security | Kinetis E | KL17 | MP | SoW | Launching | TSI | Android | Design limitation | Benchmark | BD Activity | Unknown | Documentation - Others | Community
Richy | Wireless Charger | Kinetis M | KM14Z64 | DL | Lib Release |  | AFE | WinCE | RM defect |  |  | CQI | System Cases | NA
William | Motor Control | Kinetis V | ​MK60DN512 |  | Documentation |  | GPIO | CW10.6 | DS defect |  |  |  | System Engineering
Eric | Digital Power | Kinetis K | MC56F82313 |  | Testing |  | ENET | IAR | System improvement |  |  |  | Board - Design
XD | WirelessConnectivity/IoT | Kinetis X | MC9S08PT16AVLD |  |  |  | QTimer |  | Driver issue |  |  |  | Board - FAT Coding & test
| Smart Grid | Kinetis W | MK64FN1M |  |  |  | JTAG |  | Ref board issue |  |  |  | Board - Document
| Industry-Touch | i.MX | MWCT1012CFM |  |  |  | FLASH |  | New Requirement |  |  |  | Certification - USB
| Industry-HomeAppliance | WCT | MKE02Z32 |  |  |  | UART |  | SW issue |  |  |  | Certification - Others
| Power | WCR | MC56F82723 |  |  |  | I2S | [5 empty] | Training
|  |  | MC9S08SD8 |  |  |  | DAC | [5 empty] | Alpha Customer Support
|  |  | KL16Z128 |  |  |  | FlexIO | [5 empty] | Tools Support
|  |  | KE18Z |  |  |  | LPIT | [5 empty] | Bug analysis support
|  |  | MKV10Z32VFM7 |  |  |  | LPTimer | [5 empty] | SDK Driver
|  |  | KE18F512VLL15 |  |  |  | LPTPM | [5 empty] | System EMC
|  |  | MC56F84789 |  |  |  | Flextimer | [5 empty] | System Cases-KPET
|  |  | MC9S08PA16AVWJ |  |  |  | PWT | [5 empty] | System Cases-BLDC demo
|  |  | MT512P |  |  |  | PDB | [5 empty] | System Cases-Peripheral adder
|  |  | KE15Z |  |  |  | PIT | [5 empty] | Board - OOBE
|  |  | KL17Z32VFM4 |  |  |  | eFlexPWM
|  |  | MC9S08SU16 |  |  |  | DMA
|  |  | i.MX6RT |  |  |  | WDOG
|  |  | KW41 |  |  |  | EWM
|  |  | K81/i.MX6UL |  |  |  | SIM
|  |  | KE06 |  |  |  | MCG
|  |  | KL02 |  |  |  | SCG
|  |  | KS22F256N |  |  |  | OSC
|  |  | K81 |  |  |  | ICS
LLWU
RCM
PMC
SMC
SAI
RTC
CRC
CAN
ESDHC
ACMP
VREF
DryICE
RNGA/TRNG
CMT
QDecoder
AMP
DDR
LCD
KBI
FlexNVM
IRQ
FlexBus
CM0+
CM4
CACHE
OPAMP
bootROM
Radio
Note on L2: Author: General Customer Support
Note on L3: Author: Key Customer Support
Note on L4: Author: Professional Service
Note on E5: Author: pre mass production
Note on L5: Author: Leverage to general base from customer support
Note on N8: support enablement tools such as register header files validation, debugger svd file validation and etc
Note on N9: support PE/design to do bench test on bugs